## 4. NIPWG WORK PLAN 2018-19

**Tasks**

|  |  |
| --- | --- |
| D | Maintain Publication S-12 “Standardization of List of Lights and Fog Signals” (IHO Task 2.8.1) |
| E | Maintain Publication S-49 “Recommendations concerning Mariners’ Routeing Guides” (IHO Task 2.8.3) |
| F | Establish and monitor, in liaison with the S-100WG, the project teams required to specify and develop nautical information layers for use in ECDIS (IHO Task 2.3) |
| G | Develop high level specifications for a combined Marine Service Portfolio (MSP) covering the provision of hydrographic services to mariners in accordance with the IMO e-navigation strategy implementation plan (IHO Task 2.5.2) |
| H | Develop a test and implementation plan for the development of the MSP “hydrographic services” (IHO Task 2.5.2) |
| I | Maintain IHO Resolutions in M-3 relating to Nautical Publications as required (IHO Task 2.1) |
| J | Liaise with other HSSC WGs and other IHO and international bodies (IHO Task 2.1) |
| K | Conduct the 2017 and 2018 meetings of the NIPWG and its sub-group(s) and project team(s) (IHO Task 2.1) |

**Work items**

| **Work item** | **Title** | **Priority**H-high M-mediumL-low | **Next Milestone** | **Start Date** | **End Date** | **Status**P-PlannedO-OngoingC-Completed S-superseded | **Contact Person(s)** | **Related Pubs / Standard** | **Remarks** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| D.1 | Monitor and assess proposals for amending S- 12 | M | Next meeting | 2014 | Permanent | O |  | S-12 | In close liaison with IALA; see J.5.1 |
| F.1 | Assess the progress and perspectives of developing specifications for NP data layers in ECDIS and propose the way forward for consideration by HSSC | H |  | 2015 | Permanent | O |  |  | To be considered in the context of the IMO e-navigation strategy implementation.NIPWG to consider establishing one or more project team(s) in liaison with S-100WG as required (see J.2), in particular to continue the development of Product Specifications currently assigned to the NIPWG. |
| F.2 | Investigate the interaction between Marine Protected Area Product and ENC in ECDIS | H | Draft Product Specification for Marine Protected Areas (S-122) released in 2018 | 2015 | Permanent | O | Chair/Sec |  | In close liaison with the S-100 WGOn target for endorsement by Council - 2. |
| F.3 | Model the NP data where required. | H | Next meeting | 2004 | Permanent | O | Chair/Sec |  | S-100 related. To be included in Hydro domain of the FCD Register. |
| F.4 | Review of objects and attributes | H | Next meeting | 2004 | Permanent | O | Chair/Sec |  | S-100 related. |
| F.5 | Propose amendments to HYDRO domain of the FCD Register | H |  | 2005 | Permanent | O | Chair/Sec |  | S-100 related. To be included in the FCD register |
| F.8.1 | Develop S-12n - Nautical Information Product Specification |  |  |  |  |  |  |  |  |
| F.8.1.1 | For Radio Services | H | next NIPWG meeting | 2012 | 2019 | O | Chair/Sec | S-123 |  |
| F.8.1.2 | For Navigational services | L | next NIPWG meeting | 2013 |  | P | Chair/Sec | S-125 | On Hold |
| F.8.1.3 | For Traffic management | H | next NIPWG meeting | 2013 | 2021 | O | Chair/Sec | S-127 |  |
| F.8.1.3.1 | For Marine Protected Areas | H | next NIPWG meeting | 2011 | 2019 | O | Chair/Sec | S-122 |  |
| F.8.1.4 | For Physical environment | L | next NIPWG meeting | 2013 |  | P | Chair/Sec | S-126 | On Hold |
| F.8.1.5 | Catalog of nautical products | H | next NIPWG meeting | 2016 | 2021 | O | Chair/Sec | S-128 |  |
| G.1 | Monitor the requirements for and provision of nautical information in e-navigation test-bedsProduce NP1 sample data sets |  |  |  |  |  |  |  | According to the tasks assigned by HSSC4. Collection of information to be modelled |
| G.1.3 | For Traffic management | H | next meeting | 2012 | 2018 | O | Chair/Sec | S-127 |  |
| G.1.4 | For Physical environment | L | next meeting | 2013 |  | O | Chair/Sec | S-126 |  |
| G.3 | Rules and guidelines for displaying nautical information in ECDIS and in combined Marine Service Portfolios |  |  |  |  |  |  |  |  |
| G.3.1 | Develop basic display principles for NP data intended for use in ECDIS (NP3) | H |  | 2008 |  | O | Chair/Sec | S-52 | Close co-operation with NCWG and S-100WG required. Interoperability Spec to be considered. |
| G.3.2 | Monitor and contribute to the development of IMO guidelines showing how navigation information received by communications equipment can be displayed in a harmonized way and what equipment functionality is necessary. | M |  | 2015 | 2019 | O |  | S-52 | e-nav IMO Strategy Implementation Plan, Task T13 (HSSC6-07.1A refers)Output number 5.2.6.2 of NCSR biennial agenda 2016-17 |
| G.5 | Contribute to considering the future of paper charts in the perspective of the establishment of MSPs | M |  | 2014 |  | O |  |  | Subject to request from NCWG |
| I.1 | Maintain and extend resolutions in M-3 relating to Nautical Publications | M | Next meeting | 2012 | Permanent | O | Chair/Sec NIPWG | M-3 | A review is required due for the harmonization of M3 information and potential ProdSpecs content |
| J.0 | Liaise with the NCWG | M |  |  | Permanent | O | Chair/Sec NIPWG |  | Establish joint project teams as required and endorsed by HSSC. |
| J.1 | Liaise with the ENCWG | M |  |  | Permanent | O | Chair/Sec NIPWG |  |  |
| J.2 | Liaise with the S-100WG | H |  |  | Permanent | O | Chair/Sec NIPWG |  | Establish joint project teams as required and endorsed by HSSC. |
| J.2.1 | Draft Data Classification and Encoding Guides |  |  |  |  |  |  |  | Document for NPs similar to Use of the Object Catalog |
| J.2.3 | Draft Product Specification |  |  |  |  |  |  |  |  |
| J.2.3.2 | For Navigational services | L |  | - |  | P | Chair/Sec | S-125 |  |
| J.2.3.3 | For Traffic management | H |  | 2011 | 2021 | O | Chair/Sec | S-127 | Depends on contract award |
| J.2.3.5 | For Physical environment | L |  | - | - | P | Chair/Sec | S-126 |  |
| J.2.3.6 | For Digital Catalog of Nautical Product |  | Next meeting | 2016 | 2021 | O | Chair/Sec | S-128 |  |
| J.3 | Liaise with other HSSC WG  | M |  | 2004 | Permanent | O | Chair/Sec NIPWG |  |  |
| J.4 | Liaise with IRCC |  |  |  |  |  |  |  |  |
| J.4.1 | Liaise with WWNWS Sub-Committee |  |  |  |  |  |  | S-124 | Monitor developments of S-124 Correspondence Group |
| J.5 | Liaise with other international bodies which contribute to nautical information | H |  | 2015 | Permanent | O | Chair/Sec NIPWG |  |  |
| J.5.1 | Liaise with IALA e-Nav Committee | H |  | 2013 | Permanent | O | Chair/Sec NIPWG |  |  |
| J.5.2 | Liaise with International Harbor Masters’ Association | L |  | 2015 | Permanent | O | Chair/Sec NIPWG |  | See outcome HSSC8 Section 7.10 of the minutes |
| J.5.3 | Liaise with International Cable Protection Committee (ICPC) | M |  | 2016 | Permanent | O | Chair/Sec NIPWG |  | MOU signed between IHO and ICPC |

**Meetings** (Task K)

|  |  |  |
| --- | --- | --- |
| **Date** | **Location** | **Activity** |
| 12–16 March 2018 | Genoa, Italy | NIPWG5 |
| Jan 2019 | Rostock, Germany | NIPWG6 |
| Nov 2019 | St. Petersburg, Russian Federation – tbc (fallback Monaco), eventually India (inivitation expected) | NIPWG7 |
| Sept 2020 | Brest (tbc), France  | NIPWG8 |

 Chair: Jens Schröder-Fürstenberg, BSH, GE Email: jens.schroeder-fuerstenberg@bsh.de
 Vice Chair: Edward Hosken, UKHO, UK Email: Edward.Hosken@UKHO.gov.uk
 Secretary: Thomas Loeper, NOAA, USA Email: Thomas.Loeper@noaa.gov