## GBM01_actions
Updated : 8 September 2021
Ref.Doc | Action No. | Title | Status | Remarks
GBM01-01 | Action 1/1 | Parry OEI to consider proposing one more SG member at an early opportunity. | Closed | Confirmed to keep two seats from the host country. Will revisit when necessary.
GBM01-03 | Action1/2 | PO will submit a revised proposal to the next meeting to highlight the need to include a Capacity Building Initiative component. | Closed | It will be considered as a part of the project proposal if deemed necessity
| Action1/3 | Chair proposed to the next meeting by making amendments reflecting the Lab on IHO Organigram. | Completed
| Action1/4 | YB creates an IHO Lab web page and reports the progress to the next meeting | Completed
| Action1/5 | The General Manager drafts the ToR and RoP containing the proposed conceptual document and report it to the next meeting. | Done | Ref. Doc: GBM2_Agenda 5.c
GBM01-04 | Action1/6 | The General Manager reports the project registration website construction plan to the next meeting. | On going
| Action1/7 | The General manager drafts a simplified version of the proposal and reports it to the next meeting | Completed
GBM01-05 | Action1/8 | The General Manager will contact the two project representatives (ENCWG and NIPWG Chairs) to evaluate the adequacy of project performance and report progress to the next meeting. | Completed | Ref. Doc: GBM02-02
GBM01-06 | Action1/9 | Secretary prepares a draft SNS and disclose it to SNS after the review of the members.