**10th MEETING OF THE IHO INTER-REGIONAL COORDINATING COMMITTEE**

**IHO-IRCC10**

**India, Goa, 4-6 June 2018**

**LIST OF ACTIONS**

**(Updated as of 23 November 2018)**

| **N.** | **Action (Agenda item)** | **Responsible** | **Deadline** | **Status** |
| --- | --- | --- | --- | --- |
| 1 | to submit the endorsed amendments to the IRCC ToR and RoP (Annex A) to the Council (4) | Chair | C-2 | DONE |
| 2 | to submit the IHO Resolution 2/1997 as amended (original with small amendments, Annex B) to the Council (6.2) | Chair | C-2 | DONE |
| 3 | to submit draft IHO Resolution 2/1997 as amended (Annex C) to the RHC Members for comments and report back to IRCC (6.2) | RHC Chairs | October 2018 | DONE |
| 4 | to compile the inputs from RHC Chairs to the draft IHO Resolution 2/1997 as amended and distribute to IRCC Members (6.2) | Chair and IHO Secretariat | November 2018 | DONE |
| 5 | to provide comments to the revised draft IHO Resolution 2/1997 as amended (6.2) | IRCC Members | January 2019 | DONE |
| 6 | to submit the updated revised draft IHO Resolution 2/1997 as amended to the next IRCC meeting (6.2) | IHO Secretariat | IRCC11 | DONE |
| 7 | to investigate the possibility to translate the MSI training material developed with resources from the CB Fund from French to Spanish and report back to IRCC (7b) | Spain | IRCC11 | ONGOING |
| 8 | to report the status of MSI in coastal States to the next IRCC meeting (7b) | WWNWS-SC Chair | IRCC11 | DONE |
| 9 | to submit the revised CBSC ToR and RoP (doc. *CBSC16-01D* as amended by Decision 8) as amended by the meeting to the Council (7c) | Chair | C-2 | DONE |
| 10 | to develop basic MSDI training material in order to allow RHCs to deliver trainings with their own personnel (7c) | MSDIWG | IRCC11 | DONE |
| 11 | to install a permanent CB Coordinator and to ensure the participation in the CBSC meetings and to report back to IRCC (7c) | RSAHC Chair | IRCC11 | DONE |
| 12 | to report the Decision 11 to the Council (7d) | Chair | C-2 | DONE |
| 13 | task the IHO Project Team on the implementation of the UN-GGIM Shared Guiding Principles for Geospatial Information Management (PPT) work under its ToR and RoP and to report back to IRCC (7e) | PPT | IRCC11 | ONGOING |
| 14 | to create a web page to present the work of the IHO Project Team on the implementation of the UN-GGIM Shared Guiding Principles for Geospatial Information Management (PPT) (7e) | Secretariat | July 2018 | DONE |
| 15 | to submit the CSB Guidance Document to the Council for endorsement and subsequent approval by Member States (7g) | Chair | C-2 | DONE |
| 16 | to share lessons learned with Rose Points engagement (7g) | USA | IRCC11 |  |
| 17 | to amend IHO Publications S-5A Ed 1.0.1 and S-8A Ed 1.0.0 in accordance with Annex C of doc. *IRCC10-07H* and publish in the IHO website (7h) | Secretariat | July 2018 | DONE |
| 18 | to submit the draft revised IHO Resolution 6/2009 IHR (Annex to *doc. IRCC10-11B*) to the Council (11) | Chair | C-2 | DONE |
| 19 | to follow up on Decision WENDWG8/10 to commission the new IHO ENC Catalog and report back to IRCC (14) | Chair and Secretary | IRCC11 |  |