## CSBWG Actions
No. | Agenda Item | Subject | Status/Date | Comments | Action | Status | Notes | Action
CSBWG9
7 | 3c | Current CSB Efforts | CSBWG10 | Discuss further development of DCDB to allow inclusion of data other than single track lines | DCDB/MZ | In process | DCDB: Will discuss at Jan tag up and report out at CSBWG13 | Completed - Close
CSBWG10
5 | 2.3 | Canadian CSB Update | IRCC13 | Raised generic CSB charting standards at IRCC13 and discussions should be progressed with the DQWG and the NCWG. | Chair/Vice-Chair | On Going | Vice Chair: Change to "In process" or "Ongoing'. PW to discuss with WG. | recraft action to reflect the analysis of S-100 roadmap to identify who and when needs to be engaged with these considerations + Anders + Meredith
17 | 6.3 | AOB | CSBWG11 | Generate vision statement for CSBWG | JPH | On Going | Drafted by JPH in 9/21: CSBWG Vision - "To organize Crowdsourced Bathymetry data for the benefit of all and to ensure that Crowdsourced Bathymetry data is accessible and useful for the broad marine community." CSBWG13 Discussion: Review as a WG - both the intent and text | Review after Strategy discussion
CSBWG11
4 | 5.2 | Next Sectors | CSBWG12 | Create a leisure craft flyer | IHO/Chair/RB | In Process | RB: Change status to "CSBWG14". | ongoing
5 | 5.2 | Next Sectors | CSBWG12 | Investigate creating a commercial shipping flyer IHO | IHO/Chair | No update | Pinged David M and Paul H 12/8/22. CSBWG13 Discussion: Need to discuss with WG and see if any others would like to take lead on ths. | Change date for CSBWG14 and include Nautical Institute
CSBWG12
1 | 1.5 | Review of Actions | CSBWG13 | IHO Sec to circulate consolidated Actions and Decisions following CSBWG12 | IHO Sec | Action completed.
2 | 2.3.2 | B-12 Data Contribution | CSBWG13 | Consider production of dedicated 2 page flyer for indigenous peoples | Chair | In Process | Suggestion: Change status to "CSBWG14". Pinged Candian WG members 12/8/22: Several replied with agreement to tackle this. | In Process
3 | 2.3.2 | B-12 Data Contribution | CSBWG13 | IHO to consider whether a new CL is required following publication of B-12 3.0.0 | IHO Sec | To be addressed at CSBWG13 | CSBWG13 Discussion: Is this worth another CL? Did this approach provide the desired results? Are there alternative means? | to be discussed
10 | 2.3.6 | B-12 Additional Considerations | 2022-04-22 | Chair to publish list of CSB Trusted Nodes | Chair | In Process | CSBWG13 Discussion: Similar to Action 2/CSBWG10; To be discussed at CSBWG13 | to be discussed
14 | 4.2 | AOB | CSBWG13 | Develop and circulate retrospective questionnaire | Chair/Vice Chair | On Going | Worth checking with group to see if we should do this after CSBWG13?
CSBWG13
1 |  |  | CSBWG14 | Create a task group to refine GeoJSON Schema proposal and report back to CSBWG14 | GZ/BC
2 |  |  | CSBWG14 | Consider the implications of GDPR | IHO Sec
3 |  |  | Jan 23 | IHO sec to make representation at SC-MMO re. the CSB problem and the need for near-shore bathymetry | IHO Sec
4 |  |  | Jan 23 | Draft a resolution for consideration by A3 relating to the IHO’s commitment to the UN Decade via GEBCO and CSB | Chair Team/IHO Sec/GGC Chair/Dir SB2030/SK
5 |  |  | Jan 23 | Establish a CSB Industry day working group/task team (JJ and Bill to Co-lead) | Chair
6 |  |  | Feb 23 | Explore opportunity for dedicated session at the next WOC SOS | Bill Staby
7 |  |  | Feb 23 | Explore opportunity for dedicated focus at MtG Symposium for CSB | Tim Kearns
8 |  |  | CSBWG14 | Create a HO specific issue Sub-group | Vice Chair
9 |  |  | Feb 23 | Chair team to review ToRs with agreed high level priorities and circulate to WG for approval via correspondence | Chair Team/IHO Sec
10 |  |  | March 23 | Chair team to take work items and produce a draft CSBWG work plan for circulation and approval by the WG via correspondence | Chair Team/IHO Sec
11 |  |  | CSBWG14 | Explore the possibility of a dedicated CSB reference book exploring the various tech, legal and social components. | SK