## SCUFN
Task | Work Item | Priority H-High M-Medium L-Low | Milestones | Start Date | End Date | Status P-Planned O-Ongoing C-Completed | Contact Person(s) *indicates lead | Related Pubs/Standard/Comments | Allocated budget (EUR) 2024 (GGC40) | Spend Forecast 2024 |  |  |  | Notes (Including likelihood of spend during the funding year) | Requested budget 2025 (GGC41) | Spend Forecast 2025 |  |  |  | Notes (Including likelihood of spend during the funding year)
[10 empty] | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec |  |  | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec
B1 | Ensure conduct of SCUFN meeting | H |  | Permanent |  | O | SCUFN Chair/Secretary | Two plenary meetings planned in March and November 2022 as part of business continuity measures. Significant back log of proposals to be considered.
B2 | Develop a repository of typical cases for helping in the consistency of the decision-making process | M |  | 2017 | 2022 | O | Roberta Ivaldi/Kevin MacKay | SCUFN ToRs and RoPs Since 2020, this includes some new developments on geometric definitions of features. Possible impact for the preparation of Ed. 4.3.0 of B-6 in future
B3 | Renewal of SCUFN Membership |  |  |  |  | C |  | Three new SCUFN Members in 2022.
B4 | Development a general strategy for UFN (horizontal resolution, minor features | H |  | 2018 | 2022 | O | Yasuhiko Ohara/SCUFN Chair/Kevin Mackay as Head of one Seabed2030 centre | Following guidance from GGC36, draft recommendation was submitted by Ohara at SCUFN35.1. Following this, a consolidated proposal is to be submitted for approval at SCUFN35.2.
B5 | Maintain relationship with other stakeholders (national naming boards, UNGEGN, GEBCO, Marine Regions, …) | H |  |  | Continuous | O | SCUFN Chair/ Secretary/Trent Palmer (for UN GEGN) | Database Quality, Interoperability.
E1 | Maintain IHO bathymetric publications | L |  | Continuous | Continuous | C |  | Possible amendments to align with scufn.ops-webservices.kr and SCUFN cookbook
E2 | Encourage the provision of bathymetric data associated to UFN | H |  | 2018 | Continuous | O | SCUFN Chair/Secretary/SCUFN Members | GEBCO Grid Actions in progress through B-6 and development of integrated web services as well as relations between Secretary and Proposers post-meetings
J1 | Update and enhance the GEBCO Gazetteer (B-8) database | H |  | Annual | Annual | O | SCUFN Chair/Secretary | B-8 – Gazetteer (implement SCUFN meeting decisions in the database, monitor pending names, chase SCUFN actions with proposers, chase missing data) – Work carried out by contract. | 12000
J2 | Maintain the GEBCO Gazetteer as a web service via a geospatially enabled database | H |  | 2016 | Permanent | O | SCUFN Chair/ Secretary/Jennifer Jencks | B-8 – Gazetteer – Capture user requirements (incl. SCUFN Secretary.), develop improvements and general maintenance. New release made in 4.3.6 with major enhancements.
J3 | Develop and make available public and management on-line interfaces to the Gazetteer | H |  | 2014 | 2023/24 | O | Hyun-Chul Han (as SCUFN Chair) /KHOA | B-8 – Gazetteer New requirement from IHO Secretariat to develop an IHO SCUFN Archive as part of SCUFN web services.
J4 | Develop a S-100-based product specification (if confirmed) for Undersea Feature Names | M / L |  | 2015 | 2022 | O | Chair Project Team (Anna Hendi) | S-100, B-6 Harmonized definitions of generic terms across B-6, S-32, IHO GI Registry
J5 | Upgrade the quality of the geometry of major existing undersea features in the Gazetteer which are known as being inaccurate and ambiguous | M |  | 2017 | Permanent | P | SCUFN Members | B-8 - Gazetteer (Aim: 10 features / SCUFN Member / per year)
| SCUFN Total Allocation | 12000

## TSCOM
Task | Work Item | Priority H-High M-Medium L-Low | Milestones | Start Date | End Date | Status P-Planned O-Ongoing C-Completed | Contact Person(s) *indicates lead | Related Pubs/Standard/Comments | Allocated budget (EUR) 2024 (GGC40) | Spend Forecast 2024 |  |  |  | Notes (Including likelihood of spend during the funding year) | Requested budget 2025 (GGC41) | Spend Forecast 2025 |  |  |  | Notes (Including likelihood of spend during the funding year)
[10 empty] | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec |  |  | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec
B | Ensure conduct of TSCOM meeting | H | Report of TSCOM meeting to GGC | continuous |  | O | Chair TSCOM
C | Ensure effective operation of IHO DCDB | H | Conduct review | Continuous |  | O | Director DCDB
D3 | Conduct DCDB Industry Day and Data Contribution Workshop | H | Conduct virtual workshop and industry day | 2020 | 2023 | C | Chair TSCOM Director DCDB
D4.0 | Develop and structure plans for the Goals identified in D3 | H | Structure for WG and ToRs for each of the goals | 2023 | 2024 | P | Chair TSCOM Chair SCRUM Chair SCOPE Director DCDB |  | 7500 | 2500 | 2500 | 2500 | 0 | high
D4.1 | Goal 1: Increase data availability: Transit Mapping | M | Objective A, B, C See Annex A | 2023 | 2026 | P | Chair TSCOM Chair SCRUM Chair SCOPE Director DCDB |  | 2500 |  |  |  |  | medium
D4.2 | Goal 2: Enhance Metadata and improve Web services | M | Objective A, B, C See Annex A | 2023 | 2026 | P | Chair TSCOM Chair SCRUM Chair SCOPE Director DCDB |  | 2500 |  |  |  |  | medium
D4.3 | Goal 3: Encourage the use of a common generic sonar format for bathymetry | M | Objective A, B, C See Annex A | 2023 | 2026 | P | Chair TSCOM Chair SCRUM Chair SCOPE Director DCDB |  | 2500 |  |  |  |  | medium
D4.4 | Goal 4: Unify an approach for disseminating information & outcomes | M | Objective A, B See Annex A | 2023 | 2026 | P | Chair TSCOM Chair SCRUM Chair SCOPE Director DCDB |  | 2500 |  |  |  |  | medium
E1 | Maintain IHO bathymetric publications | H |  | Continuous |  | O | All members of GEBCO GC through the Chair | B-4 - Information concerning recent bathymetric data B-11 - GEBCO Cookbook
E2 | Add and update instructive chapters in IHO-IOC GEBCO Cook Book | H | Maintain B-11 | Continuous |  | O | Chair TSCOM Chair, Cookbook editorial board | B-11 GEBCO Cookbook
|  | M | Maintain section related to Seabed 2030 | 2019 | 2030 | O
|  | H | Create on-line wiki structure for Cookbook | 2020 | 2024 | P |  |  | 1500 |  | 1500 |  |  | low
|  |  | Seek instructive chapters on contributing data, metadata requirements, platforms for viewing gaps and coverage, CSB, etc. | Continuous | 2030 | O
E3 | Review GEBCO Digital Grid and methodologies | H | Yearly review | continuous |  | O | Chair TSCOM Digital Atlas Manager
F | Develop, review, and maintain the on-line function of B-4 | M | Conduct review | Continuous |  | O | Director DCDB
H3 | Review, Update and Maintain IHO-IOC GEBCO website | H | Ensure Website Continuity by providing funds | continuous |  |  | Chair TSCOM BODC |  | 4000 | 4000 | 0 | 0 | 0 | high
|  | M | Update website with meeting documents | 2019 | 2024 | O | BODC
|  | H | Validate members and contact information for SCRUM, TSCOM, and SCOPE | continuous |  | O | Chairs TSCOM, SCRUM, SCOPE
|  | M | Review and maintain all working links | continuous |  | O | Chair TSCOM, BODC
|  | M | Provide technical and content review of both websites | continuous |  | O | Chairs TSCOM, SCRUM, SCOPE
|  | H | Maintain Google workspace for GGC and Sub committees. | continuous |  | O | Chair TSCOM, BODC |  | 1500 | 1500 | 0 | 0 | 0 | high
|  | L | Investigate possible integration of SCOPE website into main GEBCO website | 2022 | 2023 | P | Chairs TSCOM, SCOPE, BODC |  | 5000 | 0 | 0 | 5000 | 0 | low
K1 | Support Seabed 2030 | H | Provide scientific expertise and outreach | 2018 | 2030 | O | Chair TSCOM,
|  | M | Proposal for Discrete Global Grid Systems | 2022 | 2024 | O | Chair TSCOM |  | 1500 |  |  |  |  | medium
K2 | Travel to assist gathering technical needs from RDACCs and GDACC | M | Attend RMCs for RDACCs | 2019 | 2025 | O | Chair TSCOM |  | 4000 | 1000 | 1000 | 1000 | 1000 | high
K3 | Provide oversight and review of Seabed 2030 web services, methodologies and applications in accordance with TSCOM ToRs | H | Conduct regular reviews and participate in technical meetings | 2019 | 2030 | O | Chair TSCOM
L1 | Develop template for seafloor mapping route optimization application | H | Conduct requirements survey | 2019 | 2025 | O | Chair TSCOM |  | 7500 | 0 | 5000 | 2500 | 0 | medium
|  |  | Prototype and document web app |  |  | O
|  |  | Optimal use of metadata schema |  |  | O
L2 | Monitor and advice (on) use of metadata based on outcome of metadata working group |  |  | 2022 | 2030 | O
| TSCOM Total Allocation | 42500

## SCRUM
Task | Work Item | Priority H-High M-Medium L-Low | Milestones | Start Date | End Date | Status P-Planned O-Ongoing C-Completed | Contact Person(s) *indicates lead | Related Pubs/Standard/Comments | Allocated budget (EUR) 2024 (GGC40) | Spend Forecast 2024 |  |  |  | Notes (Including likelihood of spend during the funding year) | Requested budget 2025 (GGC41) | Spend Forecast 2025 |  |  |  | Notes (Including likelihood of spend during the funding year)
[10 empty] | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec |  |  | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec
B | Ensure conduct of annual SCRUM meeting | H | Report of SCRUM meeting to GGC | 2023 | 2024 | P | Chair SCRUM
D1 | Encourage the contribution of bathymetric data to the IHO DCDB | H |  | Continuous |  | O | All members of GEBCO SC through the Chair
D2 | Identify priority areas for regional mapping and support the organization of regional mapping projects. | H |  | Continuous |  | O | Chair SCRUM
|  | M | Coordinate with FUGRO to publish list of regional mapping permission contacts | 2024 | 2025 | P | Chair SCRUM/ David Millar
|  | H | Attend CSBWG Meeting | 2024 | 2030 | P | Chair SCRUM |  | 4000 |  |  |  |  | Spend is likely to allow for better cordination with CSBWG
D3 | Promote data contribution through GEBCO participation in RHCs and IOC regional meetings | H | Identify GEBCO colleagues who are able to attend meetings in 2023-2024 | Continuous |  | O | All members of GEBCO SC through the Chair |  | 4000 |  |  |  |  | Plan to engage with the IOC more efficiently this year
|  |  | Monitor GEBCO presence at IOC meetings | Continuous |  | O
D4 | Promote data contribution by supporting participation at Regional Mapping Meetings | H |  | Continuous |  | O | Chair SCRUM
D5 | Develop and make publicly available materials to highlight and foster regional activities and initiatives including up to date GEBCO slide deck virtual engagement materials such as videos of presentations. | H |  | Continuous |  | O | Chair SCRUM in coordination with Chair SCOPE and with input from Seabed 2030 Project Team
D6 | Develop and refine messaging for IHO & IOC to facilitate increasing the support of coastal states to provide and release data from within their waters of national jurisdiction. | H |  | Continuous |  | O | All members of GGC through the Chair*
|  | H | Compile an inventory of data accessibility /releasability by geographic region – collaborative approach | 2023 | 2025 | P | SCRUM, TSCOM and BODC
| Gather input from regarding stakeholder needs via regional engagement |  |  | Continuous |  | O | All members of GGC through the Chair*
D7 | Work with Seabed 2030 GDACC to update metrics of completeness for RHCs and put on SCRUM web pages | H |  | 2019 | 2030 | P | GDACC through the Chair*
D8 | Work with Seabed 2030 RDACCs and GDACC to ensure that reasons for embargo and/or no public access are captured and articulated to IHO/IOC | H |  | 2019 | 2030 | P | RDACCs and GDACC through Chair*
D9 | Gather input about IBC status and plans | H |  | 2019 | 2025 | P | SCRUM through Chair/ Vice-Chair
E | Maintain IHO bathymetric publications | M | Update GEBCO global 15 arc-second grid with new compilations | Continuous | Continuous | O | All members of GEBCO GC through the Chair Chair SCRUM | B-4 - Information concerning recent bathymetric data B-9 - GEBCO digital atlas
|  | H | Coordiate to include regional alumni in grid review to allow for better QC | Continuous | Continuous | P | Chair SCRUM/ GDACC
|  | H | Update GEBCO World Map to included updated versions of GEBCO grid and adopted undersea feature names from SCUFN. | 2016 | 2023 | O | Chairs SCRUM/SCUFN | B-6 – Standardization of undersea feature names
|  | M |  | Continuous | Continuous | O |  | B-8 - Gazetteer
|  | L |  | Continuous | Continuous | O |  | B-9 - GEBCO digital atlas
|  | M |  | Continuous | Continuous | O |  | B-10 - The history of GEBCO
|  | M |  | Continuous | Continuous | O |  | B-11 - GEBCO Cookbook
H | Review and Update IHO-IOC GEBCO and Seabed 2030 Websites | M | Update website with meeting documents and information pertaining to SCRUM activities | Continuous |  | P | BODC
|  | M | Validate members and contact information for SCRUM, TSCOM, and SCOPE | Continuous |  | P | Chairs SCRUM, TSCOM, SCOPE
|  | M | Review and maintain all working links | Continuous |  | P | Chair SCRUM, BODC
K | Support SB2030 RDACCs | H | Provide scientific expertise, regional connections and outreach support | 2018 | 2030 | P | Chairs of TSCOM, SCRUM SCUFN, Outreach WG
|  |  | Attended WITS workshop | 2022 | 2023 | P | Chair SCRUM/ Seabed2030
|  | H | Technical meetings between Seabed 2030 and SC's | 2024 | 2030 | P | Chair SCRUM/ Chair TSCOM/ Seabed2030
|  |  | Appointed Seabed2030 Coordinator - Shereen Sharma | 2023 | 2030 | C | Chair SCRUM/ Seabed2030
| SCRUM Total Allocation | 8000

## SCOPE
Task | Work Item | Priority H-High M-Medium L-Low | Milestones | Start Date | End Date | Status P-Planned O-Ongoing C-Completed | Contact Person(s) *indicates lead | Related Pubs/Standard/Comments | Allocated budget (EUR) 2024 (GGC40) | Spend Forecast 2024 |  |  |  | Notes (Including likelihood of spend during the funding year) | Requested budget 2025 (GGC41) | Spend Forecast 2025 |  |  |  | Notes (Including likelihood of spend during the funding year)
[10 empty] | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec |  |  | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec
A1 | Annual and semi-annual SCOPE meetings with membership | M | Coordination of meeting, Meeting minutes, Meeting Reports | 2022 | 2023 | P | Tim Kearns
A2 | Seek to grow/confirm SCOPE membership | L | Review of membership, plan, growth plan | 2022 | 2023 | P | To be assigned
A3 | Integration of GEBCO and GEBCO-SCOPE webpages | H | Review of existing sites, establish joint mini-committee, set a plan, integration | 2022 | 2023 | P | Tim, George, BODC, others.
B1 | Support organisation and execution of Map the Gaps symposium | M | Plan, Event, Analytics, Report | 2016 | annually | O | Tim Kearns
B2 | Social Media Review, Plan, Schedule Development | L | Report, Plan, Schedule, Analytics | 2022 | 2023 | P | Inactive - needs to be reinvigorated
B3 | B-10 Additional Chapter | M | Chapter published | 2021 | 2023 | O | Eunmi Chang | B-10
B4 | Coordinated Plan for GEBCO 120 including supporting materials | M | Committee, Plan, Execution, Report | 2022 | 2023 | P | Tim, Kira, Sarah, IOC rep.
B5 | Finalization and printing of new GEBCO Map for distribution/ordering (tubes: €6/per @250) | L | Completion | 2021 | 2023 | O | Eunmi Chang and Tim Kearns
B6 | ArcGIS Story Map(s) of GEBCO | L | Team, Plan, Execution, Product | 2022 | 2023 | P | Sarah, Caitlyn, Meredith
B7 | GEBCO 120 Booth Materials (estimated costs of pop-ups, banner, table-cloth) | L | Committee, Plan, Procurement, Deliverables | 2022 | 2023 | P | Tim Kearns
C1 | Review of GEBCO communications, messaging, identity and recommendations for a future communications plan. | M | Plan, Proposal, Award, Execution, Deliverable | 2022 | 2023 | O | Tim Kearns
C2 | Develop a Communications Matrix and Best Practices among the GEBCO community | L | Committee, Review, Report | 2022 | 2023 | P | To be assigned
C3 | Consultation for tactical planning Phase 1 (deferred until completion of review of GEBCO comms) | L |  | 2022 | 2023 | P | Tim Kearns
| SCRUM Total Allocation | 0

## SCET
Task | Work Item | Priority H-High M-Medium L-Low | Milestones | Start Date | End Date | Status P-Planned O-Ongoing C-Completed | Contact Person(s) *indicates lead | Related Pubs/Standard/Comments | Allocated budget (EUR) 2024 (GGC40) | Spend Forecast 2024 |  |  |  | Notes (Including likelihood of spend during the funding year) | Requested budget 2025 (GGC41) | Spend Forecast 2025 |  |  |  | Notes (Including likelihood of spend during the funding year)
[10 empty] | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec |  |  | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec
Gov | Expand and enhance SCET membership | H |  | 2023 | Ongoing | O | Chair of SCET Vice-Chair SCET
A | Create an inventory of international groups undertaking seabed mapping education and training programs | H | Develop an initial inventory | 2023 | GGC40 | O | Chair SCET All Members of SCET *Rochelle Wigley
B | Contribute to SCOPE communication plan | M | SCET to deliver communication objectives of SCET | 2023 | 2024 | P | Chair SCET Chair SCOPE
C1 | Identify the core activities of SCET | H | Deliver a gap analysis report | 2023 | GGC40 | P | *Chair SCET Vice-Chair SCET All Members of SCET **Kim Picard
C2 | Plan, coordinate and collate website presence | L | Create a content plan and website placeholder created | 2023 | 2024 | P | Chair SCET Chair SCOPE All Members of SCET | B-4 - Information concerning recent bathymetric data B-9 - GEBCO digital atlas (discontinued as of 2022) B-11 - GEBCO Cookbook
D | Develop governance structure and cooperation ToR between SCET and the Nippon Foundation – GEBCO Training Programme at the University of New Hampshire. | H | Create Governance and ToR | 2023 | GGC40 | P | Chair SCET * Vice-Chair SCET Karolina Zwolak
|  |  | Submit official document to GGC for Annual Training programme grant application | 2023 | GGC40 | P
| SCRUM Total Allocation (EUR) | 0