## SCRUM
Task | Work Item | Priority H-High M-Medium L-Low | Milestones | Start Date | End Date | Status P-Planned O-Ongoing C-Completed | Contact Person(s) *indicates lead | Related Pubs/Standard/Comments | Allocated budget (EUR) 2024 (GGC40) | Spend Forecast 2024 |  |  |  | Notes (Including likelihood of spend during the funding year) | Requested budget 2025 (GGC41) | Spend Forecast 2025 |  |  |  | Notes (Including likelihood of spend during the funding year) | Spend 2024 |  |  |  |  | ANALYSIS
[10 empty] | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec |  |  | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec |  | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec | Annual expenditure
B | Ensure conduct of annual SCRUM meeting | H | Report of SCRUM meeting to GGC | 2023 | 2030 | P | Chair SCRUM | [17 empty] | 0 | 0
D1 | Encourage the contribution of bathymetric data to the IHO DCDB | H |  | Continuous |  | O | All members of GEBCO SC through the Chair | [17 empty] | 0 | 0
D2 | Identify priority areas for regional mapping and support the organization of regional mapping projects. | H | Attend CSBWG Meeting | 2024 | 2030 | O | Chair SCRUM |  | 4000 | [5 empty] | 5000 |  |  |  |  | Spend is likely to allow for better cordination with CSBWG |  | 1032.57 |  |  | 1032.57 | 2967.43
D3 | Promote data contribution through GEBCO participation in RHCs and IOC regional meetings | H | Identify GEBCO colleagues who are able to attend meetings in 2025 | Continuous |  | O | All members of GEBCO SC through the Chair | [17 empty] | 0 | 0
|  | H | Attend IOC meeting | 2024 | 2024 | P | Chair/ Vice chair SCRUM |  | 4000 | [5 empty] | 5000 |  |  |  |  | Plan to engage with the IOC more efficiently this year. Are in communication with Julian (IOC) |  |  |  |  | 0 | 4000
|  | H | Monitor GEBCO presence at IOC meetings | Continuous |  | O | [18 empty] | 0 | 0
D4 | Promote data contribution by supporting participation at Regional Mapping Meetings | H | Percentages of RHC mapped for 2025 to be shared with all CSB Coordinators and IRCC Chair, to be shared with their respective RHCs | Continuous | 2030 | O | Chair SCRUM | [17 empty] | 0 | 0
D5 | Develop and make publicly available materials to highlight and foster regional activities and initiatives including up to date GEBCO slide deck virtual engagement materials such as videos of presentations. | H | Production of Spainish Language slide deck | Continuous |  | O | Chair SCRUM in coordination with Chair SCOPE and with input from Seabed 2030 Project Team | [17 empty] | 0 | 0
D6 | Develop and refine messaging for IHO & IOC to facilitate increasing the support of coastal states to provide and release data from within their waters of national jurisdiction. | H |  | Continuous |  | O | All members of GGC through the Chair* | [17 empty] | 0 | 0
|  | H | Compile an inventory of data accessibility /releasability by geographic region – collaborative approach | 2023 | 2025 | P | SCRUM, TSCOM and BODC | [7 empty] | 3000 |  |  |  |  | Hire someone to compile the inventory |  |  |  |  | 0 | 0
| Gather input from regarding stakeholder needs via regional engagement |  |  | Continuous |  | O | All members of GGC through the Chair* | [17 empty] | 0 | 0
D7 | Work with Seabed 2030 GDACC to update metrics of completeness for RHCs and put on SCRUM web pages | H |  | 2019 | 2030 | P | GDACC through the Chair* | [17 empty] | 0 | 0
D8 | Work with Seabed 2030 RDACCs and GDACC to ensure that reasons for embargo and/or no public access are captured and articulated to IHO/IOC | H |  | 2019 | 2030 | P | RDACCs and GDACC through Chair* | [17 empty] | 0 | 0
D9 | Gather input about IBC status and plans | H |  | 2019 | 2025 | P | SCRUM through Chair/ Vice-Chair | [17 empty] | 0 | 0
E | Maintain IHO bathymetric publications | M | Update GEBCO global 15 arc-second grid with new compilations | Continuous | Continuous | O | All members of GEBCO GC through the Chair Chair SCRUM | B-4 - Information concerning recent bathymetric data B-9 - GEBCO digital atlas | [16 empty] | 0 | 0
|  | H | Coordiate to include regional alumni in grid review to allow for better QC | Continuous | Continuous | P | Chair SCRUM/ GDACC | [17 empty] | 0 | 0
|  | H | Update GEBCO World Map to included updated versions of GEBCO grid and adopted undersea feature names from SCUFN. | 2016 | 2023 | O | Chairs SCRUM/SCUFN | B-6 – Standardization of undersea feature names | [16 empty] | 0 | 0
|  | M |  | Continuous | Continuous | O |  | B-8 - Gazetteer | [16 empty] | 0 | 0
|  | L |  | Continuous | Continuous | O |  | B-9 - GEBCO digital atlas | [16 empty] | 0 | 0
|  | M |  | Continuous | Continuous | O |  | B-10 - The history of GEBCO | [16 empty] | 0 | 0
|  | M |  | Continuous | Continuous | O |  | B-11 - GEBCO Cookbook | [16 empty] | 0 | 0
H | Review and Update IHO-IOC GEBCO and Seabed 2030 Websites | H | Update website with regional mapping projects | 2024 | 2026 | P | Chair/vice-Chair SCRUM, BODC, | [17 empty] | 0 | 0
|  | M | Update website with meeting documents and information pertaining to SCRUM activities | Continuous |  | P | BODC | [17 empty] | 0 | 0
|  | M | Validate members and contact information for SCRUM, TSCOM, and SCOPE | Continuous |  | P | Chairs SCRUM, TSCOM, SCOPE | [17 empty] | 0 | 0
|  | M | Review and maintain all working links | Continuous |  | P | Chair SCRUM, BODC | [17 empty] | 0 | 0
K | Support SB2030 RDACCs | H | Provide scientific expertise, regional connections and outreach support | 2018 | 2030 | O | Chairs of TSCOM, SCRUM SCUFN, Outreach WG | [17 empty] | 0 | 0
|  | H | Technical meetings between Seabed 2030 and SC's | 2024 | 2030 | O | Chair SCRUM/ Chair TSCOM/ Seabed2030 | [17 empty] | 0 | 0
| SCRUM Total Allocation | 8000
| SCRUM Total expenditure | 1032.57
| BALANCE | 6967.43