**1.1. IHO-IOC GEBCO Sub-Committee for Regional Undersea Mapping Work Plan 2023-2024**

**1.1 SCRUM Tasks**

|  |  |
| --- | --- |
| B | Ensure conduct of SCRUM meeting in 2022(IHO Task3.6.1) |
| D | Encourage the contribution of bathymetric data to the IHO DCDB (IHO Task 3.6.3), identify priority areas for regional mapping and promote data contribution through GEBCO participation in IHO/IOC Regional Meetings |
| EHK | Maintain IHO bathymetric publications (IHO Task 3.6.6) including: B-4, B-9, B-10 and B-11Ensure IHO-IOC GEBCO Web site is kept current and updated regularly (IHO Task 3.6.8)Provide scientific support and advice to Seabed 2030 Project Director, RDACCs and GDACC |
|  |  |

| **Task**  | **Work item** | **Priority**H-highM-mediumL-low | **Milestones** | **Start****Date** | **End****Date** | **Status**P-plannedO-ongoingC-completed | **Contact Person(s)****\* indicates leader** | **Related Pubs/Standard** | **Funding Bid (€)** | **GGC Decision** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| B | Ensure conduct of annual SCRUM meeting | H | Report of SCRUM meeting to GGC | 2023 | 2024 | P | Chair SCRUM |  |  |  |
| D1 | Encourage the contribution of bathymetric data to the IHO DCDB | H |  | Continuous |  | O | All members of GEBCO SC through the Chair |  |  |  |
| D2 | Identify priority areas for regional mapping and support the organization of regional mapping projects.  | H | Prioritisation meetings held with TSCOM & SEABED2030 | Continuous  |  | O | Chair SCRUM |  |  |  |
| D3 | Promote data contribution through GEBCO participation in RHCs and IOC regional meetings | H | Identify GEBCO colleagues who are able to attend meetings in 2023-2024 | Continuous |  | O | All members of GEBCO SC through the Chair |  | 10,000 |  |
| D4 | Promote data contribution by supporting participation at Regional Mapping Meetings | H |  | Continuous |  | O | Chair SCRUM |  |  |  |
| D5 | Develop and make publicly available materials to highlight and foster regional activities and initiatives including up to date GEBCO slide deck virtual engagement materials such as videos of presentations. | H | Posting of videos on the SCUM Youtube Channel | Continuous |  | O | Chair SCRUM in coordination with Chair SCOPE and with input from Seabed 2030 Project Team |  | 2,000 |  |
| D6 | Develop and refine messaging for IHO & IOC to facilitate increasing the support of coastal states to provide and release data from within their waters of national jurisdiction.Gather input from regarding stakeholder needs via regional engagement | H | Coordinated submission to IOC’s State of the Ocean report | ContinuousContinuous |  | OO | All members of GGC through the Chair\*All members of GGC through the Chair\* |  |  |  |
| D7 | Work with Seabed 2030 GDACC to update metrics of completeness for RHCs and put on SCRUM web pages | H |  | 2019 | 2030 | P | GDACC through the Chair\* |  |  |  |
| D8 | Work with Seabed 2030 RDACCs and GDACC to ensure that reasons for embargo and/or no public access are captured and articulated to IHO/IOC | H |  | 2019 | 2030 | P | RDACCs and GDACC through Chair\* |  |  |  |
| D9 | Gather input about IBC status and plans | H | Meeting between Vice-chair and IBCSEP to encourage reinitialisation | 2019 | 2025 | P | SCRUM through Chair/ Vice-Chair |  | 4,000 |  |
| D10 | Convene SCRUM-focused sessions of a webinar series in conjunction with Seabed 2030 and Map the Gaps | H |  | 2021 | 2023 | P | Chairs of Sub-Committees, Seabed 2030 Project, and Map the Gaps |  |  |  |
| E | Maintain IHO bathymetric publications | MHMLMM | Update GEBCO global 15 arc-second grid with new compilationsUpdate GEBCO World Map to included updated versions of GEBCO grid and adopted undersea feature names from SCUFN. | Continuous2016ContinuousContinuousContinuousContinuous | Continuous2023ContinuousContinuousContinuousContinuous | OOOOOO | All members of GEBCO GC through the ChairChair SCRUMChairs SCRUM/SCUFN | B-4 - Information concerning recent bathymetric dataB-9 - GEBCO digital atlasB-6 – Standardization of undersea feature names B-8 - Gazetteer B-9 - GEBCO digital atlasB-10 - The history of GEBCOB-11 - GEBCO Cookbook |  |  |
| H | Review and Update IHO-IOC GEBCO and Seabed 2030 Websites | M | Update website with meeting documents and information pertaining to SCRUM activitiesValidate members and contact information for SCRUM, TSCOM, and SCOPEReview and maintain all working links | ContinuousContinuousContinuous |  | PPP | BODCChairs SCRUM, TSCOM, SCOPEChair SCRUM, BODC |  |  |  |
| K | Support SB2030 RDACCs | H | Provide scientific expertise, regional connections and outreach support Appoint Seabed2030 Coordinator | 20182023 | 20302030 | PP | Chairs of TSCOM, SCRUM SCUFN, Outreach WGChair SCRUM/ Seabed2030 |  |  |  |

**1.2 SCRUM Meetings (IHO Task 3.6.1)**

|  |  |  |
| --- | --- | --- |
| **Date** | **Location** | **Activity** |
| 7&9October 2013 | Venice, Italy | 1stMeeting |
| 11-13December 2014 | Mountain View, California, USA | 2ndMeeting |
| 5-7 October 2015 | Kuala Lumpur, Malaysia | 3rdMeeting |
| 10-12 October 2016 | Viña del Mar, Chile | 4thMeeting |
| 13-14 November 2017 | Busan, Korea | 5thMeeting |
| 5-6 November 2018 | Canberra, Australia | 6th Meeting |
| 4-5 November 2019 | Portsmouth, NH, USA | 7th Meeting |
| 11-15 January 2021 | Remote VTC | 8th Meeting |
| 2&11 November 202126October 2022 | Remote VTCSouthampton, UK/ Hybrid | 9th Meeting10th Meeting |

Chair: Aileen Bohan Email: aileenbohan@gmail.com

Vice-Chair: Hugo Montoro Email: hdmontoro@gmail.com

Secretary: Sam Harper Email: samuel.harper@iho.int