**16th MEETING OF THE IHO INTER-REGIONAL COORDINATION COMMITTEE**

**IHO-IRCC16**

**Santa Cruz Island - Galapagos, Ecuador**

**10-12 June 2024**

**DRAFT IRCC WORK PROGRAMME FOR 2024-2025**

| **No** | **ACTIVITY** | **RESP.** | **DEADLINE** | **STATUS** |
| --- | --- | --- | --- | --- |
| **Administration** | | | | |
| IRCC1601/2024 | Prepare the draft IRCC16 Report in accordance with Decision C7/19 and circulate to the IRCC16 Participants | IRCC Chair | 24 June 2024 |  |
| IRCC1602/2024 | Provide comments to the Chair on the draft IRCC15 Report | IRCC16 Participants | 1 July 2024 |  |
| IRCC1603/2024 | Submit the IRCC Report to Council 8 (CCL 01/2024) | Chair | 15 July 2024 |  |
| IRCC1604/2024 | Update and implement the IRCC List of Actions and Tasks agreed at IRCC16 | IRCC Members | Continuously |  |
| IRCC1605/2024 | Provide the IRCC Chair with progress reports on the relevant tasks in the IHO 2024 Work Programme | RHCs and IRCC bodies | 31 Jan 2025 |  |
| IRCC1606/2024 | Provide to the IRCC Chair the estimated values of SPIs as of 31 December 2024 and target values for 31 December 2025, complemented by the comments on the difficulties encountered and suggestions for a way forward | IHO Secretariat/ RHCs/ IRCC Subordinate bodies | 31 Jan 2025 |  |
| IRCC1607/2024 | Provide the Secretariat with the IRCC Annual Report for 2024 | IRCC Chair | 28 Feb 2025 |  |
| IRCC1608/2024 | Organize and prepare IRCC17 | IRCC Chair, Secretariat | IRCC17 |  |
| IRCC1609/2024 | Attend and report to IRCC17 | IRCC Chair, Secretariat, IRCC members | IRCC17 |  |
| IRCC1610/2024 | Report on progress | IRCC Fund Generation PT | IRCC17 |  |
| **Outreach** | | | | |
| IRCC1611/2024 | Investigate mechanisms for raising external funds A-3 decision 20b refers | Secretariat, IRCC  FG PT | C-9 |  |
| IRCC1612/2024 | Scoping Team to draft the TOR for a PT to work on the way how to create an IHO Resolution related with IHO social Programme (incl. Gender Balance in Hydrography) | Scoping Team | mid-September 2024 |  |
| IRCC1613/2024 | MSDIWG to establish a pilot project for the High Sea and MPAs adopted by IMO, to demonstrate the benefits of S-122 for non-navigation purposes (Council 7/Decision 44) | IRCC/MSDIWG | C-8 |  |
| IRCC1614/2024 | Take every opportunity to promote the achievements of IRCC bodies, including the use of social media and report to the IRCC Chair | Secretariat | Permanent |  |
| IRCC1615/2024 | Provide material to the Secretariat to promote the achievements of IRCC bodies and report to the IRCC Chair | Chairs of IRCC Bodies | Permanent |  |
| IRCC1616/2024 | Continue to engage suspended Member States in their region to encourage their re-admission to the IHO and report to the IRCC Chair | MBSHC | Permanent |  |