Annex C – Work Plan Milestones 2023

| **DELIVERY DATE****(2022)** | **ACTIONS** |
| --- | --- |
| **Electronic Chart Activities** | **INT Chart Activities** |
| Jan 1 – Feb1 | Member States to provide updates based on discussions, and consideration presented at MACHC2023 , MICC meeting on plans to address ENC coverage within their area. | Member States to provide updates based on discussions, and consideration of the individual Ports Reports presented at the MACHC 2023, MICC on plans. |
| Feb 22 - 24 | Represent MACHC at WEND WG |
| March 24 | In preparation for the quarterly Conference Call, Member States to provide updates to:* the list of available ENCs
* resolutions of any gaps/overlaps identified.
* the standardized regional ENC scheme
* S-100 Production update and test beds
* Product Specification development participation
* S100 Capacity building opportunities including workshop on Dual fuel S101 – S57 production
 | In preparation for the quarterly Conference Call, * Member States to forward INT Chart metadata and shapefiles for “planned” INT Charts.
* Member States to propose additional coverage/adjustments for S-11, section B

. |
| April 14 | Hold quarterly conference call to assess status and next steps. |
| May 5 | Complete follow-up activities from Conference Call. Member States to provide all additional information identified during conference call.  |
| June 16 | In preparation for the quarterly Conference Call, Member States to provide updates to:* the list of available ENCs
* resolutions of any gaps/overlaps identified.
* the standardized regional ENC scheme
* S-100 Production update and test beds
* Product Specification development participation
* S100 Capacity building opportunities
 | In preparation for the quarterly Conference Call,* Member States to forward INT Chart metadata and shapefiles for “planned” INT Charts.
* Member States to propose additional coverage/adjustments for S-11, section B

  |
| July 14 | Hold quarterly conference call to assess status and prepare information as needed for subsequent communication to IRCC and IHB. |
| July 28 | Complete follow-up activities from Conference Call. Member States to provide all additional information identified during conference call. |
| Aug 29 | Investigate and/or track issues regarding consistencies and availability of ENCs and the corresponding INT (paper) Charts if problems persist. |
| Sept 8 |   | MS to forward S-11 updates to INT Chart Coordinator for inclusion for Region B, S-11. |
| Sept 15 |   | MICC INT Chart Coordinator to forward S-11 updates to IHB, to include Pacific INT scheme. |
| Oct 12 | In preparation for the quarterly Conference Call, Member States to provide updates to:* the list of available ENCs
* resolutions of any gaps/overlaps identified.
* the standardized regional ENC scheme
* S-100 Production update and test beds
* Product Specification development participation
* S100 Capacity building opportunities
 | In preparation for the quarterly Conference Call, * Member States to forward INT Chart metadata and shapefiles for “planned” INT Charts.
* Member States to propose additional coverage/adjustments for S-11, section B
 |
| Oct 26 | Hold quarterly follow-up conference call to update/review and discuss MS input in preparation of 24th MACHC. |
| Nov 9 | Complete follow-up activities from Conference Call. Member States to provide all additional information identified during conference call. |
| Nov 16 | Provide all updates, to the MICC Chair and INT chart Coordinator for the MICC Report to 24th MACHC. |
|  Dec 2022 | Provide update on 2023 MICC activities/accomplishments |  |