## Sheet1
MSIWG Work Plan
2023-11-30
Work Item | Work Activity | Milestones | Start Date | End Date | Status P: Planned O:Ongoing C:Completed S: Suspended | Comments | Contact
1 | Approval of the MSIWG Terms of Reference | *Members of the MSIWG Review existing TOR, *Members to propose edits to draft TO * Dristribute TOR for the wider comment from the MACHC; *Approve TOR | 2023-12-11 | 2023-12-15 | C
2 | Election of Chair/Vice Chair of MSI WG | *Members of the MSIWG to accept nominations *Members of MSIWG to vote on Chair/Vice Chair Positions (If Needed), *Bring results to wider MACHC | 2023-12-11 | 2023-12-15 | C
3 | MSIWG to develop a list of additional tasks needed to support MSI promulgation and development within the MACHC region | *Determine the subjects to be covered by meetings of the MACHC MSIWG, *Develop list; *Use list to determine agenda of further meetings | 2023-12-11 |  | O
4 | MSIWG to develop a S-124 plan for the MACHC | *Determine the S-124 requirements for the MACH Region *Determine the means of coastal states to produce s-124; *Develop an implementation plan in accordance with IMO/IHO guidelines | 2023-12-11 |  | P
5 | Conduct Bi-Annual MSIWG Meetings | *Plan a intersessional MSI WG meeting via telecon; *Plan one in person meeting prior to the MACHC meeting; * Determine if more MSIWG Meetings are necessary to accomplish the objectives and work plan | 2023-12-11 |  | 0