**Status Report on the Progress made on the List of Actions and Recommendations from the MBSHC 23 up to 15 February 2024**

| **ID** |  | **Responsible**  | **Deadline** | **Status** | **Action proposed by Chair** |
| --- | --- | --- | --- | --- | --- |
|  | **MBSHC23 ACTIONS** |  |  |  |  |
| **MBSHC 23/01**  | MBSHC will translate new Statutes to French | Francesupportedby IHO Sec. | **Sept.2022** | **Completed** |  |
| **MBSHC 23/02**  | MBSHC will upload new Statutes to the MBSHC webpage. | MBSHCChair | **15 April2022** | **Completed** |  |
| **MBSHC 23/03**  | MBSHC will upload Disaster Response Framework (DRF) approved to the MBSHC webpage. | MBSHCChair | **15 April2022** | **Completed** |  |
| **MBSHC 23/04**  | MS will update tables 1 & 2 of DRF.  | All  | **30 June2022** | **Completed** **for 2022 and 2023** |  |
| **MBSHC 23/05**  | MBSHC will consider DRF updating.  | MBSHC  | **MBSHC24** | **Completed** | Table 1 and Table 2 published on IHO web portal.Under preparation a call to MS to propose amendments to DRF ver. 2022 to be considered at MBSHC24. |
| **MBSHC 23/06** | Member States are encouraged to provide feedback on the draft CB plan of 2023, provide feedback on the efficiency of the remote CB activities carried out in 2021, and needs for the 2024. | All  | **15 May2022** | **Completed for 2024.** **Ongoing for 2025.** |  |
| **MBSHC 23/07**  | Albania to consider signing the MBSHC Statutes, to become an Associate Member State.  | ALL  | **MBSHC24** | **Completed** |  |
| **MBSHC 23/08** | MS are encouraged to communicate with their concerned national authorities on the interest to sign the Convention on the International Organization for Marine Aids to Navigation, which aims to transform IALA from a Non –Governmental Association to an Inter-Governmental Organization. https://www.iala-aism.org/the-igo-project/ | ALL  | **2022** | **Completed** |  |
| **MBSHC 23/09** | MBSHC is invited to encourage MSDI initiatives, make the Ambassador aware of relevant MSDI Initiatives. | All  | **MBSHC24** | **Ongoing** | MBSHC to issue a CL informing MS of the adoption of Ed. 3.0.0 of IHO Pub. C-17- Spatial Data Infrastructures "The Marine Dimension" - Guidance for HOs. To remind MS on this action. |
| **MBSHC 23/10** | MBSHC Chair will send by CL to Full Members, Associate Members and Observers a call for applications for membership to MBSHC S-1XX WG | MBSHCChairsupportedby France | **End ofApril 2022** | **Completed** MBSHC CL 04/2022 |  |
| **MBSHC 23/11** | MBSHC - S1XXWG member to designate a Chair and to prepare ToRs and RoPs for submission to MBSHC for approval by correspondence. | S1XXWGmembers | **Dec.2022** | Chair selection **completed** (FR).**Ongoing**ToRs and RoPs.MBSHC CL 06/2022  | MBSHC Chair to issue a CL informing MS about progress status and summary of the activities asking FR to support it.To send Draft ToRs and RoPs. |
| **MBSHC 23/12** | MS who wish to apply for Council participation to submit their application (see MBSHC statutes available on the MBSHC web page). CL to be issued by MBSHC Chair. | MBSHCChair | **EndOctober2022** | **Completed** | MBSHC CL 03/2023 MBSHC Chair announced the selection of Croatia, France and Italy to occupy seats in the IHO Council 2023-2026. |
| **MBSHC 23/13**  | DZ to update the RCC about the new ENC scheme implementation and RCC to provide support.  | DZ, UK, RCC  | **MBSHC24** | **Ongoing** | UK provided update to MBSHC Chair as their response to MBSHC CL 12/2023.  |
| **MBSHC 23/14**  | ES/DZ to inform the RCC about the co-production of INT3106.  | ES, DZ  | **MBSHC24** | **Ongoing** | MBSHC Chair to contact RCC by email asking him is there any info from DZ, if not to send reminder to DZ regarding this action.  |
| **MBSHC 23/15** | Region F ICCWG to re-consider the INT and ENC charting scheme submitted by Lebanon and make proposal by correspondence when appropriate. | ICCWG  | **TBD** | **Completed**  |  |
| **MBSHC 23/16** | Region F ICCWG supported by the BASWG, to re consider the INT and ENC charting scheme in the Black and Azov Seas globally when the situation in the region is stabilized. | ICCWG  | **MBSHC24** | **Completed**  | To contact ICCWG and BASWG asking for situation update, early 2024. |
| **MBSHC 23/17** | Greece will re-submits the proposal of INT chart scheme on the Aegean Sea to the MBSHC Chair for consideration by the MBSHC | GR  | **Sept 2022** | **Completed**  | Transferred for discussion to MBSHC 24. Ref: MBSHC CL 02/2023. |
| **II.** | **MBSHC 23 RECOMENDATIONS** |  |  |  |  |
| MBSHC23/01 | Member States are encouraged to attend next IRCC Workshop strategic plan to deal with SPI (CL 12/2022). | All  | **28 April 2022** | **Completed** |  |
| MBSHC23/02  | MS are encouraged to participate in the Empowering Women in Hydrography projects.  | All  | **2022** | **Completed** |  |
| MBSHC23/03  | Member States are encouraged to take part in the HSSC14 hybrid meeting, in Bali (Indonesia).  | All  | **2022** | **Completed** |  |