**8th ICC-WG Action Items**

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **Action** | **Action By** | **Deadline** |
| 1 | ICC-WG Coordinator to contact Russia and Australia to resolve ENC overlap | ICC-Coordinator | The ICCWG Coordinator had contacted the countries by formal letter on 12 February 2018 and has had no response to date. No progress  Ongoing |
| 2 | Provide link to ENC portal demonstrator to MS | IHO Secretariat | INToGIS superceded the ENC Portal. ENC schema included in the IHO GIS.  Item closed |
| 3 | Define minimum meta data required to support trial ENC scheme | ICC-Coordinator | The INToGIS 2 system has been undergoing development and minimum metadata would therefore be incorporated into the INToGIS 2 system.  Item closed |
| 4 | To define ENC scheme for SAIHC Region H. | ICC-Coordinator | Developments wrt the IHO GIS will assist in identifying existing gaps in the ENC schema and serve as a tool for future planning of ENC within the region.  Ongoing |
| 5 | Suggested trial teleconference | ICC-Coordinator | There will more focus on improving communications between MS to discuss pertinent charting matters by means of teleconference once we have established an effective and appropriate ‘freephone’ solution.  Ongoing |
| 6 | INT 7582 – is to be removed from S11 and the chart is to become INT 7583 (new INT number). A copy of this chart needs to be circulated to the members for comment and will be pending until this is done. | SAIHC Member States | INT 7582 removed from S11.  New chart INT 7583 has been added to S-11 (national number still to be decided). Mozambique and Portugal still in discussions and work is progressing.    Ongoing |
| 7 | INT 7631 & INT 7632 - ongoing discussions between UK, MZ and PT. New survey data is awaited and this will affect buoyage’s and chart limits (which still need to be confirmed). | UK  Portugal  Mozambique | Ongoing |
| 8 | INT 7645 – the Scheme has been proposed and is in process. As soon as the limits have been established they are to be forwarded to the chairman for inclusion in S11. | PT/MZ | Ongoing |
| 9 | Member States to feedback comments on how CATZOC is to be used to DQWG. | Member States | Only 6 nations have provided feedback.  Ongoing |
| 10 | UK, Tanzania, Kenya, and India to coordinate ENC requirements to provide the latest data in a carriage compliant product for the Mariner and report back to ICCWG coordinator. | UK, Tanzania, Kenya, India | Ongoing |
| 11 | PCA to coordinate with Kenya and Tanzania ENC priorities and create a plan for ENC scheme. | UK, Kenya, Tanzania | This action would be included and is part of defining the ENC scheme for SAIHC Region H using the tools in the newly developed IHO GIS.  Item closed |
| 12 | India and UK to confirm when overlaps with GB ENCs have been removed in Seychelles, Tanzania and Mozambique | India and UK | Ongoing |
| 13 | To provide a report on the latest state of overlaps in SAIHC region. | ICC-Coordinator | Item closed |