**Status of Actions from DQWG 18**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Action Number** | **Action** | **Delegate** | **Target date** | **Status** |
| 18/01 | DQWG Members were invited to update the DQWG Membership list and contact details. | All | *Permanent* |  |
| 18/02 | Monitor the progress of IHO ISO 9001 Cell and report Data Quality matters back to the group in order to improve risk mitigation: S-98/consistent data quality information across S-101/S-1xx ECDIS Route Monitoring products in particular. | Chair | DQWG 19 | On progress. |
| 18/03 | Arising from TWCWG7  (28 Feb – 02 Mar 2023). Provide comments back to the TWCWG and to use the guidance included in Part C of S-97 as the template for comments. | Chair & PRIMAR | DQWG 19 | Done –TWCWG7. |
| 18/04 | Report to CSBWG14 or Ms. Jennifer Jenckson, the “Survey to CATZOC” Guidelines Ed.1.0.0 (to be published in 2023). | Chair | CSBWG14 (16-18 August 2023) | Done. The CSBWG Chair Ms. Jennifer Jenckson has been informed that "Guidelines and Recommendations for Hydrographic Offices for the allocation of CATZOC" Edition 1.0.0, which will be beneficial to evaluate the quality of CSB data and promote the application of CSB data, has been finished by DQWG and will be submitted to HSSC15 for approval as a new IHO Publication S-68. |
| 18/05 | SubWG to continue review of new and amended Product Specifications and report results to DQWG19. Members are invited to join the subWG. | Chair, NL, SE, US, UNH | DQWG 19 | The cross check of DQ chapters of 7 published S-100 PSs including S-124, S-130, S-131, S-201, S-240, S-401 and S-421 has been implemented – shared with subWG members via email on Jan 22nd 2024. |
| 18/06 | Submit the template as revision proposal for Appendix D of S-100 Part 11, to the S-100WG for consideration and possible inclusion in Ed. 5.1.0 of S-100. | Chair | S-100WG8 (13 - 17 November 2023) | Done. Mr. Sean LEGEER(USA), on behalf of Chair, has reported the template in S-100WG8. |
| 18/07 | Papers from S-100WG, NIPWG and TWCWG - report results to DQWG19 and to invite WGs to nominate a DQ focal point in their WGs and him/her to participate in the activities of the DQWG. | Chair | DQWG 19 | Done–TWCWG7, S-100WG8, NIPWG vtc02-2023.  DQ focal point: Raphael Malyankar (NIPWG) |
| 18/08 | DQWG agreed to establish a subWG to review the draft S-67 new edition and recommend edits to produce a first credible output for Mariners. Plan is to submit proposed draft S-67 Ed. 2.0.0 to HSSC-15 | Chair, SE, US, PRIMAR, NO, IT | HSSC15 (15 April 2023) | Done. New S-66 has been submitted to DQWG19. |
| 18/09 | Regarding S-1xx Feature Catalogues - Chair to feedback the review results and recommendations to S-1xx developers respectively. Members of S-1xx PTs to be invited to participate in the next review before submission of Ed. 2.0.0 in any case. | Chair | DQWG19 | Done–TWCWG7, S-100WG8, NIPWG vtc02-2023. |
| 18/10 | DQWG agreed to continue the cross check of other released S-1xx FCs. | Chair, US, FR, SevenCs | DQWG19 | Done. A Report has been submitted to DQWG19. |
| 18/11 | Regarding S-101PT, RENCs to consider providing stats on the progress of the encoding of POSACC/ SOUACC to the DQWG Chair prior to HSSC16 (Action HSSC14/59 refers) for an assessment of S-57 readiness. | Chair, RENCs | HSSC16 | On progress. |
| 18/12 | Submit the Document Edition 1.0.0 of a new Publication S-68 to HSSC 15 for approval, including reservations and add a short paragraph on the cartographic aspects in the foreword. SE to draft the short paragraph and provide it to the Chair. | Chair, SE | HSSC15 (15 April 2023) | Done – HSSC15 |
| 18/13 | Regarding ‘Survey to CATZOC” document, Chair to recommend to HSSC15 the continuation of this task and subWG to continue the work and update the document. | Chair, subWG | HSSC15 (15 April 2023) | Done – HSSC15 |
| 18/14 | Chair to liaise with IHO Secretariat to release the Guidelines and recommendations for Hydrographic Offices for the allocation of CATZOC on the IHO Website after HSSC15 approves the document. | Chair, IHO Secretariat | DQWG19 | HSSC15/57: HSSC approved Ed. 1.0.0 of S-68 for initial implementation, testing and evaluation.  IHO Member States were invited to provide their initial feedback to the DQWG. |
| 18/15 | Chair to liaison with S-100WG to inform that the DQWG has started a review and revision of S-100 Part 4c. | Chair | End of March 2023 | Done. S-100WG Chair has been informed that the DQWG has started a review and revision of S-100 Part 4C and S-97 Part C and the results will be submitted to S-100WG for consideration. |
| 18/16 | Chair to liaise with the S-100WG to inform that the DQWG has started a review and revision of S-97 Part C. | Chair | End of March 2023 | Done. S-100WG Chair has been informed that the DQWG has started a review and revision of S-100 Part 4C and S-97 Part C and the results will be submitted to S-100WG for consideration. |
| 18/17 | DQWG agreed to establish a subWG to review S-100Part 4c and S-97Part C but to limit the work to critical DQ issues only. | Chair, NL and PRIMAR | End of March 2023 | Done. Two proposals has been submitted to DQWG19. |
| 18/18 | DQWG agreed to upload the ISO definitions on the DQWG webpage as a working document. NL to provide the draft covering note and a disclaimer if appropriate. | NL, Chair, IHO Secretariat | March 2023 | On progress. |
| 18/19 | DQWG agreed to consider the DQ requirements of MASS. Members are invited to feedback their comments and recommendations to DQWG Chair, when appropriate. | Chair, All DQWG Members | DQWG19 | On progress. |
| 18/20 | Members are invited to consider participating in the S-100WG Validation Workshop in Middle of 2023 in Monaco (Contact: S-100 Validation SubWG Chair Ms. Elizabeth Hahessy, Email: elihh@gst.dk), and report to the Chair, and Chair to provide feedback with DQWG comments and recommendations on the DQ requirements in S-100 validation checks to S-100WG and S-1xx PTs. | All DQWG Members | End of March, 2023 | Done. |