## S-101PT Actions 20200907
S-101PT Actions @20200916
No. | Action | Detail | Lead | Status | Remarks
ENCWG5-01 | IHO S-52 PL Edition 4.0.3 | Update Readme file to clarify to ensure that the images reflect the mariner view. | IHO Sec | New Action
ENCWG5-02 | IHO S-52 PL Edition 4.0.3 | Delete M_NSYS covering the whole ‘Buoys and beacons (Q)’ area from ECDIS Chart 1 ENC AA4C1XMS. | HP | New Action
ENCWG5-03 | IHO S-52 PL Edition 4.0.3 | Add plot numbers in Section 16.2 and ensure that they cross-reference correctly with the Readme. | IHO Sec | New Action
ENCWG5-04 | IHO S-52 PL Edition 4.0.3 | Readme.txt, Shallow Water Pattern: More work required. AU to check. Possibly fix the plot. | AS | New Action
ENCWG5-05 | IHO S-52 PL Edition 4.0.3 | Include set-up instruction regarding Information about chart display (AB) in Readme.txt file. Update Foreword p. xiv table of contents by including entry describing the changes to the Readme.txt file. | IHO Sec | New Action
ENCWG5-06 | IHO S-52 PL Edition 4.0.3 | Include set-up instruction regarding ‘Highlight’ ECDIS function in Readme.txt file. Update Foreword p. xiv table of contents by including entry describing the changes to the Readme.txt file. | IHO Sec | New Action
ENCWG5-07 | IHO S-52 PL Edition 4.0.3 | 16.2 Port Features: Revised plot has been provided by Hannu. Needs to be resent to Tom M. | HP | New Action
ENCWG5-08 | IHO S-52 PL Edition 4.0.3 | 16.2 Seabed, Obstructions, Pipelines etc (J, K, L) : Revised plot provided by Hannu. Needs to be resent to Tom M. | HP | New Action
ENCWG5-09 | IHO S-52 PL Edition 4.0.3 | 16.2 Buoys and Beacons (Q): Apply changes as suggested. | HP | New Action
ENCWG5-10 | IHO S-52 PL Edition 4.0.3 | 18.2.7 Para 1: Review the content of this paragraph to better represent the way ECDIS Chart1 ENC are built up. | IHO Sec | New Action
ENCWG5-11 | IHO S-52 PL Edition 4.0.3 | S-52 PresLib Ed 4.0.2 Part I App C Look-up: Amend viewing group from 21 to 26 (TX(OBJNAM,3,1,2,'15110',1,0,CHBLK,21)); Apply change as clarification. | IHO Sec | New Action
ENCWG5-12 | IHO S-52 PL Edition 4.0.3 | PresLib_e4.0.2.dai (CHRVID01, CHDATD01 and CHRVID02 draw incorrectly. Refer to ENCWG4Action 5.2): More work required. Further investigation required. | HP | New Action
ENCWG5-13 | IHO S-52 PL Edition 4.0.3 | S-52 Sub-Group to be formed to address other comments via future on-line meeting(s). Names to be supplied to IHO Sec (Tony and Jeff). | ENCWG | Completed | List of participants in the S-52 Sub-Group as at 21 September 2020: Tom M (lead), Alvaro, Christian, Hannu, Jochen, Inga, Verena, Yong, Jeff
ENCWG5-14 | IHO S-58 | Check 19: More work required. Defer to S-58 Sub-WG. | RF | New Action
ENCWG5-15 | IHO S-58 | Check 44: New proposed 44b: Possible clash with another Check (1768?): Apply change, with possible refinement required, and apply associated changes to the UOC. | IHO Sec | New Action
ENCWG5-16 | IHO S-58 | All other Checks will need to be covered by a smaller group (S-58 Sub-WG). Volunteers for this group to be provided to Richard, cc to IHO Sec (Tony and Jeff). | ENCWG | Completed
ENCWG5-17 | IHO S-58 | In addition to the list of proposed changes provided by the S-58 Sub-WG Leader, proposed changes from AU (refer ENCWG5-11A – Amendments to ENC Validation Checks), that were not discussed at the meeting, will be discussed by the volunteer group. | S-58 Sub-Group | New Action
ENCWG5-18 | IHO S-63 | Robert will ensure that a single text and picture file would be included in the test data. | RS | New Action
ENCWG5-19 | IHO S-63 | Tony/Yong is going to investigate a location to host the test data, possibly on the Github site along with the S-58 test data sets. | IHO Sec/Chair | New Action
ENCWG5-20 | IHO S-63 | Antonio Di Lieto (Carnival) will provide contact details in regard to a contact on end-user impact. Suggestions for other possible options included Intertanko, The Nautical Institute and other shipping companies. | ADL | New Action
ENCWG5-21 | IHO S-63 | Create a small sub-WG to formulate the Impact Assessment fully so that it is ready to be circulated (including the impact of the supply of corrupt files). Volunteers for this group to be provided to ENCWG Chair, cc to IHO Sec (Tony and Jeff). | ENCWG | Completed
ENCWG5-22 | HSSC Letter 03/2020 and Report to HSSC12 | Chair and Vice Chair to coordinate on developing a paper addressing HSSC issues raised to the ENCWG for the HSSC. | Chair/Vice-Chair | New Action
ENCWG5-23 | Consider removing the term Master/Slave | Chair to provide an input paper from ENCWG to the HSSC (input from US (Megan) and IIC (Jonathan) – any other ENCWG member is invited to participate). Circulate to the WG to review before publication. | Chair/MB/JP | Completed
ENCWG5-24 | S-52 – Missing CSP missing from the PL | Chair to further investigate (refer paper S-100WG5-11) – possibly remove LUT reference. | Chair | New Action
ENCWG5-25 | Maximum Permissible ENC File Size | Further work required. Defer discussion until closer to S-101 implementation taking into account the duel fuel ECDIS. | Chair/AS | New Action
ENCWG5-26 | Grouping of Soundings in ENC Updates | Further work required. AU, DK and IHO Sec to look at including some “best practice” guidance on soundings included by Update in the UOC. | AS/RF/IHO Sec | New Action
ENCWG5-27 | Use of the Edge Attribute USAG C by ECDIS | Further work required. To be incorporated in discussions for the S-58 Sub-WG (refer agenda ENCWG5-7) | S-58 Sub-Group | New Action
ENCWG5-28 | Agree to Move Forward with Encoding Proposals | Create a small sub-WG to further develop proposals for optimizing S-57 datasets for conversion to S-101. Volunteers for this group to be provided to ENCWG Chair, cc to IHO Sec (Tony and Jeff). | ENCWG | Completed
ENCWG5-29 | Agree to Move Forward with Encoding Proposals | Chair to discuss with S-101PT Chair as to best way to proceed. | Chair/TR | New Action
ENCWG5-30 | S-64 Edition 3.0.3 | Create a small sub-WG to evaluate the clarifications applied to S-64. Volunteers for this group to be provided to ENCWG Chair, cc to IHO Sec (Tony and Jeff). | ENCWG | Completed

## CompletedClosed
S-101PT Actions @20200916
Source | Action | Detail | Lead | Status | Remarks