## ENCWG6
ENCWG6 Actions @20221116
No. | Action | Detail | Lead | Status | Remarks
ENCWG6-01 | Member | ENCWG members and Stakeholders to provide the IHO Sec. with their updates to the ENCWG List of Contacts. | All | Ongoing
ENCWG6-02 | S-63 | ENCWG members interested in participating in the S-63 Cyber-Security Sub-Group to notify the Chair at their earliest convenience. | All | Completed | Ref. List of ENCWG members
ENCWG6-03 | IHO S-52 PL Edition 4.0.4 | Chair/S-52 Sub-Group reviews the issues on the papers and drafts a new clarification version of S-52 PL 4.0.4 and submits it at the next WG for approval. | Chair/S-52sub-Group | Ongoing | Ref. Agenda WG7-4.7
ENCWG6-04 | IHO S-58 Test Datasets | S-58 Sub-Group considerate of the impact of the revised Checks for isolated shoals and deeps where the shoal or deep is intersected by the ENC cell data limit. | S-58 Sub-Group | Ongoing | Ref. Agenda WG7-4.13
ENCWG6-05 | IHO S-58 Edition 7.0.0 | IHO Secretariats prepares the final draft Edition 7.0.0 of S-58 for final ENCWG endorsement and Chair submits it to the HSSC for endorsement to proceed to publication. | IHO Sec/Chair | Completed | Ref. HSSC14-5.2A
ENCWG6-06 | S-63 Cyber Security | The Sub-group drafts a first edition and submit it to the next WG for endorsement. | S-63 Sub-Group | Ongoing | Ref. Agenda WG7-4.5
ENCWG6-07 | Study on ECDIS use | The document will be provided by the IHO Sec(Yong) upon request. Any review comment on the document to be submitted to Chair at their earliest convenience (no later than 02 July). | All | Completed
ENCWG6-08 | SOE issue | ENCWG members interested in participating in the ECDIS Display Correspondence Sub-Group to notify the Chair at their earliest convenience. | All | Completed
ENCWG6-09 | SOE issue | ECDIS Display Correspondence Sub-Group review of test data to support testing by Data Producers and for inclusion with the OEM survey to be conducted; and the feedback form for the OEM survey to be developed | Display Sub-GrouP | Completed
ENCWG6-10 | SOE issue | Chair/ECDIS Display Correspondence Sub-Group upon collation of the results of the OEM survey, an interim ENCWG to be convened to discuss findings and refine guidance as required. | Chair | Ongoing | Ref. Agenda WG7-4.2
ENCWG6-11 | SOE issue | 7Cs reports to be provided on ECDIS upgrades at the next (interim) meeting of the ENCWG. | 7Cs | Completed | Ref. ENCWG_VTC1-11
ENCWG6-12 | S-57 Appendix B-1 Annex A | IHO Sec. prepares a final draft Revision 4.3.0 of the UOC to be prepared for submission to the HSSC for endorsement to proceed to publication | IHO Sec | Completed | Ref. HSSC14-5.2A
ENCWG6-13 | S-57 Appendix B-1 Annex A | IHO Sec removes the full date range option for attributes PEREND and PERSTA | IHO Sec | Completed | Ref. HSSC14-5.2A
ENCWG6-14 | S-57 to S-101 conversion | The Sub-Group provides WG chair/IHO Sec status of the conversion and summary of the guideline document in order to support C-5 report of HSSC | Conversion Sub-Group | Completed
ENCWG6-15 | S-57 to S-101 conversion | Chair proposes to the HSSC that the “S-57 to S-101 Conversion Guidance” document be included as an Appendix to S-65. | Chair | Completed | Ref. HSSC14-5.2A
ENCWG6-16 | S-57 to S-101 conversion | PT chair provides WG chair status of the conversion and summary of the guideline document to support C-5 report. | PT chair | Completed | Ref. HSSC13/30
ENCWG6-17 | HDENC | ENCWG members interested in providing information on their process for generating contours for HD ENCs and/or participating in a small group to compile this information into a single document for reference to notify the Chair at their earliest convenience. | HDENC Sub-Group | Completed | Ref. Agenda WG7-4.6