## ENCWG6 Actions
ENCWG Actions @15Feb2022
No. | Action | Detail | Lead | Status | Remarks
ENCWG6-01 | General | ENCWG members and Stakeholders to provide the IHO Sec. with their updates to the ENCWG List of Contacts. | IHO Sec | Done
ENCWG6-02 | S-63 | ENCWG members interested in participating in the S-63 Cyber-Security Sub-Group to notify the Chair at their earliest convenience. | All | Done
ENCWG6-03 | S-52 ed 4.0.4 | Chair/S-52 Sub-Group reviews the issues on the papers and drafts a new clarification version of S-52 PL 4.0.4 and submits it at the next WG for approval. | Chair/S-52SG | Completed | ENCWG VTC1-4
ENCWG6-04 | S-58 Ed.7.0.0 | S-58 Sub-Group considerate of the impact of the revised Checks for isolated shoals and deeps where the shoal or deep is intersected by the ENC cell data limit. | S-58SG | Completed | ENCWG VTC1-5
ENCWG6-05 | S-58 Ed.7.0.0 | IHO Secretariats prepares the final draft Edition 7.0.0 of S-58 for final ENCWG endorsement and Chair submits it to the HSSC for endorsement to proceed to publication. | IHO Sec | Completed | ENCWG VTC1-5
ENCWG6-06 | Cyber Security Guideline | The Sub-group drafts a first edition and submit it to the next WG for endorsement. | Subgroup | On going
ENCWG6-07 | Study on ECDIS use from practitioners | The document will be provided by the IHO Sec(Yong) upon request. Any review comment on the document to be submitted to Chair at their earliest convenience (no later than 02 July). | all | Done
ENCWG6-08 | Display issue | ENCWG members interested in participating in the ECDIS Display Correspondence Sub-Group to notify the Chair at their earliest convenience. | all | Done
ENCWG6-09 | Display issue | ECDIS Display Correspondence Sub-Group review of test data to support testing by Data Producers and for inclusion with the OEM survey to be conducted; and the feedback form for the OEM survey to be developed. | Subgroup | On going
ENCWG6-10 | Display issue | Chair/ECDIS Display Correspondence Sub-Group upon collation of the results of the OEM survey, an interim ENCWG to be convened to discuss findings and refine guidance as required. | Subgroup | On going
ENCWG6-11 | Display issue | 7Cs reports to be provided on ECDIS upgrades at the next (interim) meeting of the ENCWG. | 7Cs
ENCWG6-12 | ENC UOC | IHO Sec. prepares a final draft Revision 4.3.0 of the UOC to be prepared for submission to the HSSC for endorsement to proceed to publication | IHO Sec | Completed | ENCWG VTC1-6
ENCWG6-13 | Enc UOC | ENCWG approved the proposal, with the caveat that the full date format is removed as allowable for PEREND and PERSTA. | IHO Sec | Completed
ENCWG6-14 | S-57 to S-101 conversion | The Sub-Group provides WG chair/IHO Sec status of the conversion and summary of the guideline document in order to support C-5 report of HSSC. | PT chair | Completed
ENCWG6-15 | S-57 to S-101 conversion | Chair proposes to the HSSC that the “S-57 to S-101 Conversion Guidance” document be included as an Appendix to S-65. | PT chair
ENCWG6-16 | S-57 to S-101 conversion | PT chair provides WG chair status of the conversion and summary of the guideline document to support C-5 report. | PT chair | Done
ENCWG6-17 | Generation of depth contours | ENCWG members interested in providing information on their process for generating contours for HD ENCs and/or participating in a small group to compile this information into a single document for reference to notify the Chair at their earliest convenience. | all | Done

## ENCWG5 Actions
ENCWG Actions @15Feb2022
No. | Action | Detail | Lead | Status | Remarks
ENCWG5-01 | IHO S-52 PL Edition 4.0.3 | Update Readme file to clarify to ensure that the images reflect the mariner view. | IHO Sec | Completed
ENCWG5-02 | IHO S-52 PL Edition 4.0.3 | Delete M_NSYS covering the whole ‘Buoys and beacons (Q)’ area from ECDIS Chart 1 ENC AA4C1XMS. | HP | Completed
ENCWG5-03 | IHO S-52 PL Edition 4.0.3 | Add plot numbers in Section 16.2 and ensure that they cross-reference correctly with the Readme. | IHO Sec | Completed
ENCWG5-04 | IHO S-52 PL Edition 4.0.3 | Readme.txt, Shallow Water Pattern: More work required. AU to check. Possibly fix the plot. | AS | Completed
ENCWG5-05 | IHO S-52 PL Edition 4.0.3 | Include set-up instruction regarding Information about chart display (AB) in Readme.txt file. Update Foreword p. xiv table of contents by including entry describing the changes to the Readme.txt file. | IHO Sec | Completed
ENCWG5-06 | IHO S-52 PL Edition 4.0.3 | Include set-up instruction regarding ‘Highlight’ ECDIS function in Readme.txt file. Update Foreword p. xiv table of contents by including entry describing the changes to the Readme.txt file. | IHO Sec | Completed
ENCWG5-07 | IHO S-52 PL Edition 4.0.3 | 16.2 Port Features: Revised plot has been provided by Hannu. Needs to be resent to Tom M. | HP | Completed
ENCWG5-08 | IHO S-52 PL Edition 4.0.3 | 16.2 Seabed, Obstructions, Pipelines etc (J, K, L) : Revised plot provided by Hannu. Needs to be resent to Tom M. | HP | Completed
ENCWG5-09 | IHO S-52 PL Edition 4.0.3 | 16.2 Buoys and Beacons (Q): Apply changes as suggested. | HP | Completed
ENCWG5-10 | IHO S-52 PL Edition 4.0.3 | 18.2.7 Para 1: Review the content of this paragraph to better represent the way ECDIS Chart1 ENC are built up. | IHO Sec | Completed
ENCWG5-11 | IHO S-52 PL Edition 4.0.3 | S-52 PresLib Ed 4.0.2 Part I App C Look-up: Amend viewing group from 21 to 26 (TX(OBJNAM,3,1,2,'15110',1,0,CHBLK,21)); Apply change as clarification. | IHO Sec | Completed
ENCWG5-12 | IHO S-52 PL Edition 4.0.3 | PresLib_e4.0.2.dai (CHRVID01, CHDATD01 and CHRVID02 draw incorrectly. Refer to ENCWG4Action 5.2): More work required. Further investigation required. | HP | Completed
ENCWG5-13 | IHO S-52 PL Edition 4.0.3 | S-52 Sub-Group to be formed to address other comments via future on-line meeting(s). Names to be supplied to IHO Sec (Tony and Jeff). | ENCWG | Completed | List of participants in the S-52 Sub-Group as at 21 September 2020: Tom M (lead), Alvaro, Christian, Hannu, Jochen, Inga, Verena, Yong, Jeff
ENCWG5-14 | IHO S-58 | Check 19: More work required. Defer to S-58 Sub-WG. | RF | Completed
ENCWG5-15 | IHO S-58 | Check 44: New proposed 44b: Possible clash with another Check (1768?): Apply change, with possible refinement required, and apply associated changes to the UOC. | IHO Sec | Completed
ENCWG5-16 | IHO S-58 | All other Checks will need to be covered by a smaller group (S-58 Sub-WG). Volunteers for this group to be provided to Richard, cc to IHO Sec (Tony and Jeff). | ENCWG | Completed
ENCWG5-17 | IHO S-58 | In addition to the list of proposed changes provided by the S-58 Sub-WG Leader, proposed changes from AU (refer ENCWG5-11A – Amendments to ENC Validation Checks), that were not discussed at the meeting, will be discussed by the volunteer group. | S-58 Sub-Group | Completed
ENCWG5-18 | IHO S-63 | Robert will ensure that a single text and picture file would be included in the test data. | RS | Completed
ENCWG5-19 | IHO S-63 | Yong is going to investigate a location to host the test data, possibly on the Github site along with the S-58 test data sets. | IHO Sec/Chair | Completed
ENCWG5-20 | IHO S-63 | Antonio Di Lieto (Carnival) will provide contact details in regard to a contact on end-user impact. Suggestions for other possible options included Intertanko, The Nautical Institute and other shipping companies. | ADL | Closed
ENCWG5-21 | IHO S-63 | Create a small sub-WG to formulate the Impact Assessment fully so that it is ready to be circulated (including the impact of the supply of corrupt files). Volunteers for this group to be provided to ENCWG Chair, cc to IHO Sec (Tony and Jeff). | ENCWG | Completed
ENCWG5-22 | HSSC Letter 03/2020 and Report to HSSC12 | Chair and Vice Chair to coordinate on developing a paper addressing HSSC issues raised to the ENCWG for the HSSC. | Chair/Vice-Chair | Done
ENCWG5-23 | Consider removing the term Master/Slave | Chair to provide an input paper from ENCWG to the HSSC (input from US (Megan) and IIC (Jonathan) – any other ENCWG member is invited to participate). Circulate to the WG to review before publication. | Chair/MB/JP | Completed
ENCWG5-24 | S-52 – Missing CSP missing from the PL | Chair to further investigate (refer paper S-100WG5-11) – possibly remove LUT reference. | Chair | Completed
ENCWG5-25 | Maximum Permissible ENC File Size | Further work required. Defer discussion until closer to S-101 implementation taking into account the duel fuel ECDIS. | Chair/AS | Ongoing
ENCWG5-26 | Grouping of Soundings in ENC Updates | Further work required. AU, DK and IHO Sec to look at including some “best practice” guidance on soundings included by Update in the UOC. | AS/RF/IHO Sec | Ongoing
ENCWG5-27 | Use of the Edge Attribute USAG C by ECDIS | Further work required. To be incorporated in discussions for the S-58 Sub-WG (refer agenda ENCWG5-7) | S-58 Sub-Group | Ongoing
ENCWG5-28 | Agree to Move Forward with Encoding Proposals | Create a small sub-WG to further develop proposals for optimizing S-57 datasets for conversion to S-101. Volunteers for this group to be provided to ENCWG Chair, cc to IHO Sec (Tony and Jeff). | ENCWG | Completed
ENCWG5-29 | Agree to Move Forward with Encoding Proposals | Chair to discuss with S-101PT Chair as to best way to proceed. | Chair/TR | Ongoing
ENCWG5-30 | S-64 Edition 3.0.3 | Create a small sub-WG to evaluate the clarifications applied to S-64. Volunteers for this group to be provided to ENCWG Chair, cc to IHO Sec (Tony and Jeff). | ENCWG | Completed
ENCWG Catch-Up Feb 2021 | S-52 & S-64 Clarifications, Approval & Publication | Post minor revisions of S-52 and S-64 on IHO web site. | IHO Sec | Completed
ENCWG Catch-Up Feb 2021 | S-52 & S-64 Clarifications, Approval & Publication | Yong to give a presentation on the Technology Lab in Singapore to ENCWG6 and discuss how they can support ENCWG work. | YB | New Action
ENCWG Catch-Up Feb 2021 | S-63 | WG members to initiate contact with ECDIS stakeholders in their country and request that they check and update their contact details at the IHO Secretariat. | ENCWG | New Action
ENCWG Catch-Up Feb 2021 | S-58 Edition 7.0.0 Report | Draft changes to UOC iaw Frank’s paper on encoding DRVAL1 and DRVAL2 for isolated shoals and deeps. | JW | Completed | Draft UOC Edition 4.3.0 to be submitted to ENCWG6.
ENCWG Catch-Up Feb 2021 | S-57 to S-101 Report, Recommendations | Any member of the ENCWG that would like to participate in the S-57 to S-101 Conversion Sub-Group to indicate their interest to Jonathan/Christian/Jeff. | ENCWG | Closed
ENCWG Catch-Up Feb 2021 | Future of ENC Display Sub-Group | Form small group to evaluate proposals of the ENC Display Sub-Group so as to forward to the correct group for further evaluation. Any member of the ENCWG that would like to participate in this work to indicate their interest to Christian. | ENCWG | New Action | Christian (lead), Alvaro, IHO Sec
ENCWG Catch-Up Feb 2021 | IC-ENC Technical Issues | Develop draft ENC EB and guidance for the UOC clarifying the number of decimal places to be encoded for the attribute VALSOU. | JW/RF | New Action
ENCWG Catch-Up Feb 2021 | IC-ENC Technical Issues | Create S-58 Test Dataset to test loading of Update datasets in ECDIS containing “reused” RCID values. Investigate possibility of accessing the IHO Special Projects Fund to create the test dataset. | Chair/RF/IHO Sec | New Action | Tom R will provide the dataset in question directly to RF.

## CompletedClosed
ENCWG Actions @15Feb2022
Source | Action | Detail | Lead | Status | Remarks