## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Manually Scheduled | Publish interim DCEG version 1.0.1 | 27 days | 22 January 2021 8:00 AM | 01 March 2021 5:00 PM |  | 1
2 | Yes | Manually Scheduled | Review cycle - S-101 PS (1.0.0) and DCEG (1.0.1) | 87 days | 02 March 2021 8:00 AM | 30 June 2021 5:00 PM | 1 | 1
3 | Yes | Manually Scheduled | Publish 'Incomplete' Draft PC (0.9.x) in IHO's Github repository | 66 days | 02 March 2021 8:00 AM | 01 June 2021 5:00 PM |  | 1
4 | Yes | Manually Scheduled | Finalise portrayal impact assesment of remodelled S-57 to S-101 (1.0.0) Features and Attributes | 274 days | 15 October 2020 8:00 AM | 02 November 2021 5:00 PM |  | 1 | Required to generate a 'Complete' S-101 PC draft for peer review, testbeds, etc
5 | Yes | Manually Scheduled | Update Rules and develop draft symbols | 134 days | 03 November 2021 8:00 AM | 09 May 2022 5:00 PM | 4 | 1 | Currently (Feb 2022) in progress plus scope extended due to additional changes as a result of Gap analysis against FC 1.0.2.
6 | Yes | Manually Scheduled | Present portrayal changes recommendations to S-101PT for endorsement | 7 days | 10 May 2022 8:00 AM | 18 May 2022 5:00 PM | 5 | 1
7 | Yes | Auto Scheduled | Submit new symbology for external stakeholder review | 3 days | 19 May 2022 8:00 AM | 23 May 2022 5:00 PM | 6 | 1 | According to current 'Portrayal changes workflow' this requires 3months and involves NCWG, Mariners and S-100TSM. To speed up the proces of having a complete S-101 PC 1.0.0, the S-101 executive decided not to involve mariners or S-100TSM at this stage.
8 | Yes | Auto Scheduled | New symbology - Stakeholders review period | 90 days | 24 May 2022 8:00 AM | 26 September 2022 5:00 PM | 7 | 1
9 | Yes | Auto Scheduled | Apply stakeholder's feedback and upload S-101 PC 1.0.2 to Github for peer review | 20 days | 27 September 2022 8:00 AM | 24 October 2022 5:00 PM | 8 | 1 | PC version would be aligned with FC 1.0.2 - Should we call it PC 1.0.2 athough a version 1.0.0 was never uploaded to the IHO Registry ???
10 | Yes | Auto Scheduled | S-101 PC 1.0.2 Peer review process in Github | 33 days | 25 October 2022 8:00 AM | 08 December 2022 5:00 PM | 9 | 1
11 | Yes | Auto Scheduled | Apply peer review corrections and complete final PC 1.0.2 draft | 13 days | 09 December 2022 8:00 AM | 27 December 2022 5:00 PM | 10 | 1 | This is to include rule changes requiered as a result of the gap analysis against FC/DCEG version 1.0.2
12 | Yes | Auto Scheduled | Process Registry changes resulting from the devlopment of new symbology | 23 days | 28 December 2022 8:00 AM | 27 January 2023 5:00 PM | 11 | 1
13 | Yes | Auto Scheduled | Publish S-101 Portrayal Catalogue 1.1.0 in GI Registry | 42 days | 30 January 2023 8:00 AM | 28 March 2023 5:00 PM | 12 | 1 | All new and S-57 remodellled features/attributes must be included in this version. ...
14 | Yes | Manually Scheduled | Endorsement of S-100 5.0.0 by HSSC | 3 days | 03 May 2022 8:00 AM | 05 May 2022 5:00 PM |  | 1 | Planned for HSSC-14
15 | Yes | Manually Scheduled | Approval of S-101 PS 1.1.0 | 60 days | 06 May 2022 8:00 AM | 28 July 2022 5:00 PM | 14 | 1
16 | Yes | Manually Scheduled | Approval of DCEG 1.1.0 | 60 days | 06 May 2022 8:00 AM | 28 July 2022 5:00 PM | 14 | 1
17 | Yes | Manually Scheduled | Approval of S-101 Validation Checks compliant with version 1.1.0 | 41 days | 29 July 2022 8:00 AM | 23 September 2022 5:00 PM | 15,16 | 1 | As a minimum, the plan is to have all CRITICAL checks completed at the time S-101 version 1.1.0 is published....
18 | Yes | Manually Scheduled | Publish S-101 Feature catalogue 1.1.0 in GI Registry | 1 day | 29 July 2022 8:00 AM | 29 July 2022 5:00 PM | 16,14,15 | 1
19 | Yes | Auto Scheduled | Submit S-101 version 1.1.0 for S100WG approval | 66 days | 26 September 2022 8:00 AM | 26 December 2022 5:00 PM | 18,16,15,17 | 1 | ...
20 | Yes | Manually Scheduled | Perform portrayal gap analysis between FC/DCEG S-101 1.1.0 & PC 1.0.2 | 30 days | 29 July 2022 8:00 AM | 08 September 2022 5:00 PM | 18,16,15 | 1 | This includes the updating of rules as reqired but, if new symbology is required, a full creation-approval cycle must be added to the GANTT.
21 | Yes | Manually Scheduled | Follow 'Portrayal changes workflow' to develop and approve new symbology that enables the cretion of S-101 PC 1.1.0 Drfat | 90 days | 09 September 2022 8:00 AM | 12 January 2023 5:00 PM | 20 | 1
22 | Yes | Manually Scheduled | Upload S-101 PC 1.1.0 Drfat to Github for peer review | 1 day | 13 January 2023 8:00 AM | 13 January 2023 5:00 PM | 21 | 1
23 | Yes | Manually Scheduled | S-101 PC 1.1.0 Peer review process in Github | 15 days | 16 January 2023 8:00 AM | 03 February 2023 5:00 PM | 22 | 1
24 | Yes | Manually Scheduled | Aply Peer review corrections and complete S-101 PC 1.1.0 Draft | 13 days | 06 February 2023 8:00 AM | 22 February 2023 5:00 PM | 23 | 1
25 | Yes | Manually Scheduled | Process Registry changes resulting from the devlopment of new symbology | 23 days | 23 February 2023 8:00 AM | 27 March 2023 5:00 PM | 24 | 1
26 | Yes | Manually Scheduled | Endorsement of S-101 version 2.0.0 by HSSC | 282 days | 18 April 2023 8:00 AM | 15 May 2024 5:00 PM | 28,29 | 1 | As per M-3 Resolution 2/2007 (as amended), the approval process for Edition 2.0.0 (Opertaional version) involves: ...
27 | [7 empty] | 1
28 | Yes | Manually Scheduled | S-101 1.2.0 - Exchange Catalogue |  |  |  |  | 1
29 | Yes | Manually Scheduled | S-101 1.2.0 - Data protection (compression, encryption and digital signatures) |  |  |  |  | 1
30 | Yes | Manually Scheduled | Publication of S-98 version 1.0.0 | 3 days | 03 May 2022 8:00 AM | 05 May 2022 5:00 PM |  | 1 | As per M-3 Resolution 2/2007 (as amended), the approval process for Edition 1.0.0 (Development Phase) involves: ...
31 | Yes | Manually Scheduled | Publish S-101 Alerts and Indications Catalogue aligned with 1.1.0 |  |  | 05 June 2023 5:00 PM |  | 1
32 | [7 empty] | 1
33 | Yes | Manually Scheduled | Publish S-164 Version 1.0.0 including S-101 Test datasets |  |  |  |  | 1 | As per M-3 Resolution 2/2007 (as amended), the approval process for Edition 1.0.0 (Development Phase) involves: ...
34 | Yes | Manually Scheduled | Publication of New version of IMO's MSC.232(82) ECDIS Performance Standard |  |  |  |  | 1 | Expected to be approved by MSCXX on dd/MMM/202n
35 | Yes | Manually Scheduled | Publication of New version of IEC Standards 61174, 62288 & 61924-2 |  |  |  | 34 | 1
36 | [7 empty] | 1
37 | [7 empty] | 1
38 | [7 empty] | 1
39 | [7 empty] | 1
40 | [7 empty] | 1
41 | [7 empty] | 1
42 | Yes | Manually Scheduled | DF-ECDIS Type approval commences |  |  |  | 33,35,34,26 | 1

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | KHOA | K | Work |  |  |  |  | 100% | $0.00/h | 0
2 | ALL | A | Work |  |  |  |  | 100% | $0.00/h | 0
3 | NIWC | N | Work |  |  |  |  | 100% | $0.00/h | 0
4 | S100TSWG | S | Work |  |  |  |  | 100% | $0.00/h | 0
5 | NCWG | N | Work |  |  |  |  | 100% | $0.00/h | 0
6 | IHO Secretariat | I | Work |  |  |  |  | 100% | $0.00/h | 0
7 | S100WG Chair | S | Work |  |  |  |  | 100% | $0.00/h | 0
8 | S101PT Chair | S | Work |  |  |  |  | 100% | $0.00/h | 0
9 | S-101 Portrayal subWG | S | Work |  |  |  |  | 100% | $0.00/h | 0
10 | S-101PT Vice-Chair | S | Work |  |  |  |  | 100% | $0.00/h | 0
11 | S-101 Project Team | S | Work |  |  |  |  | 100% | $0.00/h | 0
12 | HSSC | H | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Publish interim DCEG version 1.0.1 | IHO Secretariat | 1 | 216h | 100%
Review cycle - S-101 PS (1.0.0) and DCEG (1.0.1) | ALL | 1 | 696h | 100%
Publish 'Incomplete' Draft PC (0.9.x) in IHO's Github repository | IHO Secretariat | 1 | 528h | 100%
Publish 'Incomplete' Draft PC (0.9.x) in IHO's Github repository | NIWC | 1 | 528h | 100%
Finalise portrayal impact assesment of remodelled S-57 to S-101 (1.0.0) Features and Attributes | S-101 Portrayal subWG | 1 | 2,192h | 100%
Update Rules and develop draft symbols | KHOA | 0 | 536h | 50%
Update Rules and develop draft symbols | NIWC | 0 | 536h | 50%
Present portrayal changes recommendations to S-101PT for endorsement | S-101PT Vice-Chair | 0 | 56h | 100%
Submit new symbology for external stakeholder review | S-101PT Vice-Chair | 0 | 24h | 100%
New symbology - Stakeholders review period | NCWG | 0 | 720h | 100%
New symbology - Stakeholders review period | S100TSWG | 0 | 720h | 100%
Apply stakeholder's feedback and upload S-101 PC 1.0.2 to Github for peer review | NIWC | 0 | 160h | 100%
S-101 PC 1.0.2 Peer review process in Github | ALL | 0 | 264h | 100%
Apply peer review corrections and complete final PC 1.0.2 draft | NIWC | 0 | 104h | 100%
Process Registry changes resulting from the devlopment of new symbology | IHO Secretariat | 0 | 184h | 100%
Publish S-101 Portrayal Catalogue 1.1.0 in GI Registry | IHO Secretariat | 0 | 336h | 100%
Approval of S-101 PS 1.1.0 | S-101 Project Team | 0 | 480h | 100%
Approval of DCEG 1.1.0 | S-101 Project Team | 0 | 480h | 100%
Approval of S-101 Validation Checks compliant with version 1.1.0 | S-101 Project Team | 0 | 328h | 100%
Publish S-101 Feature catalogue 1.1.0 in GI Registry | IHO Secretariat | 0 | 8h | 100%
Submit S-101 version 1.1.0 for S100WG approval | S101PT Chair | 0 | 528h | 100%
Perform portrayal gap analysis between FC/DCEG S-101 1.1.0 & PC 1.0.2 | S-101 Portrayal subWG | 0 | 240h | 100%
Follow 'Portrayal changes workflow' to develop and approve new symbology that enables the cretion of S-101 PC 1.1.0 Drfat | IHO Secretariat | 0 | 720h | 100%
Follow 'Portrayal changes workflow' to develop and approve new symbology that enables the cretion of S-101 PC 1.1.0 Drfat | KHOA | 0 | 720h | 100%
Follow 'Portrayal changes workflow' to develop and approve new symbology that enables the cretion of S-101 PC 1.1.0 Drfat | NCWG | 0 | 720h | 100%
Follow 'Portrayal changes workflow' to develop and approve new symbology that enables the cretion of S-101 PC 1.1.0 Drfat | NIWC | 0 | 720h | 100%
Follow 'Portrayal changes workflow' to develop and approve new symbology that enables the cretion of S-101 PC 1.1.0 Drfat | S-101 Portrayal subWG | 0 | 720h | 100%
Upload S-101 PC 1.1.0 Drfat to Github for peer review | NIWC | 0 | 8h | 100%
S-101 PC 1.1.0 Peer review process in Github | ALL | 0 | 120h | 100%
Aply Peer review corrections and complete S-101 PC 1.1.0 Draft | NIWC | 0 | 104h | 100%
Process Registry changes resulting from the devlopment of new symbology | IHO Secretariat | 0 | 184h | 100%
Endorsement of S-101 version 2.0.0 by HSSC | HSSC | 0 | 2,256h | 100%
Publication of S-98 version 1.0.0 | IHO Secretariat | 0 | 24h | 100%