## Task_Table
Name | Duration | Start | Finish | Predecessors | Notes
Publish interim DCEG version 1.0.1 | 27 days | 2021-01-22 | 2021-03-01
Publication of New version of IMO's MSC.232(82) ECDIS Performance Standard | 1 day | 2021-04-27 | 2021-04-27 |  | Expected to be approved by MSCXX on dd/MMM/202n
Publish 'Incomplete' Draft PC (0.9.x) in IHO's Github repository | 66 days | 2021-03-02 | 2021-06-01
Review cycle - S-101 PS (1.0.0) and DCEG (1.0.1) | 87 days | 2021-03-02 | 2021-06-30 | 1
Finalise portrayal impact assesment of remodelled S-57 to S-101 (1.0.0) Features and Attributes | 274 days | 2020-10-15 | 2021-11-02 |  | Required to generate a 'Complete' S-101 PC draft for peer review, testbeds, etc
Endorsement of S-100 5.0.0 by HSSC | 3 days | 2022-05-03 | 2022-05-05 |  | Planned for HSSC-14
Publication of S-98 version 1.0.0 | 3 days | 2022-05-03 | 2022-05-05 |  | As per M-3 Resolution 2/2007 (as amended), the approval process for Edition 1.0.0 (Development Phase) involves: ...
<New Summary Task> | 41 days | 2022-07-29 | 2022-09-23
Approval of S-101 Validation Checks compliant with version 1.1.0 | 41 days | 2022-07-29 | 2022-09-23 | 11,12 | As a minimum, the plan is to have all CRITICAL checks completed at the time S-101 version 1.1.0 is published....
Update Rules and develop draft symbols | 258 days | 2021-11-03 | 2022-10-28 |  | Currently (Feb 2022) in progress plus scope extended due to additional changes as a result of Gap analysis against FC 1.0.2.
Finalise PC 1.0.2 and submit for S101PT9 endorsement | 1 day | 2022-11-22 | 2022-11-22
Submit new symbology for external stakeholder review | 52 days | 2022-09-12 | 2022-11-22 |  | According to current 'Portrayal changes workflow' this requires 3months and involves NCWG, Mariners and S-100TSM. To speed up the proces of having a complete S-101 PC 1.0.0, the S-101 executive decided not to involve mariners or S-100TSM at this stage....
S-101 PC 1.0.2 Peer review process in Github | 17 days | 2022-10-31 | 2022-11-22 | 5
Approval of S-101 PS 1.1.0 | 3 days | 2022-11-23 | 2022-11-25 | 10
Approval of DCEG 1.1.0 | 3 days | 2022-11-23 | 2022-11-25 | 10
Submit S-101 PS & DCEG version 1.1.0 for S100WG approval | 1 day | 2022-12-05 | 2022-12-05 | 12,11 | ...
Perform portrayal gap analysis between FC/DCEG S-101 1.1.0 & PC 1.0.2 | 30 days | 2022-11-28 | 2023-01-06 | 15,12,11 | This includes the updating of rules as reqired but, if new symbology is required, a full creation-approval cycle must be added to the GANTT.
Upload S-101 PC 1.1.0 Draft to Github for peer review | 1 day | 2023-02-20 | 2023-02-20 | 18
Complete submission of new portrayal change proposals (included in PC 1.1.0) to the GI Registry | 90 days | 2022-10-31 | 2023-03-03 | 17
S-101 PC 1.1.0 Peer review process in Github | 15 days | 2023-02-21 | 2023-03-13 | 19
Publish S-101 Portrayal Catalogue 1.1.0 in GI Registry | 1 day | 2023-03-31 | 2023-03-31 |  | All new and S-57 remodellled features/attributes must be included in this version. ...
Publish S-101 Feature catalogue 1.1.0 in GI Registry | 40 days | 2023-02-06 | 2023-03-31 | 12,10,11
S-101 1.2.0 - Exchange Catalogue | 1 day | 2023-07-01 | 2023-07-01
S-101 1.2.0 - Data protection (compression, encryption and digital signatures) | 1 day | 2023-07-01 | 2023-07-01
Finalise FC & DCEG 1.2.0 | 66 days | 2023-04-03 | 2023-07-01 | 15
Finalise PC 1.2.0 including A&I | 66 days | 2023-04-03 | 2023-07-01 | 9
Endorsement of S-101 version 1.2.0 by S100WG | 22 days | 2023-07-03 | 2023-08-01 | 31,30,26,27
Finalise FC & DCEG 2.0.0 | 45 days | 2023-08-01 | 2023-10-01
Finalise PC 2.0.0 | 45 days | 2023-08-01 | 2023-10-01
Publish S-164 Version 1.0.0 including Test datasets (S-57 & S-101) | 147 days | 2023-06-09 | 2023-12-31 |  | As per M-3 Resolution 2/2007 (as amended), the approval process for Edition 1.0.0 (Development Phase) involves: ...
Endorsement of S-101 version 2.0.0 by S100WG | 131 days | 2023-10-02 | 2024-03-31 | 21,22
Endorsement of S-101 version 2.0.0 by HSSC | 23 days | 2024-04-01 | 2024-05-01 | 26,27,23 | As per M-3 Resolution 2/2007 (as amended), the approval process for Edition 2.0.0 (Opertaional version) involves: ...
Publication of New version of IEC Standards 61174, 62288 & 61924-2 |  |  |  | 35
DF-ECDIS Type approval commences |  | 2024-07-01 |  | 34,36,35,24

## Resource_Table
Type | Material Label | Group | Email Address | User Logon Account | Standard Rate | Cost Per Use | Notes
Work |  |  |  |  | $0.00/hr | 0
Work |  |  |  |  | $0.00/hr | 0
Work |  |  |  |  | $0.00/hr | 0
Work |  |  |  |  | $0.00/hr | 0
Work |  |  |  |  | $0.00/hr | 0
Work |  |  |  |  | $0.00/hr | 0
Work |  |  |  |  | $0.00/hr | 0
Work |  |  |  |  | $0.00/hr | 0
Work |  |  |  |  | $0.00/hr | 0
Work |  |  |  |  | $0.00/hr | 0
Work |  |  |  |  | $0.00/hr | 0
Work |  |  |  |  | $0.00/hr | 0
Work |  |  |  |  | $0.00/hr | 0
Work |  |  |  |  | $0.00/hr | 0

## Assignment_Table
Work | Units
216 hrs | 100%
696 hrs | 100%
528 hrs | 100%
528 hrs | 100%
2,192 hrs | 100%
1,032 hrs | 50%
1,032 hrs | 50%
8 hrs | 100%
8 hrs | 100%
416 hrs | 100%
136 hrs | 100%
8 hrs | 100%
24 hrs | 100%
24 hrs | 100%
328 hrs | 100%
320 hrs | 100%
8 hrs | 100%
240 hrs | 100%
720 hrs | 100%
720 hrs | 100%
720 hrs | 100%
720 hrs | 100%
720 hrs | 100%
8 hrs | 100%
120 hrs | 100%
360 hrs | 100%
360 hrs | 100%
184 hrs | 100%
8 hrs | 100%
8 hrs | 100%
24 hrs | 100%
528 hrs | 100%
528 hrs | 100%
176 hrs | 100%
1,176 hrs | 100%
705.6 hrs | 100%