**10. HDWG/HDCG WORK PLAN 2024-2025**

**Tasks**

|  |  |
| --- | --- |
| A | Maintain and extend the definitions in the IHO S-32 Hydrographic Dictionary (IHO Task 2.8.2) |
| B | Liaise with other IHO bodies preparing publications containing glossaries (IHO Task 2.8.2) |
| C | Liaise with other organizations developing dictionaries and/or glossaries (IHO Task 2.8.2) |
| D | Change HDWG to HDCG (IHO Task 2.1.2.10) |
| E | Modernize the IHO S-32 Hydrographic Dictionary (IHO Task 2.8.2) |

**Work items**

| **Task**  | **Work item** | **Priority**H-highM-mediumL-low | **Next milestone** | **Start****Date** | **End****Date** | **Status**P-plannedO-ongoingC-completed | **Contact Person(s)****\* indicates leader** | **Related Pubs / Standard** | **Remarks** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A.1 | Endorse the Ed. 6.0.0 of S-32 “IHO Hydrographic Dictionary” and submit to HSSC16. | H |  | 2023 | 2024 | O | Chair | S-32 | New terms have been added by the Shom Delegate, which were previously absent in the English version but were included in the French version. |
| A.2 | Maintain and distribute the IHO S-32 Hydrographic Dictionary | H |  | 2023 | Permanent | O | Chair | S-32 | Through the Concept Registry |
| C.1 | Liaise with Member States who have developed a national HD | M |  | 2023 | 2024 | O | Chair |  | China, Indonesia, Spain |
| C.2 | Update the list of countries who wish to develop their own national HD | M |  | 2023 | 2024 | C | Chair HDCG |  | Oman, Japan |
| A.3 | Update the HD French national version  | L |  | 2023 | ? | P | SHOM Delegate  |  | Only if confirmed by Shom |
| D | Harmonize the S-32 IHO Hydrographic Dictionary database with the IHO GI Registry through the Concept Registry Domain Control Body | L |  | 2020 | 2024 | C | Chair HDCG | S-32 | The concept API service has been tested and can be called.To achieve the updating of HD database via a terminology API is a better approach. |
| D | Prepare the necessary steps to move the HDWG to HDCG | H | The workshop on the IHO HD and GI Registry | 2023 | 2024 | O | Chair HDCG | S-32 | Completion of HDCG ToRs Draft and Submission to HSSC16 |
| E.1 | Introduce a methodological approach to update the HD from a terminological perspective. | H | The workshop on the IHO HD and GI Registry | 2024 | 2025 | P | BSH (Lars Schiller) | S-32 |  |
| E.2 | Modernize the IHO S-32 Hydrographic Dictionary | H | The workshop on the IHO HD and GI Registry | 2024 | 2025 | P | IHO Sec (Jeff Wootton) | S-32 |  |
| E.3 | Further advance the establishment of a concept-centered terminology database | M |  | 2024 | 2026 | P | HDCG |  |  |

**Meetings** (IHO WP task 3.1.8)

|  |  |  |
| --- | --- | --- |
| **Date**  | **Location** | **Activity** |
| 27-28 November 2018 | IHO, Monaco | HDWG2 |
| 3 February 2022 | HD/GI Registry Workshop | VTC |
| 26 April 2022 | Discussion on Hydrospatial | VTC |
| Late 2024 (potential mid October ahead of the IHO Council), TBC. | IHO, Monaco | Workshop on the IHO HD and GI Registry |

Chair: Lyu Yu Xiao, China Email: 38893531@qq.com

Vice-Chair: Vacant Email:

Secretary: Samuel Harper, IHO Sec. Email: samuel.harper@iho.int