Release history for the document

| Date | Comments |
| --- | --- |
| 21-01-20 | Template - first version |
| 21-02-17 | Inputs from meeting with DQWG Chair (Rogier Broekman), Hans Engberg and Patrik Nilsson from the Swedish Maritime Administration |
| 16-08-21 | Update to reflect decisions made at ISO 9001 cell focus group VTC meeting on 12AUG2021. |
| 16-11-21 | Update to reflect decisions made at ISO 9001 cell focus group VTC meeting on 16NOV2021. |
| 03-03-22 | Update to reflect decisions made at ISO 9001 cell focus group VTC meeting on 03MAR2022. |
| 28-09-22 | Update to reflect decisions made at ISO 9001 cell focus group VTC meeting on 27SEP2022. |
| 03-02-23 | Update to reflect decisions made at ISO 9001 cell focus group VTC meeting on 03FEB2023. |
| 29-08-23 | Update to reflect strong dependencies with S-98 & S-164. These 2 standards are now part of the ISO 9001 cell scope. This document has been updated to reflect related risks and opportunities identified at meeting on 29AUG2023. |
| 14-12-23 | Update to reflect decisions made at ISO 9001 cell focus group VTC meeting on 14DEC2023 |
| 29-02-24 | Update to reflect decisions made at ISO 9001 cell focus group VTC meeting on 29FEB2024 |
| 04-04-24 | Update to reflect decisions made at ISO 9001 cell focus group VTC meeting on 04APR2024 |

Purpose

To manage risks and opportunities of the development of S-101 to the operational version 2.0.0 according to the ISO 9001 principles (6.1). Based on direct dependencies, this document will also track S-98 and S-164 progress.

Responsibility

S101PT Chair & S100WG Chair

Risks

|  |  |  |  |  | If Evaluation = high or medium |
| --- | --- | --- | --- | --- | --- |
| Description | Origin | Impact | Evaluation* | Date of review** | Actions to reduce risk | Resp. For action | Effectiveness of the action | Action taken and date |
| Lack of available human resources | internal | Delay in S-101 Ed 2.0.0 | High | Dec 2023 | -Raise awareness among MS on the importance of allocating the necessary resources | HSSC | Targeted communication to MS | Chair action PLANNED S-101PT Letter 5 of 2021 sought volunteers and indications of capacity. (13012022) Some improvement in contributions but pool of active contributors remains insufficient. (20022023) Contributions in Portrayal group have improved and some support to Test Datasets has been provided but the active contributions remain very limited to a small group. |
|  |  |  |  |  | -Organize regular remote meetings to maintain a good level of participation | S-101 chair /DQWG chair /NCWG chair | Remote meetings organized | ONGOING Schedule of regular meetings to be set out in Jan 2022. (20022023) Two physical PT meetings set for 2023 to maintain momentum. (TR - 20240918) Two meetings now planned for 2024 Feb and June noting HSSC approval timeframes. |
|  |  |  |  |  | - Investigate the possibility of finding funding (NOAA and IC-ENC Special Activities fund) to engage expert contributors in the S-100 validation work. | S-100WG Chair/S-101PT Chair |  | Julia Powell and Liz Hahessy will write a proposal for IC-ENC during TSM10. |
| Delay to draft & validate the different components mandatory for TRL 2,3,4 | internal |  | Medium | Feb 2023 | implement a regular and shared monitoring of actions | S-101 chair | GANTT diagram | S-101PT chair team/ISO cell continue to have regular meeting to review progress, prioritise work and develop strategies to keep the project within high-level timeframes. Downgraded to Medium |
| Delay in reviewing S-101 (FC, Encoding Guide, DQ Checks) Ed 1.n.n | internal |  | Medium | Feb 2023 | Harmonize timeframe, program reviewing & allocate resources | DQWG chair | GANTT diagram | A cross check has been conducted by DQWG but did not use the very latest DCEG version. Further review planned for 1.2.0 focusing on changes to reduce effort required. |
| Delay in reviewing portrayal catalog | internal |  | Medium | Feb 2023 | Harmonize timeframe, program reviewing & allocate resources | IHO Registry DCB | IHO registry reflects changes introduced in S100 Ed 5.0.0 New proposals are actioned within S-99 stablished timeframes | Risk level remains Medium until evidence exists that the ISO 9001 cell recommendations to the IHO Sec. regarding DCB staffing and processing timeframes are in place. |
| Upgrade of FC Builder to be compliant with S-100 Ed.5.2.0 | External |  | High | Feb 2024 | Monitor development by KOHA | IHO Sec |  | March 2024: Julia Powell to raise this issue to Yong and Martin Park (KOHA). |
| Overreliance on external support for the implementation and maintenance of the S100 GI Registry | External |  | Low | Feb 2023 | IHO to enter in more formal arrangements with KHOA in order to be able to influence requirements and UAT. It may require financial investment. | HSSC | IHO can influence design and functionalities of the IHO managed S100 GI Registry. IHO staff performs UAT and approves the release of enhancements and/or new versions. | Risk level remains Medium until evidence exists that the ISO 9001 cell recommendations to the IHO Sec. regarding the implementation of more detailed and formal agreements with MS/Industry partners are in place. March 2024: Risk set to low since it is handled by ICEPT |
| Insufficient clarity in the DF-ECDIS performance. | Internal |  | Medium | Feb 2023 | Approve and publish clear guidelines | HSSC | S-101PT is able to progress or delay the development and implementation of new proposals in a timely manner. | DF-Governance document has been endorsed by HSSC13. Practical implementation is still to be tested. Retain as medium until evidence exists the guidance provided is enough to drive development decisions. |
| Insufficient time to test Dual Fuel concept in S100 ECDIS prototypes | External |  | High | Feb 2023 | Allocate resources to develop DF-S100 ECDIS able to ingest and manage S-57 and S-101 ENC by mid 2023. | S100TSWG; HSSC | DF-S100 ECDIS exists and is utilized in a rigorous testbed environment by June 2023. | DF-ECDIS prototypes started to emerge and are participating in UKHO-SHOM testbed. Although S-164 document likely to be endorsed by HSSC15 in June 2023, OEMs do not yet have access to the corresponding DF Test datasets. No DF-ECDIS system available to S-164 development group. Iterative process adopted for exchange set implementation and release plan adopted to end 2023. Communication between subgroups working well (JP – 29/8/23). Little practical progress - Upgrade risk level to High. December 2023: First exchange set is finished for testing but still no testbed available. The timeline for S-98 and S-164 is adjusted upon request from IEC. |
| Lack of systems implementing full S-100 for iterative testing for inclusion in S-164 | External |  | Medium | September 2023 | Possible to adopt Partial simulation/validation approach in absence of full systems. Work with existing providers. | S164WG, S100WG | Workarounds giving confidence in absence of full system availability | Resources have been made available to the S-164 subgroup for validation of data intended for S-164. DF system developers engaged to produce DF input to S-164 in 2023 timescales (JP 29/8/23). |
| S-98 Annex C untested (in some areas) and incomplete | External |  | High | September 2023 | Dialogue with implementers (in-principle implementation) and outreach to other working groups | S164WG, S100WG | Endorsement by implementers for most risky elements of standard | September 2023. Outreach to other working groups, meetings and OEMs is under way. More S-98 content is being captured and mitigations for the most untested parts are beginning to be in place. There is much to do though. Implementers active in S-164/S-98 WG. Test Data required (JP 29/8/23). March 2024: A general discussion about how to handle this risk is needed at TSM10 (March 2024). |
| Insufficient time to test S-98 interoperability in S100 ECDIS prototypes | External |  | High | Sep 2023 | Allocate resources to develop S100 ECDIS able to ingest and manage all S100 products and interoperability catalogue by the end of 2023. | S100TSWG; HSSC | S100 ECDIS, necessary products and interoperability catalogue exist and are utilized in a rigorous testbed environment by December 2023. | It has been confirmed that KHOA will build the S-98 catalogue and IHO Sec have requested that the current draft be made available. Still awaiting this. This has been announced but not received yet, copy requested from IHO. No ECDIS available yet. Unlikely full testbed will be available by December 2023 (JP 29/8/23) |
| IHO implementation of the security scheme | External |  | Medium | May 2024 | Implement and test Security Scheme to enable testing towards operationalisation of S-100. | IHO Sec. | IHO Security Scheme and procedures are available for testing by May 2024. | NEW (20/9/23) – Responsibility of S100SSPT (refer to HSSC15 Action 15/29). The 1st objective of the PT is to develop the S-100 appointment and termination process for data servers, OEMs and ENDS service providers. A VTC is planned for Sept/October 2023. No evidence of progress so far. It’s important to note that this issue is one of implementation, and drawing together the standards with internal policy and procedures within the secretariat. The ISO 9001 Cell believes resourcing in Monaco to be a significant issue. Risk level set to Medium. HSSC Vice Chair to follow up with Tom Mellor. December 2023: The two first meetings are planned but no progress yet. March 2024: Some progress have been made within the PT. |
| Management and distribution of S100 Catalogues | External |  | High | May2024 | Establish a process for the management and distribution of S100 catalogues (FC, PC, IC). | IHO Sec. | A process for the effective and timely management of S100 catalogue versions (including release and stakeholders’ notification protocols) are in place by August 2024. | NEW (20/9/23) – The task could be linked to the scope of the ICEPT. No evidence of progress on this topic so far. Risk level set to Medium. HSSC Vice Chair to follow up with KHOA (PT Chair). December 2023: Papers from PRIMAR, IC-ENC and IIC discussed on S-100WG8 and will be further discussed at TSM10. The issue have not been discussed in ICEPT yet. Needs to be decided what functions the IHO Sec need to be able to deliver before an infrastructure centre is established. Risk increased to High since no process is in place. March 2024: This issue will be discussed further at TSM10 (March 2024). |

*Evaluation = high / medium / low	** to be reviewed at least annually

Opportunities

| Description | Benefits | Actions (to seize opportunities and limit risks) | Responsible | Deadline | Effectiveness of the action | Action taken and date |
| --- | --- | --- | --- | --- | --- | --- |
| Participation in the various Uses Cases organised in collaboration with the OEMs | Integrate feedbacks during development | Promote Uses cases | HSSC | - | Positive feedback from OEM Meeting deadlines (no extensive re-testing due to late consideration of feedbacks) | Linked to testbed reports. Awaiting final reports to assist HSSC develop good stories about S-100 implementation benefits. |
| Establish long term mariners review service agreement with IHO-Singapore Innovation laboratory in support of proposed new S-101 ECDIS portrayal and performance requirements in both, DF-ECDIS and post S-57 ENC retirement. | Objective, transparent and user driven process to accept/discard proposals related to the look and behavior of S-101 ENCs and the performance S-100 ECDIS. | Prepare and stablish long term support task with clear workflows and agreed timeframes for reporting findings and recommendations. Action S-101PT8-11 also refers. | IHO Sec. | October 2023 (?) | Request are processed within agreed timeframes. | Reliance on mariners engagement by each testbed. Consider S101PT CL to HSSC Chair ??. |
| The wider understanding of S-100 benefits could be improved through communication and supporting evidence. | Gives clarity to stakeholders and supports their investment in S-101/S-100. | Develop materials which clearly describe the impacts and benefits of S-101. Expand this using outcomes from testbeds. | HSSC? | October 2023 (?) | Graphical material (physical and/or online) is produced by the IHO highlighting major difference between S-57/S-52 and S-101. | Dependency with first row. S-101PT chair has started an S-101 Overview slide deck, Consider S101PT CL to HSSC Chair March 2024: Jonathan Prichard to liaise with Richard Doherty at CIRM to engage OEM’s for HSSC16. |

Performance indicators of S-101 PS process

| Progress on milestones from S-101 Ed 1.0.0 to Ed 2.0.0 |
| --- |
| Goal | Monitor progress to meet deadlines |
| Measurement field (KPI) | Milestones | Progress Status |
|  | Submit Edition 1.1.0 for S100WG Approval before HSSC15 | Completed |
|  | Submit Edition 1.2.0 for S100WG Approval by November 2023 | Completed |
|  | Submit Edition 2.0.0 for HSSC Endorsement by CL August 2024 | At Risk (Low) |
| Method and presentation of results | GANTT Diagram |
| Update periodicity | 3 months |
| Accountable | S101PT Chair & S100WG Chair |

It is important to note that S-164 and S-98 Annex C are considered to be in the critical path for an operational DF-ECDIS from 2026.

GANTT Diagram

Currently managed in MS Project