## Task_Table
Name | Start | Finish | Notes
Publish interim DCEG version 1.0.1 | 2021-01-22 | 2021-03-01 17:00
Publication of New version of IMO's MSC.232(82) ECDIS Performance Standard | 2021-04-27 | 2021-04-27 | Expected to be approved by MSCXX on dd/MMM/202n
Publish 'Incomplete' Draft PC (0.9.x) in IHO's Github repository | 2021-03-02 | 2021-06-01
Review cycle - S-101 PS (1.0.0) and DCEG (1.0.1) | 2021-03-02 | 2021-06-30
Finalise portrayal impact assesment of remodelled S-57 to S-101 (1.0.0) Features and Attributes | 2020-10-15 | 2021-11-02 | Required to generate a 'Complete' S-101 PC draft for peer review, testbeds, etc
Endorsement of S-100 5.0.0 by HSSC | 2022-05-03 | 2022-05-05 | Planned for HSSC-14
Publication of S-98 version 1.0.0 | 2022-05-03 | 2022-05-05 | As per M-3 Resolution 2/2007 (as amended), the approval process for Edition 1.0.0 (Development Phase) involves: ...
Approval of S-101 Validation Checks compliant with version 1.1.0 | 2022-07-29 | 2022-09-23 | As a minimum, the plan is to have all CRITICAL checks completed at the time S-101 version 1.1.0 is published....
Update Rules and develop draft symbols | 2021-11-03 | 2022-10-28 | Currently (Feb 2022) in progress plus scope extended due to additional changes as a result of Gap analysis against FC 1.0.2.
Finalise PC 1.0.2 and submit for S101PT9 endorsement | 2022-11-22 | 2022-11-22
Submit new symbology for external stakeholder review | 2022-09-12 | 2022-11-22 | According to current 'Portrayal changes workflow' this requires 3months and involves NCWG, Mariners and S-100TSM. To speed up the proces of having a complete S-101 PC 1.0.0, the S-101 executive decided not to involve mariners or S-100TSM at this stage....
S-101 PC 1.0.2 Peer review process in Github | 2022-10-31 | 2022-11-22
Approval of S-101 PS 1.1.0 | 2022-11-23 | 2022-11-25
Approval of DCEG 1.1.0 | 2022-11-23 | 2022-11-25
Submit S-101 PS & DCEG version 1.1.0 for S100WG approval | 2022-12-05 | 2022-12-05 | ...
Perform portrayal gap analysis between FC/DCEG S-101 1.1.0 & PC 1.0.2 | 2022-11-28 | 2023-01-06 | This includes the updating of rules as reqired but, if new symbology is required, a full creation-approval cycle must be added to the GANTT.
Upload S-101 PC 1.1.0 Draft to Github for peer review | 2023-02-20 | 2023-02-20
Complete submission of new portrayal change proposals (included in PC 1.1.0) to the GI Registry | 2022-10-31 | 2023-03-03
S-101 PC 1.1.0 Peer review process in Github | 2023-02-21 | 2023-03-13
Publish S-101 Portrayal Catalogue 1.1.0 in GI Registry | 2023-03-31 | 2023-03-31 | All new and S-57 remodellled features/attributes must be included in this version. ...
Publish S-101 Feature catalogue 1.1.0 in GI Registry | 2023-02-06 | 2023-03-31
Publish S-164 Version 1.0.0 | 2023-06-09 | 2023-06-09 | As per M-3 Resolution 2/2007 (as amended), the approval process for Edition 1.0.0 (Development Phase) involves: ...
Conduct a final 1.2.0 review cycle of the DPS and DCEG | 2023-09-20 | 2023-10-27
Submit to S-100WG8 for endorsement of completed 1.2.0 components (DPS & DCEG) | 2023-11-06 | 2023-11-14
Resolve comments from review and prepare final documents including Feature Catalogue 1.2.0 | 2023-10-30 | 2023-12-22 | DQWG consistency review follows in parallel
Prepare 1.2.0 Portrayal Catalogue, Validation Checks and Test Datasets | 2023-11-06 | 2024-03-11
Approval of S-98 version 1.2.0 by S-100WG | 2024-03-18 | 2024-04-14
Prepare DCEG and DPS 1.3.0. Submit association and association role names to GI Registry. | 2024-03-08 | 2024-03-22
Prepare a 1.3.0 Feature Catalogue | 2024-03-25 | 2024-04-19 | KOHA have indicated a delivery on the 5th of April. Will be followed by a review by a small group.
Conduct PT Review Cycle | 2024-03-08 | 2024-05-03 | Time will not allow us to do a separate review cycle in the project team. All documents will be publish as early as possible before S-101PT13 to allow the PT members to review de documents before the meeting.
Verify FC/DCEG 1.3.0 | 2024-04-19 | 2024-05-03
Prepare a 1.3.0 Portrayal Catalogue | 2024-03-22 | 2024-05-17
Prepare a 1.3.0 Validation Checks | 2024-03-22 | 2024-05-17
Prepare final documents for PT13 (1.4.0) | 2024-05-03 | 2024-05-17
Hold S-101PT13 | 2024-06-17 | 2024-06-19
Prepare final documents draft 2.0.0 | 2024-06-20 | 2024-07-05
Portrayal edit and make 2.0.0 | 2024-06-20 | 2024-07-05
Validation Checks edit and make 2.0.0 | 2024-06-20 | 2024-07-05
Send to S-100WG for approval | 2024-07-05 | 2024-07-05
DQWG review of S-101 ed.2.0.0 | 2024-07-05 | 2024-08-05 | In parallell with the approval process.
Endorsement of S-101 version 2.0.0 by S100WG | 2024-07-08 | 2024-08-16
Endorsement of S-101 version 2.0.0 by HSSC | 2024-08-19 | 2024-09-20 | As per M-3 Resolution 2/2007 (as amended), the approval process for Edition 2.0.0 (Opertaional version) involves
Endorsement of S-101 version 2.0.0 by HSSC | 2024-08-19 | 2024-09-20 | As per M-3 Resolution 2/2007 (as amended), the approval process for Edition 2.0.0 (Opertaional version) involves
Approval of S-101 version 2.0.0 by MS | 2024-09-23 | 2024-12-20
Test datasets (S-101 + other PS) for S-164 | 2024-10-01 | 2025-01-31
Finalising S-164 2.0.0 | 2024-10-01 | 2025-02-28
Finalising S-98 2.0.0 | 2024-10-01 | 2025-02-28
Endorsement of S-98 edition 2.0.0 by HSSC | 2025-03-03 | 2025-04-02 | As per M-3 Resolution 2/2007 (as amended), the approval process for Edition 2.0.0 (Opertaional version) involves
Endorsement of S-164 edition 2.0.0 by HSSC | 2025-05-01 | 2025-05-31
Approval of S-98 version 2.0.0 by MS | 2026-06-02 | 2025-08-31
Approval of S-164 version 2.0.0 by MS | 2025-06-02 | 2025-08-31
Publish S-98 & S-164 Version 2.0.0 (complete - Instructions and datasets) | 2025-09-01 | 2025-11-30
IEC 61174 Edition 5 to International Standard | 2025-09-01 | 2025-12-01
First type approved DF-ECDIS models | 2026-04-01 | 2026-09-30