**TWCWG WORK PLAN 2024-2025 \*\*\*DRAFT\*\*\***

# Objective

1. To monitor developments related to tidal and water level observation, analysis and prediction and other related information including vertical and horizontal datums;
2. To develop and maintain the relevant IHO standards, specifications and publications for which it is responsible in liaison with the relevant IHO bodies and non-IHO entities;
3. To develop standards for the delivery and presentation of navigationally relevant current information; and
4. To provide technical advice and coordination on matters related to tides, water levels, currents and vertical datum.

# Tasks

|  |  |
| --- | --- |
| A | Maintain the list of standard tidal constituents (IHO Task 2.8.4). |
| B | Compare the tidal predictions generated as a result of analysis of a common data set using different analysis software. |
| D | Develop, maintain and extend a Product Specification for Surface Currents in ECDIS (S-111) (IHO Task 2.3.4). |
| E | Develop, maintain and extend a Product specification for Water Level Information and Water Level Adjustment, WLA in ECDIS (S-104) (IHO Task 2.3.4). |
| E | Develop, maintain and extend a Product specification for Water Level Information (non-Water Level Adjustment, WLA) (S-10x) (IHO Task 2.3.4). |
| F | Liaise with S-100WG on water levels and currents themes relevant to ECDIS applications (IHO Task 2.3.5). |
| G | Liaise with industry experts on the development of Product Specifications for water levels and currents (IHO Task 2.5.1). |
| H | Prepare and maintain an inventory of water level gauges and current meters used by Member States and publish it on the IHO/TWCWG web site (IHO Task 2.8.5). |
| I | Review and maintain the Actual Tides and Currents On-Line links as published on the IHO TWCWG website (IHO Task 2.8.5). |
| J | Maintain and extend the relevant IHO standards, specifications and publications as required (IHO Tasks 2.8.4 and 2.1.8). |
| K | Conduct at least annual meetings of TWCWG and its sub-group(s) and project team(s) (IHO Tasks 2.1.2.7). |
| L | Develop and maintain material for course on Tides, Water Levels and Currents (IHO Task 3.3.9). |
| M | Review and maintain the List of Chart Datums (CD) in use by Member States (IHO Task 2.8.8). |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A.1 | Maintain the list of standard tidal constituents. | M |  | - | Permanent | O | -Chris Jones\* -All |  | Review current list of published tidal constituents. |
| B.1 | Compare the tidal and tidal current predictions generated as a result of analysis of a common data set using different analysis software. | M |  | - | Permanent | O | -Hilde Sande Borck \*-All |  | Select Common data set.Analyse using different software.Compute common set of predictions.Compare results. |
| B.2 | Support and Contribute to the International Association for the Physical Sciences of the Oceans (IAPSO) Best Practice Study group on Tidal Analysis. | M | As directed by IAPSO/TWCWG contact | 2023 | tbc | ~~P~~O | -Hilde Sande Borck\*-Andreas Boesch-Zarina Jayaswal-Phil MacAulay-Peter Stone-Andrew Matthews (IAPSO/TWCWG Contact) |  | Engage with the Best Practice Study Group, co-ordinating tasks on behalf of TWCWG.Report back to, and enlist support from, TWCWG. |
| D.1 | Develop and maintain a product specification for surface currents information in ECDIS (S-111). | H | Issue Edition 1.0.0 | 2013 | ~~2017~~~~2018~~2019 | ~~O~~ C | See report TWCWG4: List of involved and active members:-Greg Seroka\*-Thomas Hammarklint~~-Gwenaële Jan,~~ -Phil MacAuley (Gilles -Mercier & Maxime Carre)-Raphael Malyankar-Kwang nam HAN-Ronald Kuilman  | S-100S-98M-3 IHO Resolutions  | Joint project team is established as required.Liaise with S-100WG (see F.1).Liaise with industry experts (see G.1).Edition 1.2.0 (S-111) is aligned with S-100 Edition 5.0.0.Edition 2.0.0 (S-111) is aligned with S-100 Edition 5.2.0. |
| H | Issue Edition 1.2.0 | 2021 | 2023 | C |
| H | Issue Edition 2.0.0 | ~~2023~~2024 | ~~2024~~2025 | P |
| E.1 | Develop and maintain a product specification for water levels information in ECDIS (S-104). | H | ~~Develop draft~~~~Product Specifications (S-104) for water level information for surface navigation in~~~~S-100~~ | 2009 | ~~2017~~~~2018~~~~2019~~2020 | C | See report TWCWG4: List of involved and active members:-Zarina Jayaswal\*-Andreas Boesch-Thomas Hammarklint-Phil MacAuley (Gilles Mercier Maxime Carre)-Raphael Malyankar-Kwang nam HAN,-Greg Seroka | S-100S-98M-3 IHO Resolutions  | Joint project team is established as required.Liaise with S-100WG (see F.1) Liaise with industry experts (see G.1)Edition 1.1.0 (S-104) is aligned with S-100 Edition 5.0.0.Edition 2.0.0 (S-104) is aligned with S-100 Edition 5.2.0. |
| H | Issue Edition 1.0.0 | 2019 | 2021 | C |
| H | Issue Edition 1.1.0 | 2021 | 2023 | C |
| H | Issue Edition 2.0.0 | ~~2023~~2024 | ~~2024~~2025 | P |
| E.2 | Create, develop and maintain S-10x Product Specification (water levels information in ECDIS; extended scope). | M | Develop draftProduct Specification (S-10x) for water level information for surface navigation; extended scope. | 2024 | 2025 | P | -Phil MacAuley-Felipe Rodrigues Santana-Greg Seroka-Peter Stone -Chris Jones (Tom Cropper)-Raphael Malyankar-Fernando Oreiro-Zarina Jayaswal -Anni Jokiniemi-Hilde Sande Borck-Nicki Andreasen-Silvia Costa |  | ‘New’ Water level product specification to ‘re-insert’ the information removed from initial S-104. |
| F.1 | Liaise with S-100WG on water level and currentmatters relevant to ECDIS applications | H |  | - | Permanent | O | -Chris Jones-Zarina Jayaswal -Raphael Malyankar-Greg Seroka |  | Joint project team is established as required. |
| G.1 | Liaise with industry experts on the development of product specifications forwater levels and currents | H |  | - | Permanent | O | -All |  |  |
| H.1 | Maintain an inventory of water level gauges and current meters used by Member States and publish it on the IHO/TWCWG website. | H |  | - | Permanent | O | -All |  | Initial inventory from TWCWG members available on IHO web site. |
| I.1 | Review and maintain the Actual Tides and Currents On-Line links as published on the IHO/TWCWGWebsite. | L |  | - | Permanent | O | -All |  |  |
| J.1 | Maintain and extend the relevant IHO standards, specifications and publications. | M |  | - | Permanent | O | -Chris Jones\* -Ruth Farre-All | S-44C-13S-104S-111 |  |
| J.2 | Maintain IHO resolutions & Charting Specifications. | H |  | - | Permanent | O | -Ruth Farre\*-All | IHO Resolutions in M-3 | Review the relevant Resolutions and Charting Specifications annually |
| J.3 | Liaise and collaborate with HSWG to review and amend relevant sections of S-44. | L | Edition 6.3.0 | May 2024 | October 2025 | P | -Fernando Oreiro -Zarina Jayaswal)-Felipe Rodrigues Santana-Phil MacAulay-Jyrki Moronen-Chris Jones-Carl Kamerer -Hilde Sande Borck  | S-44C-13S-104S-111 | Propose amendments to improve water level and surface currents observation uncertainty standards within the relevant sections of S-44.Review S-44 in accordance with maintenance and publication schedule. |
| L.1 | Develop and maintain material for CB course on Tides and Tide gauges | H |  | - | Permanent | O | -Ruth Farre\*-Peter Stone-Zarina Jayaswal~~-Gwenaële Jan~~**~~-~~**Cesar Borba |  | Adapt currently available course material to create a course suitable for delivery in support of CBSC requests |
| M.1 | Review and maintain the List of Chart Datums (CD) in use by Member States | L |  | - | Permanent | O | -Chris Jones\*-Peter Stone -Sam Harper-All |  | Maintain a reference list of vertical Chart Datums in use globally by Hydrographic Offices relating to their national charting / tidal & water level products and services. |

 **Meetings (Task K)**

|  |  |  |
| --- | --- | --- |
| **Date** | **Location** | **Activity** |
| 25-29 April 2016 | Niterói, Brazil | TWCWG-1 |
| 8-12 May 2017 | Victoria, Canada | TWCWG-2 |
| 16-20 April 2018 | Viña del Mar, Chile | TWCWG-3 |
| 8-12 April 2019 | Busan, Republic of Korea | TWCWG-4 |
| 16-18 March 2021 | Remote VTC | TWCWG-5 |
| 5-7 April 2022 | Remote VTC | TWCWG-6 |
| 28 February – 2 March 2023 | Remote VTC | TWCWG-7 |
| 20-~~23~~ 22 February 2024 ~~(tbc)~~ | ~~Monaco, IHO~~ Remote VTC | TWCWG-8 |
| 19-22 November 2024 (tbc) | Monaco, IHO | TWCWG-9 |

Chair: Chris Jones (UK) Email: christopher.jones@ukho.gov.uk

Vice Chair: Ruth Farre (South Africa) Email: ruth.farre@sanavy.co.za; hydrosan@iafrica.com

Secretary: Sam Harper (IHO) Email: adso@iho.int