**Work Plan 2020-21 Summary of Progress**

(updated to 5 November 2021 following NCWG6, HSSC13 and subsequent activity)

**Tasks**

|  |  |
| --- | --- |
| A | Maintain and extend Publication S-4 'Chart Specifications of the IHO & Regulations of the IHO for INT Charts' (IHO Task 2.2.1) |
| B | Maintain and extend Publication S-11 Part A ‘Guidance for the Preparation and Maintenance of INT Chart schemes’ (IHO Task 2.2.2) |
| D | Development of new (and revised) symbology (IHO Task 2.2.1) |
| E | Maintenance of S-4 supplementary publications INT 1, 2 & 3 (IHO Task 2.2.1) |
| G | Conduct meetings of NCWG (IHO Task 2.1) |
| H | Provide technical assistance to other IHO working groups and support regarding the implementation of S-100 (IHO Task 2.3) |

**Work items**

\* Allowing for approval via HSSC (in accordance with Resolution 2/2007) before MS and publication.

| **No** | **Work item** | **Priority**H-highM-mediumL-low | **Next Milestone** | **Start****Date** | **End****Date** | **Status**P-PlannedO-OngoingC-Completed | **Contact Person(s)** | **Affected Pubs/Standard** | **Remarks** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A26 | Portrayal subWG | H | Agree protocol for seeking advice from NCWG | 2016 |  | O | Chair NCWG |  | HSSC7 Action 18NCWG2 Actions 5, 22, 30-32Attendance at NIPWG Visualization workshop May 2017. NCWG3 Action 15* Is this still required?
 |
| A28 | Future of S-4 | H | NCWG6 – discuss future of S-4 and agree work tasks | 2020 | 2022 | O | Chair NCWG | S-4 | NCWG3 Agenda 7.4: waiting on progress with A16 |
| E1 | Maintain official INT 1s |  | UK to take over English INT 1 from DE and publish new edition  |  |  | O | UK: Sam LerigoFR: S GuillouES: J. Bustamante | INT 1 | DE INT 1 edition 9 published August 2018ES INT 1 edition 6 published April 2018FR INT 1 edition 7 published in 2019UKHO have taken over responsibility for English INT 1 from DE and published edition 8 in 2020 |
| E9 | Develop new section V for INT1 for ‘data quality’ | M | Draft under consideration by INT1 subWG | 2014 | 2021 | O | Chair NCWGINT1 subWG | INT1 | CSPCWG10 Action 35NCWG3 Agenda 11.2: Transferred to UKNCWG4 – Action 4/18 ongoing |
| E10 | Symbol library | L | UK to confirm freedom to use UK's symbol set | 2016 |  | O | UK (N Rodwell)US (C Harmon) | S-4, INT1 | NCWG Actions 45, 46NCWG3 Agenda 3: Not required to progress at this time. |
| E11 | Develop baseline symbology to support automated chart production | H | NCWG6 – discus and agree work tasks | 2020 |  | P |  | INT1, S-4 | New proposal by NCWG at HSSC12SubWG established following NCWG 6 and first meeting scheduled 1 March 2021. |

**Meetings** (Task G)

|  |  |  |
| --- | --- | --- |
| **Date**  | **Location** | **Activity** |
| 5-8 November 2019 | Stockholm, Sweden | NCWG5 |
| 3-4 November 2020 | VTC | NCWG6 |
| 9-12 November 2021 | Cadiz, Spain tbc | NCWG7 |

Chairman: Mikko Hovi (FI) Email: mikko.hovi@traficom.fi
Vice Chairman: Nick Rodwell (UK) Email: Nick.Rodwell@UKHO.gov.uk
Secretary: Edward Hands (NO) Email: Edward.Hands@kartverket.no