## Sheet1
S-101 Change Tracker post 2.0.0
Impact
Serial | Paper/Issue | Meeting | Description | Status | Considered by ENCWG | S-57/S-52 Update | Considered by NCWG | S-4 Update | DPS | Registry | DCEG | FC | PC | VCs | S-164 | Issue
1 | Ongoing change | N/A | Update DSID - PRSP and PRED subfields (Annex B) | Applied. To be confirmed when Edition number finalised. | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | ?
2 | Ongoing change | N/A | Update S-101 version and version date | Applied. To be confirmed when Edition number finalised. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | ?
3 | S-101PT14-6.4 | PT14 | Changes to submarine cable symbology | Issues open to progress | ENCWG9 | S-52 5.0/YYMMDD | Seek confirmation of no change to S-4. | N/A | N | Y | N | N | Y | ? | Y | https://github.com/S-101-Portrayal-subWG/Working-Documents/issues/184
4 | S-101PT14-6.4 | PT14 | Changes to cable area symbology | Issues open to progress | ENCWG9 |  | Seek confirmation of no change to S-4. | N/A | N | Y | N | N | Y | ? | Y | Changes to Cable Area symbology (S-52 5.0.0) · Issue #183 · S-101-Portrayal-subWG/Working-Documents
5 | S-101PT14-6.4 | PT14 | Changes to overhead cable symbology | Issues open to progress | ENCWG9 |  | Seek confirmation of no change to S-4. | N/A | N | Y | N | N | Y | ? | Y
6 | 193 | PT15 | Add Silo Tank to association for Air Obstruction Light | Agreed at PT15 Applied to draft | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | https://github.com/iho-ohi/S-101-Documentation-and-FC/issues/193
8 | S-101PT15-6.2 | PT15 | Text Pattern and Precision | To be discussed | N/A | N/A | N/A | N/A | N | Y | N | Y | N | N | N
9 | S-101PT15-6.1 | PT15 | Uncertainty in S-101 | To be discussed | [5 empty] | ? | Y
10 | 195 | PT15 | Remove of unit Knots from simple attribute speed limit. | Agreed at PT15 Applied to draft Registry action needed | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | Attribute Speed Limit should not have UOM Knots in Feature Catalogue · Issue #195 · iho-ohi/S-101-Documentation-and-FC
11 | 194 | PT15 | RadarStation could not be related to landmark | Agreed at PT15 Applied to draft | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | RadarStation could not be related to landmark (association) · Issue #194 · iho-ohi/S-101-Documentation-and-FC
12 | Email correspondence with Peter Duguid 05/03/25 | DCEG SG | Value range closure and guidance for the population of the Meta attribute update number does not reflect that an Update Information feature(s) may be included in a New Edition dataset (update number = 0). | Draft changes made to DCEG. For consideration of DCEG Sub-Group. Change made to GI Registry. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | ?
13 | Email correspondence with Frank Hippman 12/03/25 | DCEG SG | Add Mooring Buoy [and Obstruction] to list of structures that have not been established specifically as an aid to navigation | Draft changes made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N
14 | Email correspondence with Frank Hippman 12/03/25 | DCEG SG | Add new guidance to encode buoys that have primary purpse as a mooring buoy using the Mooring Buoy feature; and use attribute colour to encode purpose if also used as a navigational aid | Draft changes made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N
15 | 61 | PT15 | Add note stating that Aliases are to be retained in the S-101 FC until the end of the dual-fuel implementation period. | Agreed at PT15 Applied to draft | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | N
16 | 179 | PT15 | Amend Comment entry for DSID - DSEC sub-field. | Draft changes made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | Y | N | N | N | N | ? | N
17 | 176 | PT15 | Amend Comment entry for CRSH - CRNM and VDAT - DTNM sub-fields. Amend Value entry for VDAT - DTID sub-field. | Draft changes made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | Y | N | N | N | N | ? | N
18 | 167 | PT15 | Amend Comment entry for COCC - NCOR, SECC - NSEG and CCOC - NCCO sub-fields. | Draft changes made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | Y | N | N | N | N | ? | N
19 | Telecon with Richard Fowle 17/03/24. | DCEG SG | Correct encoding guidance for seabed material extraction areas from categoryOfProductionArea = 13 (seabed material extraction area), which does not exist. | Draft change made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | ?
20 | 466 | Por SG | Consistency with S-52 Ed 4.0(.4). Refer to email correspondence 26-27/03/25. | Issue open to progress. | N/A | S-52 PL Ed 4.0(.4) | N/A | N/A | N | N | N | N | Y | N | ?
21 | 85 | PT15 | Improved guidance for encoding the TidalStreamPanelData feature. | Draft change made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N
22 | Email from Christina Ulrich 17/04/25. | DCEG SG | Clarify that the value to be populated for “system” attribute default clearance depth on features that are within or partly within a DepthArea or DredgedArea feature having an unknown value for the attribute depthRangeMinimumValue follows the same rule as for features that are within or partly within an UnsurveyedArea feature. | Draft change made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N
23 | Email from Gert Morlion 28/04/28. | DCEG SG | Amend the term "None" for identifying no geometry as an allowable geometric primitive for S-101 features to "No Geometry" to be consistent with S-100. | Draft change made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N