## S-101PT Actions
S-101PT Actions @ 20240508
No. | Topic | Detail | Lead | Status | Remarks | Chair Comments (for S-101PT11); NIWC Comments (yellow)
S-101PT5-13 | Datum Issues | A small group, led by NIWC, to discuss the issues raised in the Paper S-101PT5-10. Possible feedback required to TSM8. | NIWC (Lead) | Ongoing | Recommendation 1 & 2: We need a path to close these out. Recommend address via update to PS. 1) S-101 ISO-8211 ordering of VDAT records (S-101PT Chair: Propose new action to make proposal re VDAT needed.) 2) S-101 ISO-8211 encoding of AXTY (axis orientation) Recommendations 3 and 4 are withdrawn Recommendation 5 (modify model of sounding/verticalDatum): Recommend refer to DCEG SG S-101PT7: OEMs to please look at Portrayal Issues in the GitHub and provide input to these discussions. See also Paper S-101PT10-07.9 and Action S-101PT10-25. | 1) Can be withdrawn if recommendation two is accepted. The type of datum can determined from the axis orientation. 2) PS 1.1.0 B-5.1.11 shows "12" as only allowed value of AXTY. "11" should also be allowed. note: PS 1.1.0 clause 5.3 describes vertical CRS for soundings. There is no section describing vertical CRS for VerticalDatumOfData. 5) Can copy the relevant parts of the paper into a new issue. --- We also note that the default CRS's are unavailable to the portrayal or any other scripting function because they are not available via the GFM. Ideally, the default datums would be available via one or more dataset features.
S-101PT6-10 | Validation Update | Incorporate process to ensure alignment of all draft Validation Checks and test datasets to single versions of related publications (S-100/S-101/S-101DCEG) in the overall Validation Checks development process. | KÖ | Ongoing | 02/12/21: Chair: Consideration will be reflected in workplan activity during 2022. Expected completion mid 2022. 19/07/22: Action transferred to Klas (S-101PT10).
S-101PT9-13 | ENC Scales and Dataset Load/Unload Sub-Group Update | Report the decision to prohibit overlapping scale ranges for ENC coverages to the WENDWG (WEND100 and ENC scheming workspace) and possibly NCWG (S-11 Part A) for information. | Chair | Ongoing | For WENDWG14 (2024) and NCWG9 (2023). 30/08/23 (Chair): Chair to raise at NCWG 9 and thence WEND noting revision of S-11 Part A.
S-101PT10-06 | Portrayal Sub-Group Update | Discuss the possibility of applying a bulk update of all registered symbols in the GI Registry to conform to the S-100 Edition 5.1.0 Portrayal Schema and report to the S-101PT. | IHO Sec, UNH, KHOA | In Progress | For S-101PT11. 23/08/23: GI Registry Development Team informed that a bulk update is not possible. UNH (Christos) working on a converter tool in cooperation with KHOA to convert Tiny (or other) SVG to the required S-100 SVG format. On completion, KHOA will perform the conversion of all symbols directly within the Portrayal Register database. 06/02/24: To be discussed in conjunction with paper S-101PT12-07.2.
S-101PT10-07 | Portrayal Sub-Group Update | Review the gaps in the content of the various Item Types in the IHO GI Registry, Portrayal Register and submit proposals to close these gaps as required. | Portrayal Sub-Group | In Progress | For S-101PT11. 07/02/24 (SG Lead): Not started. Lack of resources.
S-101PT10-11 | Data Quality Portrayal in S-101 | Continue data quality symbol development for (traditional) ECDIS dual-fuel display for S-101 Edition 1.2.0. | UNH (Lead), NIWC | In Progress | For S-101PT11.
S-101PT11-03 | S-101PT Actions | Liaise with the ENCWG Task Group established to address S-57/S-101 inconsistencies (Action S-101PT4-07 and ENCWG8-05.2). | Chair, IHO Sec | In progress | For S-101PT12.
S-101PT11-04 | S-101PT Actions | Develop changes to S-101 to address issues related to the triggering of false alarms in ECDIS, based on feedback from S-101PT Chair/IHO Sec (Action S-101PT4-07). | Portrayal SG | Pending | For S-101PT13.
S-101PT11-05 | S-101PT Actions | Address invalid geometries issue with US (NOAA) and report to S-101PT (Action S-101PT6-01). | Chair | Ongoing | For S-101PT13.
S-101PT11-06 | S-101PT Actions | Develop guidelines on using S-101 scale ranges and scaleMinimum (Action S-101PT8-34). | ENC Scales and Dataset Load/Unload SG | Ongoing | For S-101PT13.
S-101PT11-07 | S-101PT Actions | Investigate the depth resolutions for regulatory depths for consistency and report to S-101PT (Action S-101PT10-09). | IHO Sec | Ongoing | For S-101PT13. Note Paper S-101PT12-06.22 that may supersede this action.
S-101PT11-15 | Portrayal Sub-Group Update | Develop ECDIS Chart 1 equivalent S-101 test datasets. | Test Dataset SG | Ongoing | For S-101PT13. 07/02/24 (Chair): IIC to report on progress to S-101PT12 (IIC: Expected to be completed before TSM10).
S-101PT11-20 | Test Dataset Sub-Group Update | Progress development and updating of the Test Datasets to S-101 Edition 1.2.0 once the Feature Catalogue is available. | Chair (Lead), IC-ENC, PRIMAR, Vice-Chair | In progress | For S-101PT12. 07/02/24 (Chair): Delayed by the availability of the Feature Catalogue and Production Software see TDS SG report to S-101Pt12.
S-101PT11-23 | Scales Sub-Group Update | Develop more extensive fundamental guidance (figures/diagrams) to be included as a new Annex to S-101. | ENC Scales and Dataset Load/Unload SG | Ongoing | S-101 Edition 2.0.0
S-101PT11-31 | Allowable Differences Between S-52 and S-101 Display and Functionality in ECDIS | Develop a list of new and changed symbology as a reference list. | Portrayal SG | Ongoing | For S-101PT12. 07/02/24 (SG Lead): Early days. Expect first draft in June (S101PT13). S-101PT12: Note also S-101 Portrayal subWG GitHub Issue #115.
S-101PT11-46 | NIPWG Liaison | S-101PT Members encouraged to implement and test Edition 1.0.0 of S-128 which is to be published later this year. | S-101PT | Ongoing | For S-101PT13.
S-101PT11-52 | Towards S-101 Edition 2.0.0 | Enquire to S-101 ENC production software manufacturers on the time frame between publication of a version of the S-101 Feature Catalogue and the upgrade of their systems. | Chair | Ongoing | For S-101PT13. 07/02/24 (Chair): Information has been gathered on this. Suggest this is completed clearly it is not possible to define a fixed timeframe as there are many variables but we have information that will assist planning.
S-101PT12-01 | S-101PT11 Report (S-101PT12-03) | Complete the Minutes of the S-101PT 11 meeting for submission to S-101PT13. | IHO Sec |  | For S-101PT13.
S-101PT12-02 | S-101PT Actions (S-101PT12-04) | Liaise with the ENCWG, small group established to look at S-52 impacts of S-100 ECDIS. (Action S-101PT10-03). | Chair | In progress | For S-101PT13
S-101PT12-03 | S-101PT Actions (S-101PT12-04) | Discuss the possibility of initiating a new project to implement and test (user feedback) the new options for portrayal of bathymetric data quality in ECDIS. | Chair |  | For S-101PT13
S-101PT12-04 | S-101PT Actions (S-101PT12-04) | Place a note on the S-100 Resources web page requesting anyone that has test data that may be made publicly available to supply to the IHO Secretariat. | IHO Sec | Completed | For March 2024
S-101PT12-05 | DCEG Sub-Group Update (S-101PT12-05.1) | Prepare a presentation summarising the S-101 Documentation and FC GitHub open issues that impact on the S-101 Feature Catalogue for adjudication by the S-101PT. | IHO Sec | Completed | For March 2024. Posted as Paper S-101PT12 -5.1.1.
S-101PT12-06 | DCEG Sub-Group Update (S-101PT12-05.1) | Compile a list of S-101 concept names that are in conflict with IHO Hydrographic Dictionary terms and definitions for consideration of the S-101PT. | IHO Sec |  | For March 2024
S-101PT12-07 | DCEG Sub-Group Update (S-101PT12-05.1) | aAdd the attribute reportedDate as an allowable attribute for the feature LandArea. | IHO Sec | Completed | S-101 Edition 1.3.0 draft
S-101PT12-08 | DCEG Sub-Group Update (S-101PT12-05.1) | Add URN as an allowable attribute type for S-101; and amend attribute type for interoperabilityIdentifier to URN. | IHO Sec | Completed | S-101 Edition 1.3.0 draft
S-101PT12-09 | DCEG Sub-Group Update (S-101PT12-05.1.1) | Apply changes in line with the recommendations in Paper S-101PT12-05.1.1 as agreed by the PT; and close the corresponding GitHub Issues as required. | IHO Sec | Completed | S-101 Edition 1.3.0 draft
S-101PT12-10 | DCEG Sub-Group Update (S-101PT12-05.1.1) | Conduct further investigation into the application and guidance for the attribute flareBearing and apply amendments to the DCEG as required. | IHO Sec | Completed | S-101 Edition 1.3.0 draft
S-101PT12-11 | Portrayal Sub-Group Update (S-101PT12-05.2) | Provide inputs to all open S-101 Portrayal SubWG and S-101 Portrayal Catalogue GitHub Issues, including contribution of test data based on S-101 Edition 1.2.0 to the Test Dataset Sub-Group if possible. | S-101PT Members | In progress | For S-101PT13
S-101PT12-12 | Portrayal Sub-Group Update (S-101PT12-05.2) | Raise the possibility of introducing more meaningful values for the xmlID unique identifier with the GI Registry development team. | IHO Sec | In progress | For March 2024
S-101PT12-13 | S-101 Validation Sub-Group Update (S-101PT12-05.4) | Provide inputs to S-101 Validation GitHub Issue #28. | S-101PT Members |  | For S-101PT13
S-101PT12-14 | S-101 Validation Sub-Group Update (S-101PT12-05.4) | Provide feedback on the Validation Checks currently posted. | Member States, RENCs and OEMs |  | For S-101PT13
S-101PT12-15 | Scales Sub-Group Update (S-101PT12-05.5) | Test the algorithms for dataset loading and portrayal (rendering) and provide feedback to the Scales SG Lead. | S-101PT Members |  | For S-101PT13
S-101PT12-16 | QoBD Temporal Variation (S-101PT12-06.2) | Apply changes to the DCEG as proposed in Paper S-101PT12-06.2 in line with S-101PT12 decisions. | IHO Sec | Completed | S-101 Edition 1.3.0 draft
S-101PT12-17 | QoBD Temporal Variation (S-101PT12-06.2) | Add a new S-101 Documentation and FC GitHub Issue for further discussion on the issue related to grouping of soundings and bathymetric data quality. | IHO Sec | Completed | For March 2024
S-101PT12-18 | Additional Value of Vertical Datum (S-101PT12-06.4) | Apply changes throughout the DCEG for addition of Low Water Datum as an allowable enumerate value for attribute verticalDatum, with appropriate guidance. | IHO Sec | Completed | S-101 Edition 1.3.0 draft
S-101PT12-19 | Multiple Languages in S-101 (S-101PT12-06.5) | Take the recommendations included in Paper S-101PT12-06.5 forward to the next S-100 TSM for inclusion in the next Edition of S-98. | Chair | Completed | For S-100-TSM10
S-101PT12-20 | Use and Modelling of the Update Information Feature (S-101PT12-06.6) | Apply changes to the DCEG as recommended in Paper S-101PT12-06.6, including enhanced guidance in DCEG Section 31. | IHO Sec, in consultation with AU | In progress | Email to AU, Caris and Chair 09 March (draft changes)
S-101PT12-21 | Use and Modelling of the Update Information Feature (S-101PT12-06.6) | Consider conducting a workshop to further discuss UpdateInformation implementation and discuss testing results. | Chair, in consultation with AU | Completed | For S-101PT13. Correspondence 08/05/24: Meeting to be held early June 2024.
S-101PT12-22 | Use and Modelling of the Update Information Feature (S-101PT12-06.6) | Discuss the possibility of full implementation of UpdateInformation in S-100 ECDIS for S-101 ENCs to replace existing S-57/S-52 ECDIS functionality. | S-101PT | In progress | For S-101PT13
S-101PT12-23 | New Symbol for Renewable Energy Devices (S-101PT12-06.7) | Propose an amendment to the term Current Farm to the IHO GI Registry and apply corresponding change to the S-101 DCEG. | IHO Sec | Completed | S-101 Edition 1.3.0 draft
S-101PT12-24 | Referencing Other Vertical Datums (S-101PT12-06.8) | Add a new S-101 Documentation and FC GitHub Issue for further discussion on the implementation of a new complex attribute verticalReferenceFrame. | IHO Sec | Completed | For March 2024. Issue #137.
S-101PT12-25 | Structures Over Navigable Water (S-101PT12-06.9) | Include a new feature StructureOverNavigableWater in S-101 as proposed in Paper S-101PT12-06.9. | IHO Sec | Completed | S-101 Edition 1.3.0 draft
S-101PT12-26 | Structures Over Navigable Water (S-101PT12-06.9) | Inform the S-131PT of the feature model for StructureOverNavigableWater and provide feedback to IHO Sec (new attribute name and enumerate values). | Raphael Malyankar |  | For March 2024
S-101PT12-27 | Structures Over Navigable Water (S-101PT12-06.9) | Inform the IEHG of the feature model for StructureOverNavigableWater and provide feedback to IHO Sec (definitions). | Gaël Billet | Completed | For March 2024
S-101PT12-28 | Association Roles in S-101 (S-101PT12-06.10) | Convene a meeting of the S-101 Associations Sub-Group to move forward with the recommendations included in Papers S-101PT12-06.10 and 10A. | IHO Sec | Completed | March 2024 (S-101 Edition 1.3.0 draft)
S-101PT12-29 | Association Roles in S-101 (S-101PT12-06.10) | Consider the recommendations in paper S-101PT12-06.10A and supply any suggestions on role names/conventions to IHO Sec. | S-101PT Members | Time Expired | For March 2024
S-101PT12-30 | Rendering Algorithm (S-101PT12-06.11) | Include the proposed rendering algorithm as an informative Annex in S-101. | IHO Sec | Completed | S-101 Edition 1.3.0 draft
S-101PT12-31 | Rendering Algorithm (S-101PT12-06.11) | Collate test results and report to S-101PT. | S-101 Scales and Dataset Load/Unload Sub-Group Lead |  | For S-101PT13
S-101PT12-32 | Attribute Formats and Constraints (S-101PT12-06.12) | Apply changes to the S-101 DCEG in line with the recommendations in Paper S-101PT12-06.12 and decisions of the meeting. | IHO Sec | Completed | Amendments applied for S-101 Edition 1.3.0 draft
S-101PT12-33 | Attribute Formats and Constraints (S-101PT12-06.12) | Raise Recommendation C in paper S-101PT12-06.12 and a request to provide further detail on implementing Units of measure in the Registry and FC to the S-100WG. | Chair | In progress | For S-100WG9
S-101PT12-34 | Quality of Horizontal Measurement (S-101PT12-06.13) | Apply changes to S-101 in accordance with recommendation B in Paper S-101PT12-06.13. | IHO Sec | Completed | S-101 Edition 1.3.0 draft. Note however that following further discussion and feedback from NIPWG option A in the Paper has been applied.
S-101PT12-35 | Quality of Horizontal Measurement (S-101PT12-06.13) | Discuss revising the definition for positionApproximate in slower time. | DCEG Sub-Group |  | For S-101 Edition 2.0.0
S-101PT12-36 | Submarine Danger Area (S-101PT12-06.14) | Consider submitting a proposal for the NCWG on the inclusion of specifications for including submarine danger information on charts in S-4. | UK |  | For NCWG10
S-101PT12-37 | Strategy to align S-44 and S-101 Standards (S-101PT12-06.15) | Raise the issues raised in Paper S-101PT12-06.15 up to the NCWG. | US |  | For NCWG10
S-101PT12-38 | Strategy to align S-44 and S-101 Standards (S-101PT12-06.15) | Discuss with the Chair of HSWG to open a dialogue with the DQWG via the HSWG report to DGWG19. | Chair |  | For DQWG19
S-101PT12-39 | Identification in S-101 for Equivalent S-57 ENCs (S-101PT12-06.16) | Produce a joint RENC Paper for the provision of ENC equivalency information from Data Producer to RENC for consideration of the S-101PT. | IC-ENC and Primar |  | For S-101PT13
S-101PT12-40 | Identification in S-101 for Equivalent S-57 ENCs (S-101PT12-06.16) | Report discussions on ENC equivalency to the S-100 TSM for the possible impacts of this on the end-user; and develop a follow-up proposal on how this may be included in S-98 for OEM implementation. | IIC | Completed | For S-100-TSM10
S-101PT12-41 | Update to Revision Status S-57 ENCs (S-101PT12-06.17) | Apply changes to S-101 Main document in accordance with the recommendation in Paper S-101PT12-06.17. | IHO Sec | Completed | S-101 Edition 1.3.0 draft
S-101PT12-42 | Attribute Suppression in S-101 Edition 2.0.0 (S-101PT12-06.18) | Apply changes to the S-101 Main document in accordance with the recommendation in Paper S-101PT12-06.18 as approved by the S-101PT. | IHO Sec | Completed | S-101 Edition 1.3.0 draft
S-101PT12-43 | Attribute Suppression in S-101 Edition 2.0.0 (S-101PT12-06.18) | Apply changes to the S-101 FC (once an S-100 Edition 5.2.0 FC schema is available) to incorporate attributeVisibility in accordance with the recommendation in Paper S-101PT12-06.18 as approved by the S-101PT. | KHOA | In progress | S-101 Edition 1.3.0 draft
S-101PT12-44 | Attribute Values for “Day of the Week” (S-101PT12-06.19) | Discuss revising the definitions of enumerate values for attribute dayOfTheWeek in slower time. | DCEG Sub-Group, in consultation with NIPWG | Completed | For S-101 Edition 2.0.0. Applied as per discussions in S-101 Documentation and FC Issue #132
S-101PT12-45 | “File-Less” Resources Management (Including Cancellations) for S-101 (S-101PT12-06.20) | Apply changes to S-101 Main document in accordance with the recommendation in Paper S-101PT12-06.20. | IHO Sec | Completed | S-101 Edition 1.3.0 draft
S-101PT12-46 | Support File Management (S-101PT12-06.21) | Develop a proposal, including redline changes, related to S-101 support file management. | Primar |  | For S-101PT13
S-101PT12-47 | Support File Management (S-101PT12-06.21) | Provide feedback and input to Primar in support of the development of the Primar proposal. | IIC, NIWC, Portolan Sciences, IC-ENC, NGA |  | For S-101PT13
S-101PT12-48 | Precision of Attribute valueOfSounding (S-101PT12-06.22) | Apply changes to S-101 in accordance with the recommendation in Paper S-101PT12-06.22. | IHO Sec | Completed | S-101 Edition 1.3.0 draft
S-101PT12-49 | Optimum Display Scale (S-101PT12-06.23) | Include the rendering algorithm as included in S101 Documentation and FC GitHub Issue #71 in the S-101 Main document. | IHO Sec | Completed | S-101 Edition 1.3.0 draft. NOTE: This algorithm has been augmented by a second algorithm and the addition of a new attribute displayPriority for feature DataCoverage as agreed at S-100 TSM-10.
S-101PT12-50 | Optimum Display Scale (S-101PT12-06.23) | Remove the restriction on the allowable values that can be populated for the attribute maximumDisplayScale from S-101. | IHO Sec | Completed | S-101 Edition 1.3.0 draft
S-101PT12-51 | Optimum Display Scale (S-101PT12-06.23) | Develop enhanced encoding guidance on the population of the various scales in S-101. | IHO Sec, in consultation with FR | Completed | S-101 Edition 1.3.0 draft
S-101PT12-52 | Tiny to IHO SVG Translator and CSS Inline Styling Removal (S-101PT12-07.2) | Provide the converted S-101 symbol set to NIWC; and the Tiny-to-IHO SVG Translator and CSS Inline Style Removal tools to the IHO Sec. NIWC to include the converted symbols in the next version of the S-101 Portrayal Catalogue. | UNH (Lead), NIWC |  | S-101 Edition 1.3.0 draft
S-101PT12-53 | Tiny to IHO SVG Translator and CSS Inline Styling Removal (S-101PT12-07.2) | Raise the investigation of a method for including the revised symbols in the Portrayal Register and the conversion tools in the S-100 Toolkit of the GI Registry with the ICE-PT. | IHO Sec | In progress | For May 2024. Refer to S-101 Letter 04/2024
S-101PT12-54 | Tiny to IHO SVG Translator and CSS Inline Styling Removal (S-101PT12-07.2) | Open a new Issue in the Infrastructure GitHub related to the use of the conversion tools. | IHO Sec | Overtaken by Events | For April 2024. 10/04/24: S-101 Portrayal Sub-Group discussions 09/04/24: Suggestion to resolve by bulk conversion of all symbols in the Portrayal Register to be raised to the HSSC.
S-101PT12-55 | Tiny to IHO SVG Translator and CSS Inline Styling Removal (S-101PT12-07.2) | Notify other Groups having symbols registered in the Portrayal Register of the existence of the new Tiny-to-IHO SVG Translator and CSS Inline Style Removal tools. | IHO Sec |  | For April 2024
S-101PT12-56 | Towards S-101 Edition 2.0.0 (S-101PT12-08.1) | Report any known timeframe for an S-100 5.2.0 capable Feature Catalogue Builder. | KHOA | Completed | Available 2nd week in March 2024

## Completed_Closed
Source | Action | Detail | Lead | Status | Remarks
S-101PT4-01 | Finish the S-57 to S-101 Conversion Report | Incorporate comments received. Compile a list of edge cases from the UOC/DCEG part of the study. Release the test dataset containing a set of the edge cases for testing converter technology. | Jonathan Pritchard | CLOSED | Overtaken by events - this work is now being done by the S-57 to S-101 Conversion Sub-Group (ENCWG).
S-101PT4-02 | S-101 ENC Portrayal | Determine all portrayal gaps, Design portrayal on gapped features/types Sub-WG to work on refining the current symbols, line styles, sounding structure/portrayal, colours/palettes etc… . User feedback is to be sought as part of the work. | US/NOAA NCWG Chair [Members: IHO Sec, IALA, Carnival, Germany, Teledyne-Caris, IIC, NZ, KHOA, US (NOAA), US (NGA), Netherlands (DGWG Chair) | Complete
S-101PT4-03 | Update S-101 to final IHO GI Registry | Update content of S-101 for any changes based on IHO GI Registry deconfliction work | Jeff Wootton | Complete - all draft S-101 Edition 1.1.0 items aligned to the Registry.
S-101PT4-04 | Validation Checks | Denmark and IHO Sec to investigate incorporating the S-100 product validation checks into a database and developing a GUI interface. | Bruno Cardoso (DK) Tony Pharaoh (IHO Sec.) | CLOSED | Task OBE checks now fall within Validation Check Sub Group. New action to be taken. Agenda item 4.4 refers.
S-101PT4-05 | S-57 to S-101 Convertor | IHO Sec to include entries in the S-57 to S-101 conversion spreadsheet for new items included in S-101 Edition 1.0.0. | Jeff Wootton | Completed
S-101PT4-06 | NCWG activities affecting S-101 development | Draft amendments to the S-101 DCEG to make provision of encoding different colours of floodlighting. | JW | Completed | For S-101PT11. Refer to S-101 Documentation and FC Github Issue #78.
S-101PT4-07 | NCWG activities affecting S-101 development | Consider how to reduce the triggering of “false” alarms in ECDIS through consistent encoding practices. This should be documented in the S-101 DCEG. | Chair/IHO Sec | Closed | S-101 Catch-Up March 2021: Action to be transferred to the S-101 Roadmap (Chair). S-101PT7: Report back to S-101PT8. Close - Refer to new Actions S-101PT11-03 and S-101PT11-04. | Consider this lower priority and something that needs to be expolored via Testbeds.
S-101PT4-08 | S-57 to S-101 Portrayal Gap Analysis | Provide the spreadsheet identifying the new S-101 data modelling (refer action for Agenda item 4.4) to the NCWG Chair for consideration of the NCWG of new symbology requirements at its next meeting. | Jeff Wootton | Completed (August 2019)
S-101PT4-09 | Offshore Solar Farms | Netherlands to draft a definition for “solar farm” and submit to the Registry Manager (for registration). Registry Manager to include the new item in the DCEG. | AM/Jeff Wootton | Completed
S-101PT4-10 | DCEG Changes for S-101 Edition 2.0.0 | Continue application of draft changes to the S-101 DCEG in line with the changes approved by the S-101PT4 meeting and changes to the FCD Register. For further review at S-101PT5. | Jeff Wootton | Completed
S-101PT4-11 | DCEG Changes for S-101 Edition 2.0.0 | Discuss additional encoding guidance for the population of the depthRangeMinimum attribute for isolated shoal depth areas. | JW/AS/MH/RF | Completed | Refer to outcomes of paper presented to ENCWG Catch-Up meeting (February 2021). Amendments applied to DCEG Ed. 1.0.1 iaw changes to UOC approved at this meeting.
S-101PT4-12 | Proposal of Alternate Options for Display Scale | Propose to the S-100WG Chair to include an item on loading strategy to be discussed at the next Test Strategy meeting. | Megan Bartlett (US) | Completed
S-101PT4-13 | Quality of Horizontal Measurement | Submit paper 5.4 identifying inconsistencies (with definitions) to the next DQWG. | Christian Mouden (FR) | Completed | See action S-101PT5-01.
S-101PT4-14 | Sector Extension Portrayal Attribute | Improve the wording describing sector light extension as described in paper 5.5. | NIWC/JW | Completed | Recommend transfer to DCEG SG, noting that this action is distinct from the associated discussion taking place within the Portrayal Sub-Group (GitHub issue #3). S-101PT7: JW and DG to discuss further offline. 07/06/21: Refer to S-101 Documentation and FC GitHub #5. 20/08/21: Changes applied iaw Paper S-101PT4-05.05.
S-101PT4-15 | Sector Extension Portrayal Attribute | Conditional Symbology Procedure needs to be developed for item 2 in paper 5.5. | HA/HP/JW | Completed | S-101PT7: JW and HA to discuss further offline. Needs to be taken in association with Action S-101PT4-14. 02/02/21: Attribute type in DCEG amended to Boolean. To be approved by S-101PT and GI Registry updated.
S-100TSM7 | Visualization of Quality of Bathymetric Data | What extent does DQWG findings reflect in S-101? - Email Rogier and Yong | S-101PT | Completed | See action S-101PT5-02.
S-100TSM7 | Alerts and Indications | S-52 A&I needs to be captured in S-101 | US/NIWC | CLOSED | This is a Policy issue. There is no requirement for A&I in S-101, but there is a requirement in S-52.
S-100TSM7 | Alerts and Indications | Need to define what those mappings are (not all S-52 in S-101 and vice versa) | US/NIWC | CLOSED | Need to implement S-101 A&I in the PC using S-52 as guidance since there is nothing to guide in S-101. We are doing / have done the technical issue by adding A&I to S-101 PC.
S-100TSM7 | Alerts and Indications | Sumbit full proposal to S-100WG5 | US/NIWC | Completed
S-101PT5-01 | Quality of Horizontal Measurement | Develop proposal for quality of horizontal measurement based on S-101PT4-5.4 discussion. | CM | Completed | Refer to paper S-101PT6-14. Approved at S-101PT6 and decisions incorporated in DCEG Edition 1.0.1.
S-101PT5-02 | Visualization of Quality of Bathymetric Data | Develop proposal for S-101PT consideration on possible amendments to S-101 modelling of the Quality of Bathymetric Data feature based on the outcome of the DQWG investigation of improved portrayal of this information in ECDIS (for TSM8). | JW | Completed | Refer to paper S-101PT6-12. Approved at S-101PT6 and decisions incorporated in DCEG Edition 1.0.1. Note however that further work will be required in portrayal.
S-101PT5-03 | Visualization of Quality of Bathymetric Data | Consider the implementation of DQWG recommendations on improved portrayal of Quality of Bathymetric Data information in ECDIS (for S-101PT6). | S-101 Portrayal Sub-Group | Completed | SG Lead: Recomend close - Refer to actions Port-SG 01, 02 and 03.
S-101PT5-04 | Changes Intoduced in S-101 Edition 1.1.0 DCEG | PT members interested in participating in the S-101 DCEG Sub-Group to notify JW by email (jeff.wootton@iho.int) at the earliest opportunity. | S-101PT | Completed
S-101PT5-05 | Changes Intoduced in S-101 Edition 1.1.0 DCEG | Redline version of the S-101 DCEG to be sent to S-101 DCEG Sub-Group members for review (before end of September 2020). | JW | Completed | Email to Sub-Group 28/10/20.
S-101PT5-06 | Changes Intoduced in S-101 Edition 1.1.0 DCEG | The definition as to what constitutes and “editorial” change to the S-101 DCEG is to be determined, in consultation with the S-101PT Executive (September 2020). | JW/Chair/Vice-Chair/YB | Completed | Email correspondence with S-101PT Executive 05-07/10/20.
S-101PT5-07 | Feature Catalogue | KHOA, Portolan Sciences (and any other interested parties) to review changes to the FC to ensure validitiy with S-100 FC schemas (As new versions of the FC are created). | KHOA/RM/HA/YB/NIWC | Completed | Email from Izzy 21/09/20. Note however that this action is intended to be ongoing. FC draft Ed 1.0.1 circulated to small group 21/04/21. FC Edition 1.0.1 posted July 2021. Potential new action to define process document for FC creation and verification linked to ISO 9001 activity.
S-101PT5-08 | Portrayal | PT members interested in participating in the S-101 Portrayal Sub-Group to notify the Vice Chair and JW by email (alvaro.sanchez@defence.gov.au and jeff.wootton@iho.int) at the earliest opportunity. | S-101PT | Completed
S-101PT5-09 | Portrayal | Engage with the S-100WG in regard to work required on S-101 portrayal, ECDIS performance, etc. (TSM8). | Vice-Chair | Time Expired | S-101PT10.
S-101PT5-10 | Validation Checks | PT members interested in participating in the S-100 Data Validation Sub-Group to notify the Chair and JW by email (thomas.richardson@ic-enc.org and jeff.wootton@iho.int) at the earliest opportunity. | S-101PT | Completed
S-101PT5-11 | S-101PT Work Plan | The draft S-101 Work Plan to be forwarded to the S-100WG Chair for S-100WG endorsement and inclusion in the S-100WG report to HSSC12; and to the IHO Secretariat for posting on the S-101PT page of the IHO web site (September 2020). | Chair | Completed | Included in S-100WG report (S-101PT Report) to HSSC12.
S-101PT5-12 | S-101PT Work Plan | Establish an Issues and Risk Log and design an S-101 Engagement Plan (S-101PT6). | Chair | Completed | Refer to paper S-101PT6-11. Completed - see new actions S-101PT6-13 and S-101PT6-14.
S-101PT5-14 | Navigational Purposes | A dedicated meeting of a small group to be convened to discuss the issues raised in Paper S-101PT5-11 (October 2020). Possible feedback required to TSM8. | NIWC (lead)/Chair/IHO Sec | CLOSED | Proposal withdrawn.
S-101PT5-15 | VALSOU Decimal Places | Paper S-101PT5-12 to be considered by the DCEG Sub-group (November 2020). | S-101 DCEG Sub-Group | CLOSED | Resolution amended to 0.01 metres for testing purposes. Closed pending testing recommendations. NOTE: ENCWG has agreed to 1.0m resolution.
S-101PT5-16 | VALSOU Decimal Places | Paper S-101PT5-12 to be submitted to the ENCWG for consideration. | IC-ENC | Completed
S-101PT5-17 | Fairway Portrayal | Paper S-101PT5-14 to be considered by the Portrayal Sub-Group (November 2020). | S-101 Portrayal Sub-Group | Completed | See Port SG Report S-101PT6-07 and Action S-101PT6-06.
S-101PT5-18 | Light Sector Portrayal | Paper S-101PT5-15 to be considered by the Portrayal Sub-Group (November 2020). | S-101 Portrayal Sub-Group | Completed | See Port SG Report S-101PT6-07 and Action S-101PT6-06.
S-101PT5-19 | Quality of Bathymetric data and ECDIS Performance | Paper S-101PT5-16 to be considered by the Portrayal Sub-Group (November 2020). | S-101 Portrayal Sub-Group | Completed | See Port SG Report S-101PT6-07 and Action S-101PT6-06.
S-101PT5-20 | Grouping of Soundings | Paper S-101PT5-17 to be considered by the Portrayal Sub-Group (November 2020). | S-101 Portrayal Sub-Group | Completed | See Port SG Report S-101PT6-07 and Action S-101PT6-06.
S-101PT5-21 | Compendium of AHO Proposals | Paper S-101PT5-18 to be considered by the DCEG Sub-group (November 2020). | S-101 DCEG Sub-Group | Completed | To be discussed at next DCEG SG meeting. 20/08/21: Proposals 2 and 3 applied in DCEG. 01/12/21: Portrayal SG Lead: Related Portrayal actions, if any, are listed as Port_SG - Recommend removing S-101 Portrayal Sub_Group from the 'Lead' column. DCEG SG Lead: All DCEG amendments applied except for "Off-Station" proposal for attribute status.
S-101PT5-22 | S-57 to S-101 Encoding | Liaise with the S-100WG lead on S-57 to S-101 conversion (Jonathan Pritchard) on strategies that may be adopted for S-57 datasets to facilitate S-57 to S-101 conversion | S-101 DCEG Sub-Group | Completed | Ongoing liaison with conversion sub group is required. Note drafting of S-57 to S-101 Conversion Guidance document for data producers (in development). S-101PT7: S-57 to S-101 Conversion to be included as a standing Agenda item for S-101PT meetings.
S-101PT5-23 | NIWC Testbed Update | DCEG Sub-Group to discuss the following issues raised in the NIWC Testbed Update report (S-101PT5-21 – listed by the associated Presentation slides): Slides 15, 21, 27. | S-101 DCEG Sub-Group | Completed | To be discussed at next DCEG SG meeting. Slide 15: S-100 Ed 5.1.0 (clauses 10a-4.4 and 10a-6.1.2.1) now consistent - assume now OK? Slide 21: See S-100 Ed 5.1.0, clause 10a-5.1.4. OK? Slide 27: S-58 not just for data producers, also for RENCs. These issues should be picked up prior to delivery to the end-user system.
S-101PT5-24 | NIWC Testbed Update | Portrayal and ECDIS Performance Sub-Group to discuss the following issues raised in the NIWC Testbed Update report (S-101PT5-21 – listed by the associated Presentation slides): Slides 4, 12, 16, 17, 22, 25, 26, 28, 32, 33, 34, 35, 36, 37. | S-101 Portrayal Sub-Group | Completed | See Port SG Report S-101PT6-07 and Action S-101PT6-06.
S-101PT5-25 | NIWC Testbed Update | NIWC to report to the S-100WG (TSM8) the following issues raised in the NIWC Testbed Update report (S-101PT5-21 – listed by the associated Presentation slides): Slides 15, 21, 27. | NIWC | Completed | Slide 15: OBE per latest S-101 Part 10a redlines Slide 21: SevenC's indicated they would submit proposal to standardize encoding of boolean attributes Slide 27 (invalid geometries): Ensure validation check is present? Completed - See new Action S-101PT6-01.
S-101PT5-26 | NIWC Testbed Update | Paper to be developed to describe the implementation of units of measurement for weights and measures (in conformance to S-52 clause 10.8) (for S-101PT6). | Chair/RM | Completed | See agenda item S-101PT6-INF-01. See Paper TSM8-6.2.
S-101PT5-27 | NIWC Testbed Update | National language support and ECDIS Pick Report issues (including those identified in slides 30 and 31 of the S-101PT5-21 agenda item presentation) to be addressed as a lower priority task (for S-101 Edition 1.x or 2.0). | S-101PT | Closed | Note low priority. S-101PT7: To be discussed intersessionally. 14/03/22: Chair: Noting S-100WG6 discussions this action is expected to be overtaken by S-100 Part 18. Propose close this action. Closed due to S-100 developments. | 1) S-52 10.8.4 - note aggregates use priority of highest priority member which intersects pick region, show single pick report entry for aggregates. 2) Is there a need to exclude attributes from the pick report (e.g. S-57 category "C" attributes, or tidal stream panel values)? If so, recommend add new attr to DCEG section 30 which catalogs attributes to exclude. Alternatively, propose extension to FC model and catalog these attributes in the FC - supports use by other product types.
S-101PT6-01 | NIWC Testbed Update (Action S-101PT5-25 - slide 27) | S-100 Validation Checks developers to pick up the invalid geometries issue to confirm checks cover this; and guidance on what systems should do when receiving such data exists. | JP | Closed | Close - Refer to new Action S-101PT11-05.
S-101PT6-02 | DCEG Update | PT members interested in participating in the Associations Sub-Group to notify JW by email (jeff.wootton@iho.int) at the earliest opportunity. | S-101PT | CLOSED | IHO Sec (lead), TR, RM, JP, DG, KD, HB, RF, VB, MB, HA, RB Note paper TSM8-6.8.
S-101PT6-03 | DCEG Update | PT members interested in participating in the S-101 Dataset Load/Unload Sub-Group to notify JW by email (jeff.wootton@iho.int) at the earliest opportunity. | S-101PT | CLOSED | CM (lead), JW, RG, PlB, MB, VB, KD, HA, RM, HB, IK, AS, DG
S-101PT6-04 | DCEG Update | Prepare final redline and clean versions of S-101 DCEG Edition 1.0.1 and publish on the IHO web site and the IHO GI Registry by end of February 2021. Include any changes approved as a result of discussions on Paper S-101PT6-12 and any other Papers for S-101PT6. | JW | Completed | DCEG Edition 1.0.1 posted 01 March 2021.
S-101PT6-05 | DCEG Update | Investigation to be conducted into possible amendments to the UOC resulting from the change in terminology from “Emergency Wreck Marking Buoy” to “New Danger Marking Buoy” (for ENCWG6). | JW | Completed | To be discussed at the IHO/IALA Technical Coordination Meeting April 2021. Discussion at this meeting indicates that a decision will be made by IALA later in 2021.
S-101PT6-06 | Portrayal Progress | Project Team Members to provide feedback on any of the Portrayal Sub-Group GitHub issues before 04 April 2021, noting that subject to no adverse comments this will be taken as S-101PT endorsement of the decisions/actions agreed by the Portrayal Sub-Group. | S-101PT | CLOSED | S-101PT7: JW to take up with Alvaro.
S-101PT6-07 | Portrayal Progress | Add a dedicated area for S-101 Portrayal Catalogue development under the IHO GitHub. | IHO Sec | Completed | Completed 23/04/21: https://github.com/iho-ohi/S-101_Portrayal-Catalogue
S-101PT6-08 | Portrayal Progress | Ensure that all S-101 portrayal considerations as included in the “S-57 Removed_Remodelled Items” spreadsheet have been amalgamated with the work that has been done by Germany and US (NOAA) before 04 April. | AS/JW | Completed | 01/12/21: Portrayal SG Lead: Final list of actionable entries now listed in 'S-57 Objects and Attributes' spreadsheet (106 actions).
S-101PT6-09 | Validation Update | Investigate the possibility of submitting a request to fund the development of S-101 test datasets utilising the IHO Special Projects Fund (for HSSC13). | Chair | Completed | Request passed to S-100WG as part of HSSC13 Report.
S-101PT6-11 | S-101PT Workplan Update | Pending completion of the Edition 1.0.1 DCEG (Action S-101PT6-04), version 1.0.1 of the S-101 Feature Catalogue to be prepared by end of March 2021. | IK/KHOA | Completed | Expected 09 April. Published July 2021.
S-101PT6-12 | S-101PT Workplan Update | Establish a repository for S-101 test datasets, with “development” test data to be made available by 01 September 2021. | Chair/IHO Sec | Completed | 02/12/21: Chair: Github repository has been established. Work needed on process and lead for this aspect. See workplan update PT8 09, amend to Completed.
S-101PT6-13 | S-101 Roadmap | PT members interested in participating in the S-101 Roadmap Drafting Group to notify the Chair by email (thomas.richardson@ic-enc.org) at the earliest opportunity. | S-101PT | CLOSED | Chair (lead), JW, VP, HP, AS, RG, LH
S-101PT6-14 | S-101 Issues Log | PT members to review the draft S-101 Issues Log and supply any amendments or additions by email (thomas.richardson@ic-enc.org and jeff.wootton@iho.int) at the earliest opportunity. | S-101PT | CLOSED
S-101PT6-15 | Bathymetric Data Quality | Changes to be applied to the draft S-101 DCEG Edition 1.0.1 as approved by the S-101PT in regard to the recommendations on remodelling of S-101 features based on the DQWG recommendations related to improving the indication of bathymetric data quality in ECDIS (for inclusion in finalised Edition 1.0.1 DCEG). | JW | Completed | JW email 01/03/21.
S-101PT6-16 | Portrayal of Small Craft Mooring Areas | Submit a proposal to the Portrayal Sub-Group requesting the development of new symbology for the portrayal of small craft mooring areas in S-101. | AS | Completed | Portrayal GitHub repository Issue #28.
S-101PT6-17 | Quality of Horizontal Measurement | Amend the allowable values of the attribute qualityOfHorizontalMeasurement in S-101 to the values 4 (approximate) and 5 (position doubtful), for S-101 DCEG Edition 1.0.1. | JW | Completed | JW email 01/03/21.
S-101PT6-18 | Quality of Horizontal Measurement | Raise the decisions made in relation to the restriction of the values of the attribute qualityOfHorizontalMeasurement to the NCWG for possible impacts on S-4 and INT1. | CM/MH | Completed | S-101PT7: Proposal to be submitted to next NCWG meeting. 16/03/22: Paper NCWG7-06.3A was submitted to NCWG7 (Action NCWG7/3); Additional work to be conducted). New paper to be prepared for NCWG8. Paper NCWG8-06.7A submitted at NCWG and accepted (merging of PA and PD in favour of PD). Action Completed.
S-101PT6-19 | Placement of Texts in S-101 | PT members interested in participating in the S-101 Text Placement Sub-Group to notify CM by email (christian.mouden@shom.fr) at the earliest opportunity. | S-101PT | CLOSED | CM (lead), IK, KO, HA Note paper TSM8-6.15
S-101PT7-01 | HSSC13 Outcomes | Any S-101PT members interested in contributing to the development of the DF Concept “Governance” document to indicate to the IHO Secretariat (jeff.wootton@iho.int) at the earliest opportunity. | S-101PT | CLOSED
S-101PT7-02 | S-101PT Actions | References to S-101PT meeting Agenda item numbers to be removed from column 2 of the Consolidated Actions spreadsheet. | IHO Sec | Completed
S-101PT7-03 | S-101PT Actions | S-101PT Work Plan to be updated taking into account S-100WG and HSSC approval milestones. | Chair | Completed | To be completed at S-101PT8.
S-101PT7-04 | DCEG Update | Include changes that directly impact on S-101 implementation in the DCEG Document Control page for the next Edition. | JW | Completed | To be done on agreement to publish DCEG Edition 1.0.2.
S-101PT7-05 | Feature Catalogue | Add IF (Lloyd’s Register) to the small “expert group” for future S-101 Feature Catalogue reviews. | JW | Completed
S-101PT7-06 | Outreach | PT members interested in participating in the Outreach Sub-Group to notify the Chair by email (thomas.richardson@ic-enc.org) at the earliest opportunity. | S-101PT | Closed
S-101PT7-07 | Modify TextPlacement to Support Bearing/Distance | Include the Paper Modify TextPlacement to Support Bearing/Distance as a new Issue in the S-101 Documentation and FC GitHub repository (https://github.com/iho-ohi/S-101-Documentation-and-FC) for discussion within the DCEG Sub-Group; and the S-101 Portrayal GitHub repository (https://github.com/iho-ohi/S-101-Portrayal-SubWG) for portrayal implications. | JW | Completed | 01/12/21: Portrayal SG Lead: Portrayal subWG - Done - Github Issues # 29 DCEG SG Lead: Draft amendments made to DCEG. GitHub Issue to be posted.
S-101PT8-03 | DCEG Update | JW to discuss with HB offline the issues related to sounding and vertical datum and apply changes to the draft DCEG Edition 1.0.2. | HB/JW | Completed
S-101PT8-04 | DCEG Update | Final redline and clean versions of the S-101 DCEG Edition 1.0.2 to be prepared and published on the S-101 page of the Product Specification Register within the IHO GI Registry. | IHO Sec | Completed | 14/03/22: This will be posted with the corredponding Feature Catalogue in due course.
S-101PT8-05 | DCEG Update | Final redline version of the finalised S-101 DCEG Edition 1.0.2 to be provided to KHOA for development of the Edition 1.0.2 Feature Catalogue as soon as possible. KHOA to prepare the draft Edition 1.0.2 Feature Catalogue for review. | IHO Sec/KHOA | Completed
S-101PT8-06 | DCEG Update | All substantive changes applied to the S-101 DCEG Edition 1.0.2 that have not yet been approved by the DCEG Sub-Group to be included as new issues on the S-101 Documentation and FC GitHub repository. | IHO Sec | Completed
S-101PT8-09 | Portrayal Update | “S101 Portrayal subWG summary report” spreadsheet to be refined to include only outstanding items and sent to the S-101PT for review by the end of January 2022. | Vice-Chair | Completed | AS-16MAR22 - Refer to 'S-101 Portrayal Sub-Group Actions' section below (PortSG37 to 72).
S-101PT8-10 | Portrayal Update | Decisions coming from the “S101 Portrayal subWG summary report” spreadsheet review to be included in the S-101PT master sheet of decisions and actions at the conclusion of the review period. | Vice-Chair | Completed
S-101PT8-11 | Portrayal Update | Continue discussions with the IHO Sec for possible future project related to mariner input to S-101 implementation with the Singapore Lab. | Chair | Time Expired | 17/07/23: Chair: Propose that this is time expired. Continue to include SG Lab within new Testbeds update agenda section.
S-101PT8-13 | New S-101 Symbology | Chair to initiate a liaison with the NCWG on portrayal issues, including the NCWG task for the development of a “baseline symbology set” for paper charts. | Chair | Completed | 14/03/22: Chair has engaged with NCWG no further action is nessecary at this stage.
S-101PT8-14 | New S-101 Symbology | Chair to include the subject of determination of allowable differences between S-52 and S-101 portrayal in the dual-fuel environment for a future S-101PT meeting. | Chair | Completed | 14/03/22: Item for PT9. 17/07/23: Chair: Refer paper S-101PT11-08.2. | Propose mark Completed based on the paper given the action. Further actions may then stem from the paper.
S-101PT8-15 | Validation Update | Any member of the S-101PT that is interested in taking up the role of S-101 Validation Checks Sub-Group Lead to contact the S-101PT Chair and JW (IHO Sec) at the earliest opportunity. | S-101PT | Time Expired | 14/03/22: Lead still sought. S-101PT10: Klas (SE) volunteered to lead the Sub-Group.
S-101PT8-18 | Work Plan Update Review and Updating | Draft Feature Catalogue and all related discussions/issues to be included in the IHO GitHub. | IHO Sec | Completed | Paper on documentation at S-101PT9 is related to this action. Retain. January 2023: FC Ed 1.1.0 placed in the GitHub along with S-101 documentation.
S-101PT8-19 | Work Plan Update Review and Updating | S-100WG to be appraised of the GitHub repository for the S-101 Feature Catalogue as a possibility for the hosting of related “unit tests” development. | Chair | Closed
S-101PT8-20 | Work Plan Update Review and Updating | Members of the S-101PT to consider nominating to lead the Test Data Sub-Group at the earliest opportunity. | S-101PT | Completed | Test Data Sub-Group members @ 17/03/22: NIWC, IIC, RM, NGA (US), NOAA (US), Primar, IC-ENC, Caris, 7Cs, DKart, Esri, CA, AU, FR
S-101PT8-21 | Work Plan Update Review and Updating | Test Data Sub-Group to discuss the development and provision of S-101 test datasets, including data sets to test the functionality of the Feature Catalogue, and report back to the S-101PT. | Test Data Sub-Group | Completed | 14/03/22: The group has formed and still has no lead, but some work is progressing.
S-101PT8-22 | Work Plan Update Review and Updating | Project Team Letter to be prepared and circulated to PT members setting out the proposed Work Plan for endorsement and detailing the proposed Work Flows for Test Dataset and Portrayal Catalogue developments including target dates. | Chair/IHO Sec | Completed | 14/03/22: PT letter 5/2021 refers.
S-101PT8-25 | Scales Sub-Group Update | Revised definitions for maximumDisplayScale, minimumDisplayScale and a new definition for Viewing Scale to be submitted to the S-101PT9 meeting. | CM | Completed | 14/03/22: Item for PT9. Paper S-101PT9-06.5 approved at S-101PT9 (includes the definitions). Action completed.
S-101PT8-26 | Scales Sub-Group Update | S-101PT to liaise with S-100WG and/or CIRM to try to come to an agreement on a minimum list of mandated viewing scales in ECDIS systems, so that the scale minimum policy as described in the DCEG can be efficiently implemented. | Chair/CM | Closed | 14/03/22: Engagement with S-100WG lead for S-98 has commenced. S-101PT10: Close Issue - to be tested (refer to related Action S-101PT10-09).
S-101PT8-28 | Alerts and Indications and S-101 | Recommendations B-F of paper S-101PT8-20 to be discussed within the S-101 Portrayal Sub-Group based on the way forward proposed in Recommendation A. | Portrayal SG | Completed | Portrayal GitHub #88.
S-101PT8-30 | S-101 Versioning | The versioning tables included in paper S-101PT8-21 are to be refined, with discussion with relevant stakeholders as required. | Chair | Completed | 14/03/22: Item for PT9. 17/07/23: Chair: Refer paper S-101PT11-11.1. | Propose mark Completed based on the paper given the action. Further actions may then stem from the paper.
S-101PT8-33 | Depth Resolution in S-101 ENCs | Amend the [CMFZ] to {10} in the draft S-101 Edition 1.1.0 Main document. | IHO Sec | Completed
S-101PT8-34 | Depth Resolution in S-101 ENCs | The resolutions for depth- and clearance-related attributes to be discussed in the S-101 DCEG Sub-Group. | DCEG SG | Closed | Attributes measurementDistanceMaximum and measurementDistanceMinimum amended to be consistenct with S-57 (resolution 1m). The only other attribute not consistent with S-57 is valueOfSoundingMeasurement, which has been discussed. Suggest close. Close - Refer to new Action S-101PT11-06.
S-101PT8-35 | Loxodromic Interpretation in S-101 ENCs | Paper S-101PT8-23 to be included as an Agenda Item for S-101PT9. | IHO Sec | Completed | 14/03/22: Item for PT9.
S-101PT8-36 | Improvements to Encoding Maritime Jurisdiction Features in S-101 | Paper S-101PT8-24 to be included as an Agenda Item for S-101PT9. | IHO Sec | Completed | 14/03/22: Item for PT9.
S-101PT9-01 | Actions from HSSC14 | Determine further possible associated costs involved in achieving the targets for S-101 development and report to the HSSC. | Chair | Completed | For HSSC15.
S-101PT9-02 | Actions from HSSC14 | 101PT Members to consider nominating for S-101PT Executive positions as a requirement following A-3. | S-101PT | Time Expired | For S-101PT10.
S-101PT9-03 | DCEG Sub-Group Update | Finalise S-109PT9 approved changes as included in Paper S-101PT9-06.1 to the draft Edition 1.1.0 DCEG. | JW | Completed | For S-100WG7.
S-101PT9-04 | DCEG Sub-Group Update | “Roll back” the changes related to the removal of the depth-related attributes from the feature FoulGround. | JW | Completed | For S-100WG7.
S-101PT9-05 | DCEG Sub-Group Update | Discuss and develop, as required, additional encoding guidance for the application of the portrayal related (system) attributes in S-101 ENC. | DCEG SG | Completed | For S-101PT10. 07/08/23: Refer to S-101 Documentation and FC Github Issue #77.
S-101PT9-06 | DCEG Sub-Group Update | Discuss and develop options and associated guidance for the implementation of the UpdateInformation Meta feature for consideration of the S-101PT. | DCEG SG | Closed | Overtaken by events. See Action S-101PT10-21 and Paper S-101PT11-08.4.
S-101PT9-07 | DCEG Sub-Group Update | Add the enumeration type attribute categoryOfCargo and corresponding encoding guidance for dangerous/hazardous cargo berth to the DCEG for the Berth feature. | JW | Completed | For S-100WG7.
S-101PT9-08 | DCEG Sub-Group Update | Prepare the final draft Edition 1.1.0 of the S-101 DCEG for submission to the S-100WG. S-101PT Members to review changes resulting from S-101PT9 and pass any feedback to their S-100WG representatives. | JW, S-101PT | Completed | For S-100WG7.
S-101PT9-09 | Portrayal Sub-Group Update | Provide IHO Sec with the S-101 Edition 1.0.2 Portrayal Catalogue for posting in the IHO GI Registry. | NIWC, JW | Completed | By December 2022.
S-101PT9-10 | Test Dataset Sub-Group Update | Provide any feedback on the completed S-101 Test Datasets as contained in the provided S-100 Edition 5.0.0 Exchange Set (https://github.com/iho-ohi/S-101-Test-Datasets/tree/main/dev/exports) and associated Specifications to S-101PT Chair and Kevin Dickens. | S-101PT | Time Expired | Before S-101PT10.
S-101PT9-11 | Test Dataset Sub-Group Update | Consider contributing to the updating and enhancement of the S-101 TDS for S-101 Edition 1.1.0. | S-101PT | Completed | Before S-101PT10. | UK and DK expressed interest during S-101PT9 - to be confirmed.
S-101PT9-12 | ENC Scales and Dataset Load/Unload Sub-Group Update | Apply changes related to ENC scales and dataset load/unload as approved at S-101PT9 to the final draft S-101 Edition 1.1.0 Main document. | JW | Completed | For S-100WG7.
S-101PT9-14 | S-101 Main document Edition 1.1.0 comment adjudication. | Prepare the final draft Edition 1.1.0 of the S-101 Main document for submission to the S-100WG. S-101PT Members to review changes resulting from S-101PT9 and pass any feedback to their S-100WG representatives. | JW, S-101PT | Completed | For S-100WG7.
S-101PT9-15 | S-101 Main document Edition 1.1.0 comment adjudication. | Review outstanding comments from the S-101 Edition 1.1.0 Main document review (see Annex to S-101PT9 Record) for possible changes to be included in S-101 Edition 1.2.0. | S-101PT | Closed | For S-101PT10. 06/02/24: Appears to have been overtaken by events (development of Edition 1.2.0 and new submitted papers). Recommend close.
S-101PT9-16 | Loxodromic Interpretation in S-101 ENCs | Conduct further investigations into the removal of the constraint within the S-101 Product Specification restricting interpolation of line segments to loxodromes only, using the arguments presented in Paper S-101PT9-08.1. | S-101PT | Closed | For S-101 Edition 1.2.0. Tom 20/12/23: My proposal here is to raise an issue in Github but I don’t see any urgency for this one. Unless someone volunteers to explore further I don’t think its going to make 2.0.0 but it shouldn’t get lost entirely. Refer to S-101 Documentation and FC GitHub Issue #130 | Propose transfer to Github based on PT10 discussion and close this action as below.
S-101PT9-17 | S-101 and Vertical Clearance | Develop new rules for ECDIS to alert and provide indications within S-101 ENCs for vertical clearances based on an air draft context parameter. | S-101PT | Closed | Post-Edition 2.0.0. 17/07/23: Chair: Can we hold this in the Github with a label and close the action? | Support transfer to Github.
S-101PT9-18 | Pilotage Feature Symbology in S-101 | Continue discussions to resove the issues regarding Pilotage District area boundary symbology and the distinction between a pilot boarding place encoded as an area and a pilot boarding place encoded as a point, taking into account the discussions at S-101PT9. | Portrayal Sub-Group | Completed | For S-101 Edition 1.2.0.
S-101PT9-19 | QoBD Visualisation | Develop the two preferred options for portrayal of QoBD information as included on Paper S-101PT9-08.4 for inclusion in the Portrayal Catalogue for evaluation and testing (in addition to current “star rating” symbology). | Portrayal Sub-Group | Closed | Report progress to S-101PT10. 18/09/23: For options for data modelling or QoBD and Spatial Quality, see Paper S-101PT11-08.9. 06/02/24: Overtaken by events - single option agreed at S-101PT11 - Close.
S-101PT9-20 | Improvements to Encoding Maritime Jurisdiction Features in S-101 | Review all instances of the “work-around” encoding of a “very narrow surface” to represent a linear feature in the DCEG and consider adding curve as a valid geometry for these features. | DCEG SG | Completed | For S-101 Edition 1.2.0. Refer Paper S-101PT10-07.1 and related Action S-101PT10-10.
S-101PT9-21 | Improvements to Encoding Maritime Jurisdiction Features in S-101 | Provide a further submission with additional justification and DCEG redline edits (Paper S-101PT9-08.5 refers). | UK | Completed | Before S-101PT11. Refer Paper S-101PT10-07.1.
S-101PT9-22 | Use of SMIN/SMAX in S-101 | Apply changes based on the recommendations in Paper S-101PT9-08.6 to the S-101Main document once corresponding changes have been approved for S-100. | IHO Sec, SevenCs | Completed | For S-101 Edition 1.2.0. 10/08/23: Changes applied at new clause 4.8.2 and clauses B-5.1.31 and B-6.1.30. Sent to Holger for review.
S-101PT9-23 | Order of Records in S-101 | Apply changes based on the recommendations in Paper S-101PT9-08.7 to the S-101Main document. SevenCs to review and provide any additional feedback/comment. | IHO Sec, SevenCs (HB) | Completed | For S-100WG7. More work required? Need to check with Holger as to whether he included all the requirements from this Paper in his final review of Annex B. S-101PT10: Completed.
S-101PT9-24 | Aliases in the S-101 FC | Discuss the inclusion of Aliases in the S-101 Feature Catalogue as requested by Paper S-101PT9-08.8 and report to S-101PT. | DCEG SG | Closed | For S-101PT10. 07/08/23: Refer to S-101 Documentation and FC Github Issue #61.
S-101PT9-25 | Adopting the Term "Mechanical Sweep" | Discuss and develop, as appropriate, revised modelling and guidance for the encoding of “mechanical sweep” as a new technique of vertical measurement, based on the recommendations in Paper S-101PT9-08.9. | DCEG SG | Completed | For S-101PT10. 07/08/23: Refer to S-101 Documentation and FC Github Issue #80.
S-101PT9-26 | New Point Symbol for Reed | Develop a new symbol for reed beds of type point, based on the existing symbol MARSHES1P; and submit a proposal to the IHO GI Registry. | Portrayal Sub-Group | Completed | For S-101 Edition 1.1.0.
S-101PT9-27 | HSSC ISO 9001 Cell Update | Pass any concerns on the contents of the Risks document (S-101PT9-09.2) to the S-101PT Chair and Vice-Chair. | S-101PT Members | Time Expired | For S-101PT10. 17/07/23: Chair: Propose that this is time expired.
S-101PT9-28 | HSSC ISO 9001 Cell Update | S-101PT Vice-Chair and IHO Sec to provide an abbreviated version of the HSSC ISO 9001 Cell Update report to S-101PT9 to the S-100WG7 meeting. | Vice-Chair, YB | Completed | For S-100WG7.
S-101PT9-29 | S-101 Documentation Changes | Investigate solutions within the GitHub document interface and raise the issue to the S-100WG and HSSC respectively. | Chair, IHO Sec, SHOM | Completed | For S-100WG8 and HSSC16. Engage with SHOM. | Chair to raise at S-100WG8. Paper in liaison with IHO Sec? Close - refer to Action S-100WG8-10.
S-101PT9-30 | S-101 Documentation Changes | Investigate the possibility of participating in a training session based on the development of the S-102 Product Specification document management via the GitHub. | IHO Sec | Completed | Training scheduled for April 2023.
S-101PT9-31 | Towards S-101 2.0.0 | Submit the proposed S-101 development timeline to the S-100WG for approval. | Chair | Completed | For S-100WG7.
S-101PT9-32 | S-101 Resources | Create and develop an S-101 Resources page and associated sub-pages on the IHO web site. | Chair, IHO Sec | Completed | For S-101PT10. 17/07/23: Chair: Propose that this is complete as the page is live. Promoting it can follow.
S-101PT10-01 | S-101PT Actions | Apply the agreed updates to the cumulative list of S-101PT Actions and post the updated list on the S-101PT page of the IHO Web site. | IHO Sec | Completed
S-101PT10-02 | S-101PT Actions | Review outstanding Portrayal SG Actions and provide feedback to IHO Sec. | Portrayal SG Lead | Closed | For July 2023. 07/02/24 (SG Lead): Refer to PsWG report to S101PT12. Is a standing S-110 Agenda Item. Close.
S-101PT10-03 | DCEG Sub-Group Update | Submit a Paper to the ENCWG proposing that guidance is included in the S-57 UOC on encoding the spatial attributes (POSACC and SOUACC) on the S-57 Objects corresponding to the mandation of the population of these attributes on S-101 Features. | IHO Sec | Closed | For ENCWG8. S-101PT12: May be overtaken by events. New Action for S-101PT to liaise with the ENCWG small group established to look at the impacts of S-100 ECDIS on S-52.
S-101PT10-04 | DCEG Sub-Group Update | Work on implementing and testing (including the development of test data sets) the application of the TextPlacement cartographic feature; and refining the guidance in the DCEG. | SE (Lead), IHO Sec, T_Caris, NIWC | Closed | For S-101PT10. 07/08/23: Refer to S-101 Documentation and FC Github Issue #7.
S-101PT10-05 | Portrayal Sub-Group Update | Request the S-164 Sub-Group to develop a new S-164 test for Independent Mariner Selectors. | Portrayal SG Lead | Completed | For ENCWG8. 07/02/24 (SG Lead): Refer to S-164 GitHub # 70.
S-101PT10-08 | Portrayal Sub-Group Update | Further investigate the issue with assigning a Viewing Group to INDHLT and if required bring to the attention of the S-164 Sub-Group (S-100WG). | Portrayal SG Lead | Completed | For S-100WG8. 06/02/24 (SG Lead): Refer to PsWG GitHub # 136. Should an issue be created in S-164 GitHub space?
S-101PT10-09 | ENC Scales and Dataset Load/Unload Sub-Group Update | Test the data loading algorithm and report any findings to the Sub-Group Lead. Sub-Group Lead to report findings to S-101PT. | ENC Scales and Dataset Load/Unload Sub-Group members, S-101 Implementers | Closed | For S-101PT11. Close - Refer to new Action S-101PT11-07.
S-101PT10-10 | Improvements to Encoding Maritime Jurisdiction Features in S-101 | Include line primitive to the existing S-101 maritime jurisdiction features as included in the left-hand column of the Table at Annex A to Paper S-100WG10-07.1. | IHO Sec | Completed | For July 2023.
S-101PT10-12 | S-101 Change Proposal - Berthing/Fender Berth | Propose amendments in conformance with the S-101PT decision in response to Paper S-101PT10-07.3; and update the S-101 DCEG as required. | IHO Sec | Completed | For July 2023. Berthing amended to Berthing Signal Station.
S-101PT10-13 | S-101 Change Proposal - Berthing/Fender Berth | Notify the NIPWG (Raphael) to propose the new concept “Fender Berth” to the GI Registry, Concept Register. | IHO Sec | Completed | Email to Raphael sent 19/07/23.
S-101PT10-14 | Category of Bridge in S-101 | Apply changes to the modelling of the S-101 feature Bridge as included in Paper S-101PT10-07.6; ; and update the S-101 DCEG as required. | IHO Sec | Completed | For August 2023.
S-101PT10-15 | Support for MRNs in S-101 | Take up with the S-100WG to provide further guidance on the consistent implementation of MRNs in S-100. | Chair | Completed | For S-100WG8. 30/08/23 (Chair): Engaged with NIPWG and plan to complete at S-100WG8. | Close - refer to Action S-100WG8-08.
S-101PT10-16 | Support for MRNs in S-101 | Report the S-101PT discussions on the consistent implementation of MRNs to the NIPWG. | Chair | Completed | For NIPWG10. 30/08/23 (Chair): Reported propose mark complete.
S-101PT10-17 | Mooring/ Warping Facility in S-101 | Develop a proposal on options for the modelling of mooring cables for consideration of the DCEG Sub-Group. | IHO Sec | Completed | For S-101PT11. 07/08/23: Refer to S-101 Documentation and FC Github Issue #84. 20/09/23: Refer to Paper S-101PT11-08.11.
S-101PT10-18 | Mooring/ Warping Facility in S-101 | Remove value 7 (mooring buoy) as an allowable value for attribute categoryOfMooringWarpingFacility in S-101 and develop a new feature for mooring buoy. | IHO Sec | Completed | For S-101PT11. 07/08/23: Refer to S-101 Documentation and FC Github Issue #81.
S-101PT10-19 | Mooring/ Warping Facility in S-101 | Discuss the outstanding recommendations in Paper S-101PT10-07.5. | DCEG Sub-Group | Completed | For S-101PT11. 07/08/23: Refer to S-101 Documentation and FC Github Issue #82. 20/09/23: Refer to Paper S-101PT11-08.11.
S-101PT10-20 | Mooring/ Warping Facility in S-101 | Report the S-101PT discussions on the revised modelling of the attribute categoryOfMooringWarpingFacility to the NIPWG, noting the requirement for the harmonization of information between products (S-101 and S-131). | Chair | Completed | For NIPWG10. 30/08/23 (Chair): Reported propose mark complete.Further paper to be submitted to NIPWG as a result of DCEG SG discussion.
S-101PT10-21 | Use of the Update Information Feature | Develop a proposal for the modelling and implementation of the UpdateInformation feature, based on the recommendations in Paper S-101PT10-07.10, for consideration of the DCEG Sub-Group. | IHO Sec | Completed | For S-101PT11. 07/08/23: Refer to S-101 Documentation and FC Github Issue #41 and Paper S-101PT11-08.4.
S-101PT10-22 | Use of Roles in the Feature Catalogue | Convene a meeting (VTC) of the Associations Sub-Group to discuss the recommendations included in Paper S-101PT10-07.7 and apply agreed changes to the DCEG. | IHO Sec | Closed | For August 2023. 15/09/23: Discussions held with Hugh during NIPWG10 (September 2023) and example draft changes made in the DCEG for consideration of the S-101PT. . 15/02/24: Refer to Papers S-101PT12-06.10 and 10A; Associations Sub-Group meeting to be held on 05/03/24.
S-101PT10-23 | Topmarks with Multiple Colours | Amend multiplicity of sub-attribute colour on the complex attribute topmark to [0..*] for all instances in the S-101 DCEG; and add colourPattern as an allowable sub-attribute. | IHO Sec | Completed | For August 2023.
S-101PT10-24 | Topmarks with Multiple Colours | NL to raise the issue of the validation checks associated with the colours of daymarks/topmarks with the S-101 Validation Checks Sub-Group. | NL | Closed | For July 2023. 06/02/24: Overtaken by events - multiple colours for topmarks now allowed in S-101 Edition 1.2.0. Close.
S-101PT10-25 | Vertical Datum Information in S-101 | Develop a proposal on possible options for the modelling of the metadata features in line with discussions at S-101PT10 for consideration of the DCEG Sub-Group. | IHI Sec, Chair, NIWC | Completed | For S-101PT11. 07/08/23: Refer to S-101 Documentation and FC Github Issues #59, #72, #73, #74. 19/09/23: Refer Paper S-101PT10-08.10.
S-101PT10-26 | Small Craft Mooring Areas | Re-work the proposal on small craft mooring areas in consultation with the NIPWG for presentation to NIPWG and S-101PT. | FR, UK, AU, IHO Sec | Completed | For S-101PT11. 15/09/23: Refer to Paper S-101PT11-08.8. Cleared by the NIPWG 15/09/23.
S-101PT10-27 | Mandating the ReplacedData Attribute | Apply changes to the S-101 Main document in line with the recommendations in Paper S-101PT10-07.12 and the decisions made at the meeting. | IHO Sec | Completed | For S-101PT11.
S-101PT10-28 | Cancellation Update Information | Further investigate the proposal on cancellation update information, including development of test datasets and testing, and report back to S-101PT. | PRIMAR, IC-ENC | Completed | For S-101PT11. 06/02/24: Refer to paper S-101PT12-06.20.
S-101PT10-29 | Mandating Dataset File with New Support File | Provide redline changes for the S-101 Main document for mandating a dataset file to be included in the Exchange Set containing the first release of a new support file. | PRIMAR | Completed | For S-101PT11. 06/02/24: Refer to paper S-101PT12-06.21.
S-101PT10-30 | S-100 Resources Page | Provide any comments on the structure and content of the S-100 Resources Page to the Chair and IHO Sec. | S-101PT | Time Expired | For S-101PT11. Suggest mark as Time Expired.
S-101PT10-31 | ISO Cell Update | Provide redline changes for the S-101 Main document, Section 6 (Data Quality) to conform with the DQWG template. | PRIMAR | Completed | For S-101PT11. 29/08/23: Email to Svein containing IHO Sec amended Section 6 of Main document incorporating the DQWG template. 06/02/24: S-101 Edition 1.2.0 approved at S-100WG8 meeting. Completed.
S-101PT10-32 | Election of S-101PT Office Bearers | Update the S-101PT web page for the new S-101PT Office Bearers as required. | IHO Sec | Completed | For June 2023.
S-101PT11-01 | S-101PT ToRs Review | Publish the revised S-101PT ToRs on the S-101PT on the S-101PT page of the IHO web site. | IHO Sec | Completed | To be presented at HSSC16 for approval.
S-101PT11-02 | S-101PT ToRs Review | Report the revised S-101PT ToRs to the S-100WG (S-100WG8). | Chair | Completed
S-101PT11-08 | DCEG Sub-Group Update | Discuss concerns raised by FI regarding the modelling and guidance for feature names in multiple languages; and apply changes as appropriate for consideration of the S-101PT. | IHO Sec, FI | Completed | Amended modelling included as discussed and agreed at S-101PT11 and S-100WG8 (IHO Sec, FI, Caris).
S-101PT11-09 | DCEG Sub-Group Update | Report the requirement for a context parameter for language to be included in ECDIS and impacts on S-98 to the S-100WG. | Chair | Completed | S-101PT Report to S-100WG8.
S-101PT11-10 | DCEG Sub-Group Update | Include the capability to encode variable units of measure for speed limits in S-101. | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-11 | DCEG Sub-Group Update | Apply name changes to the buoy and beacon features in S-101 (Buoy Xxxxx to Xxxxx Buoy). | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-12 | DCEG Sub-Group Update | Add a new attribute textRotation to the TextPlacement feature in S-101. | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-13 | DCEG Sub-Group Update | Add a new attribute interoperabilityIdentifier (type TE) to the aids to navigation features in S-101. | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-14 | DCEG Sub-Group Update | Include new Issues in the S-101 Documentation and FC GitHub for all changes that are being implemented for “proof of concept” and use a dedicated label to indicate them. | IHO Sec | Completed
S-101PT11-16 | Portrayal Sub-Group Update | Appraise IEC of the issues with the management of Mariners Objects and enquire as to whether they would be prepared to take on the management of them in the IHO GI Registry. | Chair | Completed | For S-101PT12. Tom 20/12/23: This has been done, a response received from TC80 MT5 and passed to Tom M as ENCWG chair to log this as a longer term action, I’ve suggested inclusion in the ENCWG workplan. In terms of this action I think it can be marked Completed.
S-101PT11-17 | Portrayal Sub-Group Update | Document requirements for Independent Mariner Selectors in S-100 ECDIS, and how these are supposed to work. | Portrayal SG | Completed | For S-101PT12. 07/02/24 (SG Lead): Pending - Refer to PsWG GitHub Issue #18 - NIWC: Completed for portrayal; IIC: Documentation will be completed before TSM10 (March 2024). Completed.
S-101PT11-18 | S-101 Validation Sub-Group Update | Initiate a task for the S-100 Validation Sub-Group to determine a standard structure for Validation Checks to be implemented across all S-100 based Product Specifications. | ENC Scales and Dataset Load/Unload SG Lead | Completed | Refer to Paper S-100WG8-03.12 and Action S-100WG8-16
S-101PT11-19 | S-101 Validation Sub-Group Update | Develop Check messages for the Parts 1 and 2 Checks. | DK (Lead), AU, PRIMAR | Completed | For S-101PT12.
S-101PT11-21 | Scales Sub-Group Update | Include new attribute optimumDisplayScale on the meta feature DataCoverage and amend all associated specification/guidance in S-101 documentation. | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-22 | Scales Sub-Group Update | Replace Main document Figure 4-6 with the proposed new Figures. | IHO Sec, FR | Completed | S-101 Edition 1.2.0.
S-101PT11-24 | Scales Sub-Group Update | Amend the wording of the paragraph at DCEG clause 2.5.9 related to application of scaleMinimum to features crossing multiple DataCoverage feature | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-25 | Scales Sub-Group Update | Remove the sentence related to overlapping scale ranges from DCEG clause 2.5.1. | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-26 | Scales Sub-Group Update | Apply changes to wording in S-101 Annex D as proposed in Paper S-101PT11-06.5. | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-27 | Scales Sub-Group Update | Develop a proposal for the inclusion of a data display (rendering) algorithm in S-101 Edition 2.0.0. | ENC Scales and Dataset Load/Unload SG | Completed | For S-101PT12. 06/02/24: Refer to Paper S-101PT12-06.11.
S-101PT11-28 | S-101 1.2.0 Main Document Changes | Review the Data Quality section 6 of the S-101 Main document draft Edition 1.2.0 and refine the changes as required, in consultation with PRIMAR (refer Action S-101PT10-31). | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-29 | Proposal - Power-Driven Vessels Prohibited | Apply changes to the DCEG as proposed in Paper S-101PT11-08.1. | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-30 | Allowable Differences Between S-52 and S-101 Display and Functionality in ECDIS | Provide the revised text based on the principles included in Paper S-101PT11-08.2 for inclusion in the S-101 Main document to the IHO Sec. | Chair | Completed | October 2023? Tom 20/12/23: This text has been included in S-101 edition 1.2.0.
S-101PT11-32 | Addressing Gaps in S-101 Raised by the MASS PT | Report the discussions at S-101PT11 to the MASS PT, noting in particular the suggestion that radarBand may also be handled by a Validation Check. | Chair | Completed | MASS PT6. Tom 20/12/23: I have informed the MASS PT chair of this progress suggest we mark this as Completed.
S-101PT11-33 | Use and Modelling of the UpdateInformation Feature | Amend the modelling for the meta feature UpdateInformation as proposed in Paper S-101PT11-08.4. | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-34 | Merging of features Restricted Area Navigational and Regulatory | Replace the current S-101 features RestrictedAreaNavigational and RestrictedAreaRegulatory with a single feature RestrictedArea. | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-35 | Proposal – Cable Submarine | Include a new value for telecommunications cable on the attribute categoryOfCable; and remove value 8 (fibre optic cable) as an allowable value. | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-36 | Overscale in ECDIS | Report the decisions of the S-101PT regarding overscale indications in ECDIS to the S-100WG for consideration. | Chair | Completed | Refer to Paper S-100WG8-03.6.
S-101PT11-37 | Proposal – Mooring Areas | Add the new feature MooringArea in the S-101 DCEG as proposed in Paper S-101PT11-08.8. | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-38 | Modelling and Quality of Bathymetric Data | Apply Option 1 of Paper S-101PT11-08.9 in the DCEG, noting the decision to retain the temporal capability for the encoding of horizontal and vertical uncertainties. | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-39 | Modelling and Quality of Bathymetric Data | Provide support for the development of test data to test the revised modelling of the QualityOfBathymetricData feature. | AU | Completed | For S-101PT12.
S-101PT11-40 | Options for Modelling Metadata Features | Apply changes to S-101 in accordance with recommendation 1 in Paper S-101PT11-08.10. | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-41 | Options for Modelling Metadata Features | Apply the redline changes to specify full coverage of the relevant metadata features in S-101. | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-42 | Options for Modelling Metadata Features | Develop a Table (based on Table 3.3 of S-57 Appendix B.1) for inclusion in S-101 documentation. | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-43 | Mooring/Warping Facilities in S-101 | Apply the modelling changes for the MooringWarpingFacility feature as proposed in Paper S-101PT11-08.11, noting the additional issues raised related to the proposal that were resolved. | IHO Sec | Completed | S-101 Edition 1.2.0.
S-101PT11-44 | Structures Over Navigable Water; Submarine Danger Area; Support File Management | Consider re-submission of these Papers to the next S-101PT meeting. S-101PT Members to review the submitted proposals for S-101PT11 for discussion at the next meeting. | IHO Sec, UK, PRIMAR | Completed | For S-101PT12.
S-101PT11-45 | NIPWG Liaison | Instigate a more active liaison with the NIPWG. | Chair | Completed | For S-101PT12 and NIPWG11. 07/02/24 (Chair): A more active liaison with cross attendance and review of papers has been instigated. Propose close action and add as standard agenda item.
S-101PT11-47 | S-98/S-164 Liaison | Prepare a Paper for S-101PT12 to facilitate a more focussed discussion on S-98 and its impact on S-101 implementation. | S-101PT Chair | Completed | For S-101PT12. Refer to Paper S-101PT12-06.5.
S-101PT11-48 | ISO Cell Update | Notify the ISO 9001 Cell (AS) of the timeframe for the upgrade of the KHOA Testbed to S-100 Edition 5.1.0. | IHO Sec | Completed | For November 2023. S-101PT12: Testbed intended to be updated to S-100 Edition 5.2.0 by mid-2024.
S-101PT11-49 | ISO Cell Update | Provide any test data that may be made publicly available to the IHO Secretariat (YB or JW) for placement on the S-100 Resources web page. | IHO MS | Completed | For S-101PT12. Refer to new Action S-101PT12-04.
S-101PT11-50 | Towards S-101 Edition 2.0.0 | Report the high risk to the timeline for publication of S-101 Edition 2.0.0 due to lack of time to test S-101 Edition 1.2.0 to the S-100WG. | Chair | Completed | Refer to Paper S-100WG8-03.6.
S-101PT11-51 | Towards S-101 Edition 2.0.0 | Report any capacity or timeframe issues that may impact on publication of S-101 Edition 2.0.0 to the S-101PT Chair. | SG Leads | Closed | For S-101PT12. S-101PT12: To be reported as part of Sub-Group reports to S-101PT. Close
S-101PT11-53 | Towards S-101 Edition 2.0.0 | Post the draft version of the S-101 Edition 1.2.0 DCEG on the S-101 Documentation and FC GitHub repository as soon as the data model changes approved at S-101PT11 have been applied. | IHO Sec | Completed | For October 2023.
S-101PT11-54 | S-100 Validation | report the S-100 Validation discussions to the S-100WG. | S-100 Validation SG Lead | Completed | Refer to Paper S-100WG8-03.12 and related Actions.
S-101PT11-55 | S-100 Validation | Contribute to the review of the Checks relating to the S-100 Parts that have been developed so far. | PRIMAR, Nautical Dimensions, IC-ENC | Completed | For S-101PT13.
S-101 Portrayal Sub-Group Actions
PortSG-01 | Quality of Bathymetric Data - Visualization of Vertical and Positional Uncertainties | Develop a portrayal proposal capable of managing both, positional and depth uncertainty values on charted Sounding, Underwater Rock, Wreck and Obstruction. | KHOA AS | Closed | Portrayal GitHub #1. (AS- 16MAR22) - Need allocation of resources and dedicated Github issue. (AS 04SEP2023) - Status changed to 'Closed'. Refer to PortSG-48.
PortSG-02 | Quality of Bathymetric Data - Visualization of Vertical and Positional Uncertainties | Develop changes to the A&I catalogue and on-shore ECDIS to implement the use of Horizontal Position Uncertainty, Vertical Uncertainty and displayUncertainties by ECDIS in-built route checking safety functions. Use the 'ECDIS expected performance' section of paper DQWG15_2020_05.1B as an starting point for this job. | NIWC | Closed | Portrayal GitHub #1. (AS 04SEP2023) - Recommend closing as this requierement is contained in the new IMO ECDIS PS. S-101PT12: Close - will be managed in the GitHub. | Awaiting test data. Alerts generated from horizontal uncertainty has been prototyped and demonstrated.
PortSG-03 | Quality of Bathymetric Data - Visualization of Vertical and Positional Uncertainties | (DCEG and FC): Add new boolean attribute displayUncertainties to the following feature types: Sounding, Underwater Rock, Wreck and Obstruction. | JW/KHOA | Completed | Portrayal GitHub #1. DCEG Completed but requires development of new portrayal in order to test behaviour (see PorSG-01).
PortSG-04 | Fairway portrayal | Submit full proposal using the online ''S-101 Portrayal request from". | Norway | Completed | Portrayal GitHub #2. Recommend close - Norway to submit new proposal (New Action to be endorsed by S101PT8) // (AS-16MAR22) -Refer to PortSG-39.
PortSG-05 | Light Sector Portrayal - Sector Light Length | Provide updated version of the PC to Norway. | NIWC | Completed | Portrayal GitHub #3. Recommended to close.
PortSG-06 | Light Sector Portrayal - Sector Light Length | Report lessons learnt and/or submit full proposal to S-101PT7. | Norway | Completed | Portrayal GitHub #3. Recommended to close. New actions to be endorsed by S101PT8. // (AS-16MAR22) -CLOSED - Refer to PortSG-40.
PortSG-07 | Quality of Bathymetric Data and ECDIS Performance (Management of Temporal variation) | DCEG subWG to discuss and present to the S101PT re-modelling proposals in support of the temporal downgrading of QoBD. | JW | Completed | Portrayal GitHub #4. Completed but 2 modeliing options available in DCEG - need testing to decide which one to retain.
PortSG-08 | Grouping of Soundings in ENC Updates | Add guidance in new version of the DCEG. | JW | Completed | Portrayal GitHub #5. New guidance added at DCEG clause 11.3.1.
PortSG-09 | Grouping of Soundings in ENC Updates | Inform the ENCWG chair so this guidance can be considered for inclusion in the UOC. | JW | Closed | Portrayal GitHub #5. (AS-16MAR22) - Added new PortSG action (# 73) to develop Test data (ENC + ENC Update). (AS - 04SEP2023) - Overtaken by events? Discussion moved to the use of UpdateInformation. S101PT to confirm. Status updated to 'Closed'. | Need clarity on CONOPS for UpdateInformation
PortSG-10 | Portrayal Catalogue 1.1.1_Endorsement and update to registry | Upload latest draft of the PC to the new Github repository. Any futher changes to be timely reflected and tacked in this location. | NIWC | Completed | Portrayal GitHub #6.
PortSG-11 | Portrayal Catalogue 1.1.1_Endorsement and update to registry | Publish 'official' PC version 1.n.n. | IHO Sec/KHOA | CLOSED | Portrayal GitHub #6. (AS-16MAR22) - CLOSED - 'Official' version now managed in Github space under IHO domain. The publication of a new version in IHO Registry is on hold until PC is complete and aligned with FC 1.1.0. | Close on confirmation that desired portrayal is to use new CATZOC attribute and implement S-52 portrayal.
PortSG-12 | Quality of Bathymetric Data - Decide portrayal requirements | Update PC draft as required. | NIWC | Completed | Portrayal GitHub #7. Recommend close as decision on using S-52 portrayal has been made and endorsed. (AS-16MAR22) - Decision on using S-52 portrayal has been made and endorsed. NIWC to CLOSE when PC is updated.
PortSG-13 | Quality of Bathymetric Data - Decide portrayal requirements | DCEG subWG to update QoBD modelling as required. | JW | Completed | Portrayal GitHub #7.
PortSG-14 | Portrayal of shared edges | Test proposed solution and report back to S-101PT7. | NIWC | Completed | Portrayal GitHub #8. Leave as is. New actions to be endorsed by S101PT8. (AS-16MAR22) - CLOSED - Refer to PortSG-45 & 46. | Recommend close
PortSG-15 | Id values in portrayal catalogues | Add xmlID values to the registry. | JW | Closed | Portrayal GitHub #9. New actions to be endorsed by S101PT8. (AS-16MAR22) - On-Hold - Pending result of action PortSG-47. (AS 04SEP2023) - Status changed to 'Closed'. Refer to PortSG-47.
PortSG-16 | Id values in portrayal catalogues | Update PC with xmlID values. | NIWC | Closed | Portrayal GitHub #9. New actions to be endorsed by S101PT8. (AS-16MAR22) - On-Hold - Pending result of action PortSG-47. (AS 04SEP2023) - Status changed to 'Closed'. Refer to PortSG-47. | Awaiting completion of PrtSG-15
PortSG-17 | Light descriptions with unknown lightCharacteristic | Update PC to support the interpretation endorsed by the S101PT. | NIWC | Completed | Portrayal GitHub #10. Recommend to close. | Recommend close: * Mariners groups have been removed from the PC * Recommend notify (Julia / Raphael?) to update S-98 with guidance for OEMs: * Application developers are responsible for implementing support for mariners / manufacturers features - Using viewing groups as specified in C-10.5.5 - Using viewing group layers as specified in C-10.5.6 - Using independent 'Mariners' display modes as specified in C-10.6
PortSG-18 | S-101 PC and Mariners viewing groups | Remove mariner's viewing groups/ viewing group layers from S-101 PC. | NIWC | Completed | Portrayal GitHub #12. | S-98? See above.
PortSG-19 | S-101 PC and Mariners viewing groups | Liaise with S-100WG Chair and IEC T80 representative to resolve this issue outside the S-101 PC. | NIWC | Closed | Portrayal GitHub #12. Confirm with NIWC who is going to submitt S-98 change proposal. (AS-16MAR22) - NIWC to confirm S-98 change proposal has been submitted and that the recommendations have been addressed by the S100WG. (AS 09SEP2023) - Decision made to exclude Mariners VG and dedicated symbology from S101PC. NIWC has an open issue to include a related note in S-98 highlighting that the responsibility of implementing MO in ECDIS is on OEMs https://github.com/S-101-Portrayal-subWG/Working-Documents/issues/135 S-101PT12: Close - will be managed in the GitHub. | Added issue #135, #136
PortSG-20 | SY(CHDATD01) symbol has no portrayal parameters. | Portrayal Register - Add new Viewing Group Layer to manage the independent selection (on/off) of SY(CHDATD01). | JW | Completed | Portrayal GitHub #13. JW to update status (New action for endorsement of S101PT). (AS-16MAR22) - CLOSED - Refer to PortSG-48. | Requested feedback from Furuno and 7cs: * 7cs: no response * Furuno: Always uses mariner selected date(s)
PortSG-21 | SY(CHDATD01) symbol has no portrayal parameters. | Implement changes to on-shore ECDIS. | NIWC | Completed | Portrayal GitHub #13. Still pending awaiting on resolution of action above. (AS-16MAR22) - Dependent on PortSG-48. | Complete
PortSG-22 | Guidance on Date dependent and Safety check | Report back to S-101PT7. [Note that S-64 3.0.0 expanded the test data for this purpose.] | NIWC | Completed | Portrayal GitHub #14. New actions to be endorsed by S101PT8. (AS-16MAR2) - CLOSED - Refer to PortSG-49.
PortSG-23 | IEC 61174 (4.18) Default selector requirement | Inform the ENCWG chair. | TR | Completed | Portrayal GitHub #15. Completed 17/11/21.
PortSG-24 | IEC 61174 (4.18) Default selector requirement | Propose S-98 amendment to S-100WG chair. | TR | Completed | Portrayal GitHub #15. Completed 17/11/21. | Recommend close - PC has been updated so that viewing group layers controlling text are not included in any catalogued display mode (e.g. text groups are not in base, std, or other)
PortSG-25 | IEC 61174 (4.18) Default selector requirement | Update PC and on-shore ECDIS as required. | NIWC | Completed | Portrayal GitHub #15. | Recommend close and address in S-98
PortSG-26 | OEM guidance on application of changes to viewing groups | Submit paper to S-100WG recommending update to S-98 Annex C. | NIWC | Completed | Portrayal GitHub #16. NIWC to update on status of S-98 change proposal. | Change proposal accepted at S-100WG6.
PortSG-27 | S-101 Feature dependency issues | Submit change proposal to TSM8/S-100WG6 recommending update to S-100 Part 9a. | NIWC | Completed | Change proposal accepted at S-100WG6. | Awaiting feedback
PortSG-28 | Independent Mariner Selections | Report back to S-101PT7. [Note that S-64 3.0.0 expanded the test data for this purpose.] | NIWC | Completed | Portrayal GitHub #18. New actions to be endorsed by S101PT8. (AS-16MAR22) - CLOSED - Refer to PortSG-50.
PortSG-29 | ENCWG 'ENC Display subWG' | Submit portrayal change proposals identified by the ENC Display Sub-Group to the S-101PT using the online 'S-101 Portrayal request form'. | CM | CLOSED | Portrayal GitHub #19. New actions to be endorsed by S101PT8. (AS-16MAR22) - Replaced with action PortSG-51.
PortSG-30 | ECDIS Chart 1. | Seek volunteers (or HSSC funding) to develop the first 'S-101 ECDIS Chart 1' (or ECDIS Chart S-101) version as per the requirements listed in S-52 Ed 6.1.1 (3.1.4) and S-52 PL Part I (17.7 & 18.2). | TR | Closed | Portrayal GitHub #20. 07/02/24 (SG Lead): Task now allocated to Test datasets sWG. See action S101PT11-15.
PortSG-31 | ECDIS Chart 1. | Inform decision and way forward to S-100WG Chair. | TR | Closed | Portrayal GitHub #20. 07/02/24 (Chair): In progress with IIC see Action S-101PT11-15; propose close action.
PortSG-32 | S-101 ECDIS Performance requirements log. | Create, update and present S-101 ECDIS performance requirements' log prototype to S-101PT7. | AS | CLOSED | Portrayal GitHub #21. Still In Progress although it may need to be closed after S101PT8. (AS-16MAR22) - CLOSED - Refer to PortSG-37 & 52.
PortSG-33 | Light Sector portrayal - Sector arc extension | Continue discussions in Github and report final recommendation at S-101PT9. | AS JW | Completed | Portrayal GitHub #26. (AS-16MAR22) - Discussion continues within the DCEG subWG. Refer to PortSG-53. (AS 04SEP2023) - Status changed to 'Completed'.
PortSG-34 | Review new portrayal requirements related to S-101 new/remodelled features and attributes | Finalise review by 04 April 2021; seek Portrayal Sub-Group approval and liaise with NIWC and KHOA as required to update PC as required. Report progress to S-101PT7. | AS | Completed | Portrayal GitHub #23. Recommend to close once new actions are endorsed by S101PT8. Final list of actionable entries uploaded to Github space. Each entry probably becomes a new individual action item (?). (AS-16MAR22) - Actions endorsed by S101PT and actionable entries have been migrated into a consolidated list of PC changes ordered by Feature & Attribute/Feature.
PortSG-35 | Small Craft moorings - Update symbology | Report progress at S-101PT7. | AS | Completed | Portrayal GitHub #28.
PortSG-36 | flipBearing attribute for TextPlacement | Report progress at S-101PT7. | AS | Completed | Portrayal GitHub #29. New actions to be endorsed by S101PT8. (AS-16MAR22) - Way forward agred by the portratal subWG. Passed to DCEG for implementtaion of changes. Refer tp PortSG-54.
PortSG-37 | ECDIS Portrayal and Performance log | Create new Github issues for each entry in the 'ECDIS Portrayal and Performance log'. | AS | Completed | Portrayal GitHub #21.
PortSG-38 | Quality of Bathymetric Data - Visualization of Vertical and Positional Uncertainties | Produce S-101 test datasets as required to support development and testing of PortSG-01 | Norway (coordinate with TDS subWG) | Closed | Portrayal GitHub #1. (AS 04SEP2023) - Focus is on A&I. Visualisation needs more discussion. 07/02/24 (Chair): Ongoing within TDS SG. S-101PT12: Close - will be managed in the GitHub.
PortSG-39 | Fairway Portrayal | Prepare new portrayal Fairway proposal without the constraints DF-ECDIS may impose to the proposed solution. | Norway | Closed | Portrayal GitHub #2 (AS 04SEP2023) - Norway to confirm willingness to proceed as planned in the GitHub issue. If not, recommend closing this action and the related GitHub issue. S-101PT12: Close - will be managed in the GitHub.
PortSG-40 | Light Sector Portrayal - Sector Light Length | Discuss amendments to DCEG to improve guidance on the use of this attribute and report back recommended changes to PC to the portrayal subWG. | JW | Completed | Portrayal GitHub #3 Amendments made to DCEG Ed 1.0.2. Further feedback required from NO and discussion at next Portrayal SG (AS 04SEP2023) - Implemented and tested. Status changed to 'Completed'.
PortSG-41 | Light Sector Portrayal - Sector Light Length | Pass recommendation for a new validation test that checks SLL <= valueOfNominalRange to S-101 Validation subWG | AS | Completed | Portrayal GitHub #3
PortSG-42 | Light Sector Portrayal - Sector Light Length | S-52 recommendation that lights sectors from Lights that sit outside the ECDIS display area but are in range should be visible, to become a mandatory ECDIS performance requirement. Add requirement to 'S-101 ECDIS Portrayal and Performance' log and create dedicated Github issue. Also submit change request to S-98 Part C. | AS | Closed | Portrayal GitHub #3. Change request form submitted to S100WG6 (Feb 2022). Decision S-100WG6: This proposal needs to be discussed by the ENCWG so as a harmonised solution is developed for S-57 ECDIS such that a consistent solution is implemented across S-57 and S-100 ECDIS (S-101PT Chair and Vice-Chair, HP, HB, RF). (AS 04SEP2023) - Not sure about this one. How do we want to move this forward? Is it possible to implement this performance requirement while in DF-ECDIS?? 07/02/24 (SG Lead): Update from NIWC required - Has it been implemented in PC 1.2.0 or is it awaiting discussions at the ENCWG level?? S-101PT12: Close - will be managed in the GitHub.
PortSG-43 | Quality of Bathymetric Data and ECDIS Performance (Management of Temporal variation) | Compile S-101 ENC using FC 1.0.1 in order to support the testing of the downgrading of QoBD using the 2 modelling options described in the corresponding DCEG version. | TR (TDS subWG) | Closed | (AS - 04SEP2023) - Ctreated new issue in TDS GitHUb space. https://github.com/iho-ohi/S-101-Test-Datasets/issues/57 07/02/24 (Chair): Ongoing within TDS SG. S-101PT12: Close - will be managed in the GitHub.
PortSG-44 | Portrayal Catalogue versioning and change management practices. | Organise VTC meeting to discuss PC versioning and best practices regading the use of terms such as 'official'or 'master' versions. | AS, JW, TR, NIWC | Completed | Portrayal GitHub #6
PortSG-45 | Portrayal of shared edges | Develop anchorage area 'combined' complex linestyle for testing. | KHOA | Completed | Portrayal GitHub #8
PortSG-46 | Portrayal of shared edges | Amend portrayal instructions to use new complex linestyle symbology (PortSG-45) when two adjoining AnchorageArea features adjoin and share and edge. Report findings. | NIWC | Closed | (AS - 04SEP2023) - New Issue - https://github.com/S-101-Portrayal-subWG/Working-Documents/issues/100 | Change proposal submitted to S-100WG7 was deferred. No further action required of PSWG at this time.
PortSG-47 | Id values in portrayal catalogues | Discuss xmlid with KHOA's development team in order to get a better understanding of its format and its use within the IHO Registry database. Once more information is gathered, further discuss best way forward with key stakeholders. | JW, JB, KHOA (first) JW, DG, AS, HB, HA (second) | Closed | Portrayal GitHub #9 (AS - 04SEP2023) - Also tracked via GitLab Issue (KHOA) since April 2023. S-101PT12: Close - will be managed in the GitHub. | Awaiting status
PortSG-48 | SY(CHDATD01) symbol has no portrayal parameters | Use the same portrayal context parameters than the 'i' symbol and allocate a new Viewing Group (31032). Commence process to update the IHO Registry. | AS | Completed | Portrayal GitHub #13
PortSG-49 | Guidance on Date dependent and Safety check | Submit S-98 Part C change proposal recommending more clear direction on the implementaion by OEMs, of mariners'selected dates and Route checking functions at both, route monitoring and route planning phases. | NIWC, AS | Completed | Portrayal GitHub #14. Change request form submitted to S100WG6 (Feb 2022). S-100WG6: Agreed for implementation in S-98 Edition 1.1.0. Further work to be done in conjunction with the ENCWG and a revised Change Proposal submitted.
PortSG-50 | Independent Mariner Selections | Schedule a workshop to discuss the implementation of independent mariners selections in DF-ECDIS and beyond. NIWC to chair workshop and prepare draft Agenda and proposed dates. S-101PT Chair to submit the invitation to OEMs and S100WG. | TR, DG | Time Expired | Portrayal GitHub #18 | Based on the disucssion I think this is time expired.
PortSG-51 | ENCWG 'ENC Display subWG' | ENC display subWG lead to seek volunteers and organise a focused meeting to identify valid S101 portrayal proposals and create Github issues for each of them in the S101 Portrayal subWG space. | CM | Completed | Portrayal GitHub #19. (AS - 04SEP2023) - Status amended to 'Completed'.
PortSG-52 | S101 ECDIS Performance requirements log | Seek decision from S100WG chair on the authority to approve amendments to S-101 portrayal/alarms&Indications that conflict with S-52.(decision must represent IHO Sec. view). | TR | Completed | Portrayal GitHub #21 | Propose close action noting paper to PT11.
PortSG-53 | Light Sector portrayal - Sector arc extension | Irrespective of SLL behaviour (still under discussion in DCEG subWG), implement sector arcs behaviour decisions in PC. This are: sector arcs must extend with SLL and 'double arcs' are not required. | NIWC | Completed | Portrayal GitHub #26 (AS 04SEP2023) - Status chnaged to 'Completed'. | PC GitHub #10
PortSG-54 | flipBearing attribute for TextPlacement | DCEG subWG to implement bearing-distance concept in DCEG and discontinue flipBearing. Also discuss need to retain textJustification and the value of extending textType to accommodate other entries. | JW | Completed | Portrayal GitHub #29
PortSG-55 | Restricted Area Navigable vs Restricted Area Regulatory | Seek resources to produce ad-hoc S-101 native test data as required (Volunteers or use Special Projects Fund) | AS TR (TDS subWG) | Completed | Portrayal GitHub #31. (AS-16MAR22) Test Datasets subWG stood up by TR and IHO special funds made availabe to engage contractor.
PortSG-56 | Restricted Area Navigable vs Restricted Area Regulatory | * In a 'branch' of the S101 PC, add RESARE04 to Restricted Area Regulatory to support testing. | NIWC | Completed | Portrayal GitHub #31 | Implemented in main branch
PortSG-57 | Restricted Area Navigable vs Restricted Area Regulatory | * Create test data that contains all possible CSP RESARE04 attribute combinations. Compare portrayal results using S-52 and S101 PC. | TR (TDS subWG) | Closed | Portrayal GitHub #31 (AS 04SEP2023) - This may have been overtaken by events (merging or Regulatory and Navigational features). Close this issue? S-101PT12: Close - will be managed in the GitHub. | Note PT11 paper (08.5) is this still required?
PortSG-58 | Restricted Area Navigable vs Restricted Area Regulatory | Remove Restricted Area Regulatory from a 'branch'of the A & I catalogue. Pending confirmation this action will not break any IMO regulation. If approved to proceed, it will require changes to S-98 Part C (14.9.8) regarding the 'Detection of areas for which special conditions exist'. | NIWC | Completed | Portrayal GitHub #31 | Implemented in main branch. Recommend track any required S-98 changes under a new GitHub issue.
PortSG-59 | Restricted Area Navigable vs Restricted Area Regulatory | Allocate and register new Viewing Group for Restricted Area Regulatory. Remove this feature from current VG. | AS, NIWC | Completed | Portrayal GitHub #31
PortSG-60 | Masking of edges by portrayal rules | DCEG subWG to review masking recommendations in section 2.5.10 and narrow them down to those not currently performed by ENC production tools. | JW | Closed | (AS 04SEP2023) - Amended GitHub reference. PsWG issue is closed and the discussions continue under https://github.com/iho-ohi/S-101-Documentation-and-FC/issues/26 S-101PT12: Close - will be managed in the GitHub. | For S-101PT11. 07/08/23: Refer to S-101 Documentation and FC Github Issue #26.
PortSG-61 | New symbology - Rapids | Email summary of discussions to Canada and Russia (only encoders of Rapids (P) identified by RENCs) and ask for preferred way forward (accept removal of Point as an allowable geometric primitive or submit proposal for new symbology). | AS | Completed | Portrayal GitHub #33
PortSG-62 | Display of the seaward edge of mangrove in intertidal areas | Request the DCEG subWG to discuss discontinuing categoryOfVegetation = 7 & 21 and expand categoryOfObstruction to include 'mangroves'. | JW | Completed | Portrayal GitHub #34. Changes implemented in DCEG 1.0.2
PortSG-63 | Limitations in display of Sloping Ground | Remove categoryOfSlopingGround= 5 & 7 from list of valid attribute values. | JW | Completed | Portrayal GitHub #35 S-101PT9: paper dubmitted to NCWG8 for discussion. Further evaluation dependant on discussion outcomes. (AS 04SEP2023) - Changed status to 'Completed'.
PortSG-64 | Current non-gravitational | Remove Curve and Surface from the list of valid geometric primitives for this feature. | JW | Completed | Portrayal GitHub #36 Change implemented in DCEG 1.0.2.
PortSG-65 | Virtual Aids to Navigation | IALA and CSMART representtaives to discuss the topic more broadly with their organisatiosna and present proposal via Github. | Antonio, Gottorm | Completed | Portrayal GitHub #37. Both inputs added to Github. (AS-16MAR22) - Requires final decision by subWG and endorsement by S101PT. (AS 04SEP2023) - Changed status to 'Completed'.
PortSG-66 | Signal generation | Update LightFlareAndDescription rule to add (man) when signalGeneration=3, 5, or 6 (by hand, radio activated, or call activated). For FogSignals , add "(man)" next to the symbol (FOGSIG01). | NIWC | Completed | Portrayal GitHub #38 | Complete (PC GitHub #52)
PortSG-67 | Signal generation | Include new abbreviation 'man' in S-98 Annex C (Table 36). Submit change proposal to S100WG | AS | Completed | Portrayal GitHub #38. Change request form submitted to S100WG6 (Feb 2022). S-100WG6: Decision was that the abbreviations need to be approved by NCWG before they can be included in S-98. However because this abbreviation is already in S-4, this should be OK. (AS - 26/10/22) - Proposal submitted to NCWG8 in November 2022. (AS 04SEP2023) - Changed status to 'Completed'.
PortSG-68 | Measured distance value | Develop new SVG symbol (DISMAR06?) identical to DISMAR05 but in CHMGD colour. Submit registration request to IHO Registry manager. | KHOA, AS | Completed | Portrayal GitHub #39
PortSG-69 | Measured distance value | Update DistanceMark rule to display text string made of distanceUnitOfMeasurement followed by waterwayDistance. Same style than the one used in InlandENCs but in CHMGD colour. | KHOA, AS | Completed | Portrayal GitHub #39
PortSG-70 | Measured distance value | DCEG subWG to continue discussion about DistanceMark modelling options. Discuss options around the best encoding practice for DistanceMark on physical structures (e.g. 2 associated features or complex attribute on each possible supporting structure ?). Also consider new bolean attribute (displayDistance?) for measuredDistanceValue to have control of the textual display on screen. Distance marks 'not physicaly installed' would be the only ones encoded using the feature DistanceMark. In this case the recommendation would be to have a new dedicated VG for this feature. This way both, the symbol (magenta circel) and the text would be turn On/Off simultaneously. The circle without the text does not make sense to me - all ON or all OFF). | JW | Completed | Portrayal GitHub #39 Amendments made to DCEG 1.0.2. Revised DCEG guidance to be discussed at next Portrayal SG meeting. (AS 04SEP2023) - Changed status to 'Completed'.
PortSG-71 | Measured distance value | Discontinue DISMAR03 and DISMAR04 SVG symbols. Remove from S101 PC and amend status in IHO Registry | NIWC, JW | Completed | Portrayal GitHub #39 | Complete (PC GitHub #217)
PortSG-72 | Measured distance value | Include abrreviations for Statute miles and Yards in S-98 Annex C (Table 36). Submit change proposal to S100WG. | AS | Completed | Portrayal GitHub #39. Change request form submitted to S100WG6 (Feb 2022). Decision S-100WG6: To be submitted to the NCWG for these abbreviations to be included in S-4 before they can be considered for ECDIS portrayal. (AS - 26/10/22) - Proposal submitted to NCWG8 in November 2022. (AS 04SEP2023) - Changed status to 'Completed'.
PortSG-73 | Grouping of Soundings in ENC Updates | Compile S-101 ENC and ENC update (both grouping and not grouping new/amended soundings); load in On-Shore ECDIS and check behaviour. | TR (TDS subWG) | Closed | Portrayal GitHub #5. (AS-16MAR22) - New action added. (AS - 04SEP2023) - Overtaken by events? Discussion moved to the use of UpdateInformation. S101PT to confirm. Status updated to 'Closed'. | Not actioned.