## Sheet1
S-101 Change Tracker post 2.0.0 |  |  | Last Updated: 23 December 2025
Impact
Serial | Paper/Issue | Meeting | Description | Status | Considered by ENCWG | S-57/S-52 Update | Considered by NCWG | S-4 Update | DPS | Registry | DCEG | FC | PC | VCs | S-164 | TDS | Issue
1 | Ongoing change | N/A | Update DSID - PRSP and PRED subfields (Annex B) | Applied. To be confirmed when Edition number finalised. | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | ? | ?
2 | Ongoing change | N/A | Update S-101 version and version date | Applied. To be confirmed when Edition number finalised. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | ? | Y
3 | S-101PT14-6.4 | PT14 | Changes to submarine cable symbology | Issues open to progress | ENCWG9 | S-52 5.0/YYMMDD | Seek confirmation of no change to S-4. | N/A | N | Y | N | N | Y | ? | Y | N | https://github.com/S-101-Portrayal-subWG/Working-Documents/issues/184
4 | S-101PT14-6.4 | PT14 | Changes to cable area symbology | Issues open to progress | ENCWG9 |  | Seek confirmation of no change to S-4. | N/A | N | Y | N | N | Y | ? | Y | N | Changes to Cable Area symbology (S-52 5.0.0) · Issue #183 · S-101-Portrayal-subWG/Working-Documents
5 | S-101PT14-6.4 | PT14 | Changes to overhead cable symbology | Issues open to progress | ENCWG9 |  | Seek confirmation of no change to S-4. | N/A | N | Y | N | N | Y | ? | Y | N
6 | 193 | PT15 | Add Silo Tank to association for Air Obstruction Light | Agreed at PT15 Applied to draft | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N | https://github.com/iho-ohi/S-101-Documentation-and-FC/issues/193
8 | S-101PT15-6.2 | PT15 | Text Pattern and Precision | Text patterns (RegEx Expressions) discussed and approved at S-101PT16. Changes applied to DCEG for Edition 2.1.0. Precision clarified in S-100 and is in agreement with format as defined in S-101 (NFA). | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N
9 | S-101PT15-6.1 | PT15 | Uncertainty in S-101 | Refer to Actions from S-101PT16. In progress. | N/A | N/A | N/A | N/A |  | ? | Y |  |  |  |  | Y
10 | 195 | PT15 | Remove unit Knots from simple attribute speed limit. | Agreed at PT15 Applied to draft Registry action needed. Registry action completed 08/05/25. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N | Attribute Speed Limit should not have UOM Knots in Feature Catalogue · Issue #195 · iho-ohi/S-101-Documentation-and-FC
11 | 194 | PT15 | RadarStation could not be related to landmark | Agreed at PT15 Applied to draft | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N | RadarStation could not be related to landmark (association) · Issue #194 · iho-ohi/S-101-Documentation-and-FC
12 | Email correspondence with Peter Duguid 05/03/25 | DCEG SG | Value range closure and guidance for the population of the Meta attribute update number does not reflect that an Update Information feature(s) may be included in a New Edition dataset (update number = 0). | Draft changes made to DCEG. For consideration of DCEG Sub-Group. Change made to GI Registry. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | ? | N
13 | Email correspondence with Frank Hippman 12/03/25 | DCEG SG | Add Mooring Buoy [and Obstruction] to list of structures that have not been established specifically as an aid to navigation | Draft changes made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N
14 | Email correspondence with Frank Hippman 12/03/25 | DCEG SG | Add new guidance to encode buoys that have primary purpse as a mooring buoy using the Mooring Buoy feature; and use attribute colour to encode purpose if also used as a navigational aid | Draft changes made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
15 | 61 | PT15 | Add note stating that Aliases are to be retained in the S-101 FC until the end of the dual-fuel implementation period. | Agreed at PT15 Applied to draft | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | N | N
16 | 179 | PT15 | Amend Comment entry for DSID - DSEC sub-field. | Draft changes made to DCEG. For consideration of DCEG Sub-Group. Changes approved 28/05/25. | N/A | N/A | N/A | N/A | Y | N | N | N | N | ? | N | N
17 | 176 | PT15 | Amend Comment entry for CRSH - CRNM and VDAT - DTNM sub-fields. Amend Value entry for VDAT - DTID sub-field. | Draft changes made to DCEG. For consideration of DCEG Sub-Group. Changes approved 28/05/25. | N/A | N/A | N/A | N/A | Y | N | N | N | N | ? | N | N
18 | 167 | PT15 | Amend Comment entry for COCC - NCOR, SECC - NSEG and CCOC - NCCO sub-fields. | Draft changes made to DCEG. For consideration of DCEG Sub-Group. Change approved by S-100TSM. | N/A | N/A | N/A | N/A | Y | N | N | N | N | ? | N | N
19 | 218 | DCEG SG | Correct encoding guidance for seabed material extraction areas from categoryOfProductionArea = 13 (seabed material extraction area), which does not exist. | Draft change made to DCEG at clause 16.7.2 (corrected to categoryOfProductionArea = 5). For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | ? | N
20 | 466 | Por SG | Consistency with S-52 Ed 4.0(.4). Refer to email correspondence 26-27/03/25. | Issue open to progress. | N/A | S-52 PL Ed 4.0(.4) | N/A | N/A | N | N | N | N | Y | N | ? | ?
21 | 85 | PT15 | Improved guidance for encoding the TidalStreamPanelData feature. | Draft change made to DCEG. For consideration of DCEG Sub-Group. Change approved 28/05/25. Any further changes to be identified as normal course of business. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
22 | Email from Christina Ulrich 17/04/25. | DCEG SG | Clarify that the value to be populated for “system” attribute defaultClearanceDepth on features that are within or partly within a DepthArea or DredgedArea feature having an unknown value for the attribute depthRangeMinimumValue follows the same rule as for features that are within or partly within an UnsurveyedArea feature. | Draft change made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
23 | Email from Gert Morlion 28/04/28. | DCEG SG | Amend the term "None" for identifying no geometry as an allowable geometric primitive for S-101 features to "No Geometry" to be consistent with S-100. | Draft change made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
24 | Secretariat observations | DCEG SG | Remove redundant duplicated last row of Table 30-2. | Draft change made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
25 | 166 and Email from Ben Hazelgrove 16/05/25 | DCEG SG 28/05/25 | Correct CRNM vertical component subfield for the CRSH field in the compound CRS encoding examples at tables 5-1 and 5-2 to remove the text “Depth – “. | Draft change made to Main Doc. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | Y | N | N | N | N | ? | ? | N
26 | 148 | DCEG SG 28/05/25 | Clarify that an aggregation or composition may include only a single component (containee) within the “container” due to the splitting of the aggregation or composition at the ENC dataset limits (NOTE: Applied for Fairway Aggregation for Edition 2.0.0 - needs to be applied for other associations.) | Agreed at DCEG SG meeting 28/05/25. Draft change made to DCEG. For consideration of S-101PT. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | ?
27 | 182 See Serial 63 below. | DCEG SG 28/05/25 | There are two ways to encode ferry cables in S-101 after the introduction of the new value 7 (ferry) to attribute categoryOfCable. Suggestion is to remove this new value and revert to encoding corresponding to S-57 (encode using FerryRoute feature). Further discussion between S-101PT Chair and Secretary regarding retention of removed modelling for backward compatibility and how this is to be indicated/described in the DCEG. | Agreed at DCEG SG meeting 28/05/25. Draft changes made to DCEG. For consideration of S-101PT. Papers in preparation for S-101PT16 and possibly S-100WG10. | N/A | N/A | N/A | N/A | N | N | Y | Y(?) | Y(?) | ? | ? | ?
28 | 189 | DCEG SG 28/05/25 | Clarify the encoding of the extent of the geometry of Bridge features covering their components so as to avoid possible conflict. | Agreed at DCEG SG meeting 28/05/25. Draft change made to DCEG. For consideration of S-101PT. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
29 | 207 and email from Richard Fowle 23/05/25. | DCEG SG | Add topmark as an allowable complex attribute for feature MooringBuoy. | Use case supplied by DK. Draft change made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | Y | Y | Y | Y | N | N | Y
30 | Email from Christina Ulrich 29/07/25 | DCEG SG | Corrected binary logic for Boolean type attribute value False from (2) to (0). | Correction required and applied at DCEG clause 2.4.2. For approval of S-101PT. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
31 | 216 | PT16 | Correct erroneous listing of type for attributes soundingDistanceMaximum and soundingDistanceMinimum from Real (RE) to Integer (IN) at DCEG clause 3.11. | Correction required and applied at DCEG clause 3.11. For approval of S-101PT. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
32 | Email from Jonathan Pritchard 12/08/25. | PT16 | Amend reference to S-101 Dataset Loading and Display (Rendering) Algorithms to S-98 Appendix E. | Correction required to align with document structure in S-98 Edition 2.0.0 and applied at Main document clauses 4.7, 4.7.1 and 4.7.2. For approval of S-101PT. | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | N | N
33 | 210 | PT16 | Amend subfield comment for the SMAX subfield of the SPAS field to specify that a NULL value is {232-1} and not {0}. | Correction required to align with S-100 Edition 5.2.0 (clause 10a-7.3.2.3). Applied at Main document clauses B-5.1.31 and B-6.1.30. For approval of S-101PT. | N/A | N/A | N/A | N/A | Y | N | N | N | N | Y | ? | ?
34 | 213 | PT16 | Amend multiplicity of sub-attribute leastDepthOfDetectedFeaturesMeasured and associated guidance from mandatory to conditionally mandatory. | Correction required to align the data model with the corresponding guidance. Changes applied at DCEG clauses 3.8 and 3.11. | N/A | N/A | N/A | N/A | N | N | Y | Y | N | Y | N | N
35 | 217 | PT16 | Amend definition for value 63 (wave recorder) for attribute categoryOfSpecialPurposeMark to allow for wave recorders attached to daymarks to be taken into account. | Correction required to allow for wave recorders attached to daymarks to be taken into account. Changes applied at DCEG clause 27.67. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N
36 | 219 | PT16 | Add missing arrows from Bridge text box to feature. Amended text in Bridge text box to be consistent with changes made as a result of resolution of Issue #189. | Correction required for consistency. Changes applied at DCEG clause 6.6. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
37 | Email from Liz Hahessy 14/08/25 and IHO Sec response 16/08/25. | PT16 | Correct S-57 acronym reference HORCLR throughout to be italic for attribute horizontalClearanceValue and upright for horizontalClearanceWidth. | Correction required for consistency. Changes applied throughout DCEG. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
38 | 223 | PT16 | Amend lower bound multiplicity value for complex attribute tidalStreamValue from 1 to 13 - there must be a minimum of 13 values populated for the tidalStreamPanelValues complex attribute to be valid. | Clarification required for informing S-101 validation and for logical consistency. Change applied at clause DCEG 10.5. | N/A | N/A | N/A | N/A | N | N | Y | Y | N | N | N | Y?
39 | 222 | PT16 | Correct S-4 reference for physical and virtual AIS from B-480-484 to B-489. | Correction required to align with latest Edition of S-4. Change applied at DCEG clauses 21.2.1 and 21.3.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
40 | 54 | PT17 | Amended guidance for the encoding of QualityOfBathymetricData features covering land areas from “must not” to “should not”. | Correction required to align with proposed change to S-158:101. Change applied at DCEG clause 3.8.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | Y?
41 | 190 | PT17 | Removed guidance related to spatial accuracies related to curve features being prohibited. | Correction required to align with first sentence of paragraph. Change applied at DCEG clause 2.4.7. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | Y | Y?
42 | Email from Christian Mouden 24/09/25 and IHO Sec response 25/09/25. | PT17 | Clarified that the fixed scale values defined for minimumDisplayScale and optimumDisplayScale only must be taken from the values in Table 3-1 of the S-101 Main document; and scale value for maximumDisplayScale can be any numeric value. | Correction required to align with guidance in S-101 DCEG clause 3.5 (maximumDisplayScale can be any numeric value). Change applied at Main document clause 4.6. | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | N | N
43 | Email from Christian Mouden 30/09/25 and IHO Sec response 02/10/25. | PT17 | Clarified that the display of the “gross overscale” pattern in ECDIS is applied in accordance with S-98 Main document, clause 12.3.3. | Change applied at Main document clause 4.6. | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | Y | Y
44 | Email from Christian Mouden 25/09/25 and IHO Sec response 30/09/25. | PT17 | Clarified that the optimumDisplayScale for the entire dataset is defined in S100_DatasetDiscoveryMetadata; and that where a dataset has multiple DataCoverage features, the value for maximumDisplayScale populated in the S100_DatasetDiscoveryMetadata must be an empty (null) value. | Clarification applied at Main document clause 4.5.3. | N/A | N/A | N/A | N/A | Y | N | N | N | N | Y | Y | Y
45 | Email from Heaxagon Geospatial (via Yong) 25/09/25. | PT17 | Various portrayal issues. | With Portrayal SG lead. | N/A | N/A | N/A | N/A | N | N | N | N | Y | N | N | Y?
46 | 208 | PT17 | Problem with multiplicities as defined in the Feature Catalogue - misinterpretation between the guidance in the DCEG. See also S-101PT16 Action 30. | Ongoing. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N | Feedback from DK supplied 25/09/25. Confirms consistency within the FC however multiplicities need to be corrected in the FC and clarifications required in the DCEG.
47 | Email from Ben Hazelgrove 03/10/25 and IHO Sec response 03/10/25. | PT17 | Issue with Validation Checks reporing an Error when soundings in a sounding group fall withinin different SoundingDatum features having the same vertical datum defined. | With Validation Checks SG Lead | N/A | N/A | N/A | N/A | N | N | Y? | N | N | N | N | Y
48 | GI Registry, Concept Register clarification proposal 09/10/25 | PT17 | Clarified definition for attribute category of restricted area code value 19 (waiting area) as proposed by the NIPWG on behalf of ITCPO/IHMA. | Clarification applied at DCEG clause 27.57. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N
49 | Email from Ruiran 20/10/25 and IHO Sec response 21/10/25. | PT17 | Clarified that the attribute verticalDatum applies only to the values populated for the populated vertical clearance(s). | Clarification applied at DCEG clauses 6.7.1, 6.8.1, 6.9.1, 6.10.1, 8.11.1 and 8.13.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
50 | Email from Ben Hazelgrove and IHO Sec response 22/10/25. | PT17 | Amended cardinality of attributes depthRangeMaximumValue and depthRangeMminimum value from optional (0,1) to conditional mandatory (0,1†) and added associated guidance. Amended associated S-57 attribute for depthRangeMaximumValue to include DRVAL1 where the Quality OfBathymetricData is also covered by a SweptArea; and amended the guidance for the population of depthRangeMaximumValue and depthRangeMinimumValue. | Clarification applied at DCEG clauses 3.8 and 3.8.1. | N/A | N/A | N/A | N/A | N | N | Y | Y | N | Y | N | N
51 | Email from Ben Hazelgrove 28/10/25 and IHO Sec response 30/10/25. | PT17 | Amended guidance for population of successive instances of sub-complex attribute fixedDateRange to specify that the dateStart an instance must be equal to the date immediately following the dateEnd of the previous instance. | Clarification applied at DCEG clause 3.8.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | Y
52 | Email from Ben Hazelgrove and IHO Sec response 27/11/25. | PT17 | Amended guidance for SpatialQuality associated to Obstruction, UnderwaterAwashRock or Wreck where attribute height or valueOfSounding is populated with an empty (null) value to state that sub-complex attribute verticalUncertainty must not be populated. | Clarification applied at DCEG clauses 13.4.1, 13.5.1, 13.6.1 and 24.5.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | Y?
53 | 234 | PT17 | Amended model for features CurrentNonNavigational and TidalStreamPanelData to replace complex attribute orientation with simple attribute orientationValue. | Revision applied at clauses 10.3 and 10.5. | N/A | N/A | N/A | N/A | N | Y | Y | Y | Y | Y | Y? | Y?
54 | 180 | PT17 | Expanded scope of definition to allow for the Structure/Equipment association to be used to associate features that are not intended as aids to navigation. | Clarification applied at DCEG clause 25.16. | N/A | N/A | N/A | N/A | N | N | Y | Y | N | Y | N | N
55 | 180 | PT17 | Added reference to clauses 18.1.and 18.2 for additional guidance on encoding the StructureEquipment association for aids to navigation. | Clarification applied at DCEG clause 25.16. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
56 | 192 | PT17 | Clarified the relationship between SoundingDatum and the Dataset Coordinate Reference System record for the dataset; and the requirement for multiple SoundingDatum features in a single dataset. | Clarification applied at DCEG clause 3.9.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
57 | 196 | PT17 | Indicated complex attribute multiplicityOfFeatures and its sub-attributes as an attribute that is no longer intended to be populated. Added new simple attribute number of features. | Revision applied at clauses 6.2, 27.131 and 29.12. | N/A | N/A | N/A | N/A | N | Y | Y | Y | Y | Y | Y | Y
58 | 196 | PT17 | Added new guidance for encoding of attribute numberOfFeatures, including intended ECDIS portrayal outcomes. | Clarification applied at DCEG clause 27.139. | N/A | N/A | N/A | N/A | N | N | Y | N | Y | N | Y | Y
59 | 199 | PT17 | Added new enumerate value 9 (painted) (from S-57) for attribute natureOfConstruction, for use for Daymark features only, with associated guidance. | Revision applied at clauses 20.14, 20.14.1 and 27.136. | N/A | N/A | N/A | N/A | N | N | Y | Y | N | N | N | N
60 | 208 | PT17 | Added new guidance related to the relationship between the multiplicities as described in the DCEG and as included in the Feature Catalogue, where a feature that is included in the “containee” end of the relationship can appear in more than one association instance of a named association. | Clarifications applied at clauses 25, 25.1,25.2, 25.4 and 25.13. | N/A | N/A | N/A | N/A | N | N | Y | Y | N | Y | N | Y
61 | 215 | PT17 | Added new allowable truncated date value for same day each month (no specific year or month - ------DD) for dateFixed and periodicDateRange attributes. | Revision applied at clause 2.4.8. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | Y
62 | 220 | PT17 | Added new guidance for provision of a visual indicator in ECDIS where the horizontal position and vertical accuracies encoded on a sounding, rock, obstruction or wreck indicates a lower accuracy than indicated by the underlying QualityOfBathymetricData Meta feature. | Clarifications applied at clauses 11.3.1, 13.3, 13.4.1, 13.5.1 and 13.6.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y? | N | N
63 | 182 | PT17 | Indicated value 7 (ferry cable) as a value for attribute categoryOfCable that is no longer intended to be populated. | Revision applied at clauses 14.2, 14.3 and 27.12. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | N
64 | 226 | PT17 | Indicated value 18 (bearing light) as a value for attribute categoryOfLight that is no longer intended to be populated. | Revision applied at clauses 19.2, 19.3 and 27.37. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | N
65 | 225 | PT17 | Amended/removed redundant INT1 references. | Clarifications applied at clauses 7.1, 20.5, 20.5.1 and 20.13.1. | N/A | N/A | N/A | N/A | N | Y | Y | N | N | N | N | N
66 | 228 | PT17 | Indicated value 21 (dredging area) as a value for attribute categoryOfRestrictedArea that is no longer intended to be populated. | Revision applied at clauses 17.8 and 27.57. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | N
67 | 228 | PT17 | Amended guidance for the encoding of “dredging areas” to be encoded using OffshoreProductionArea and not RestrictedArea. | Revision applied at clauses 14.6.1 and 16.7.2. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
68 | 231 | PT17 | Updated Table 2-8 for entry UpdateInformation to have attribute scaleMinimum set to the same value as the associated feature. | Revision applied at clause 2.5.9. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | N
69 | 233 | PT17 | Amended value for attribute categoryOfSignalStationTraffic code 9 from “dredging” to “dredging signal station”. | Revision applied at clauses 22.5 and 27.62. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N
70 | S-101PT16-07.1A | PT17 | Added guidance at Note 3 related to the depth accuracy component of the categories of Zone of Confidence that the formula used to determine depth accuracy is informative only. | Clarification applied at clause 27.74. | Y | Y | N/A | Y | N | N | Y | N | N | N | N | N
71 | S-101PT16-07.3 | PT17 | Mandated maximum string lengths for Text type simple attributes. | Revision applied at clauses 27.8, 27.79, 27.84, 27.89, 27.97, 27.104, 27.132, 27.133, 27.149, 27.153, 27.169, 27.170, 27.198, 28.21 and 28.22. | N/A | N/A | N/A | N/A | N | N | Y | Y | N | Y | N | Y?
72 | S-101PT16-07.3 | PT17 | Added text pattern (Regular Expression (RegEx) notation) for formatted text type attributes. | Revision applied at clauses 27.77, 27.98, 27.117, 27.129, 27.142 and 27.145. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | Y | N | Y
73 | 89 (S-101 Validation Checks) | PT17 | Added new guidance for the encoding of areas of the Contiguous Zones, EEZs or Territorial Seas of adjoining Coastal States that are in dispute. | Clarification applied at clause 16.2.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | N
74 | Email from Peter Duguid 19/12/25. | PT17 | Added guidance on the requirement for an Exchange Set to contain a digital signature (CATALOG.SIGN) file. | Clarification applied at Main Doc clause 11.2. | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | N | N
75 | Email from Peter Duguid 19/12/25. | PT17 | Added guidance on the mandatory requirement to digitally sign datasets for inclusion in an Exchange Set. | Clarification applied at Main Doc clause 11.3.1. | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | N | N
76 | 94 (S-101 Validation Checks) | PT17 | Added new guidance for compilers to take potential ECDIS screen clutter into account when determining whether to encode complex attribute sectorLimit for directional lights. | Clarification applied at clause 19.3.1.2. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | N
77 | 236 (Paper S-101PT16-05.1 and Decisions and Actions from S-101PT16) | PT17 | Added new enumerate attribute categoryOfObstruction value 24 (decommissioned platform jacket) and associated encoding guidance. | Revisions applied at clauses 13.6, 13.6.1 and 27.42. | Y | N/A | Y | S-4 clause B-445.1(h) | N | Y | Y | Y | Y | N | N | N
78 | 237 (Paper S-101PT16-05.1 and Decisions and Actions from S-101PT16) | PT17 | Amended guidance to reflect that the term “swept area” is now termed as “high confidence depth area” in S-4. | Revisions applied throughout DCEG. | Y | N/A | Y | S-4 clause B-415 | N | N | Y | N | N | N | N | N
79 | 238 (Paper S-101PT16-05.1 and Decisions and Actions from S-101PT16) | PT17 | Indicated value 9 (anchorage for periods up to 24 hours) as a value for attribute categoryOfAnchorage that is no longer intended to be populated. | Revisions applied at clauses 16.3, 16.5 and 27.10. | Y | N/A | Y | S-4 clause B-431.3 | N | Y | Y | Y | Y | Y | N | Y
80 | 238 (Paper S-101PT16-05.1 and Decisions and Actions from S-101PT16) | PT17 | Added new simple attribute maximumAnchorageTime. | Revisions applied at clauses 16.3, 16.5 and 27.127. | Y | N/A | Y | S-4 clause B-431.3 | N | Y | Y | Y | Y | Y | N | Y
81 | Paper S-101PT16-05.1 and Decisions and Actions from S-101PT16 | PT17 | Amended “DGPS” to “DGNSS positioning” (definition of zone of confidence A1; and A1 in Zone of Confidence Table). | Clarification applied at clause 27.74. | Y | N/A | Y | S-4 clause B-481.4 | N | Y | Y | Y | N | N | N | N