## Sheet1
S-101 Change Tracker post 2.0.0 |  |  | Last Updated: 26 March 2026
Impact
Serial | Paper/Issue | Meeting | Description | Status | Considered by ENCWG | S-57/S-52 Update | Considered by NCWG | S-4 Update | DPS | Registry | DCEG | FC | PC | VCs | S-164 | TDS | Issue
1 | Ongoing change | N/A | Update DSID - PRSP and PRED subfields (Annex B) | Applied. To be confirmed when Edition number finalised. | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | ? | ?
2 | Ongoing change | N/A | Update S-101 version and version date | Applied. To be confirmed when Edition number finalised. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | ? | Y
3 | S-101PT14-6.4 | PT14 | Changes to submarine cable symbology | Issues open to progress | ENCWG9 | S-52 5.0/YYMMDD | Seek confirmation of no change to S-4. | N/A | N | Y | N | N | Y | ? | Y | N | https://github.com/S-101-Portrayal-subWG/Working-Documents/issues/184
4 | S-101PT14-6.4 | PT14 | Changes to cable area symbology | Issues open to progress | ENCWG9 |  | Seek confirmation of no change to S-4. | N/A | N | Y | N | N | Y | ? | Y | N | Changes to Cable Area symbology (S-52 5.0.0) · Issue #183 · S-101-Portrayal-subWG/Working-Documents
5 | S-101PT14-6.4 | PT14 | Changes to overhead cable symbology | Issues open to progress | ENCWG9 |  | Seek confirmation of no change to S-4. | N/A | N | Y | N | N | Y | ? | Y | N
6 | 193 | PT15 | Add Silo Tank to association for Air Obstruction Light | Agreed at PT15 Applied to draft | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N | https://github.com/iho-ohi/S-101-Documentation-and-FC/issues/193
8 | S-101PT15-6.2 | PT15 | Text Pattern and Precision | Text patterns (RegEx Expressions) discussed and approved at S-101PT16. Changes applied to DCEG for Edition 2.1.0. Precision clarified in S-100 and is in agreement with format as defined in S-101 (NFA). | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N
9 | S-101PT15-6.1 | PT15 | Uncertainty in S-101 | Refer to Actions from S-101PT16. In progress. | N/A | N/A | N/A | N/A |  | ? | Y |  |  |  |  | Y
10 | 195 | PT15 | Remove unit Knots from simple attribute speedLimit. | Agreed at PT15 Applied to draft Registry action needed. Registry action completed 08/05/25. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N | Attribute Speed Limit should not have UOM Knots in Feature Catalogue · Issue #195 · iho-ohi/S-101-Documentation-and-FC
11 | 194 | PT15 | RadarStation could not be related to landmark | Agreed at PT15 Applied to draft | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N | RadarStation could not be related to landmark (association) · Issue #194 · iho-ohi/S-101-Documentation-and-FC
12 | Email correspondence with Peter Duguid 05/03/25 | DCEG SG | Value range closure and guidance for the population of the Meta attribute update number does not reflect that an Update Information feature(s) may be included in a New Edition dataset (update number = 0). | Draft changes made to DCEG. For consideration of DCEG Sub-Group. Change made to GI Registry. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | ? | N
13 | Email correspondence with Frank Hippman 12/03/25 | DCEG SG | Add Mooring Buoy [and Obstruction] to list of structures that have not been established specifically as an aid to navigation | Draft changes made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N
14 | Email correspondence with Frank Hippman 12/03/25 | DCEG SG | Add new guidance to encode buoys that have primary purpse as a mooring buoy using the Mooring Buoy feature; and use attribute colour to encode purpose if also used as a navigational aid | Draft changes made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
15 | 61 | PT15 | Add note stating that Aliases are to be retained in the S-101 FC until the end of the dual-fuel implementation period. | Agreed at PT15 Applied to draft | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | N | N
16 | 179 | PT15 | Amend Comment entry for DSID - DSEC sub-field. | Draft changes made to DCEG. For consideration of DCEG Sub-Group. Changes approved 28/05/25. | N/A | N/A | N/A | N/A | Y | N | N | N | N | ? | N | N
17 | 176 | PT15 | Amend Comment entry for CRSH - CRNM and VDAT - DTNM sub-fields. Amend Value entry for VDAT - DTID sub-field. | Draft changes made to DCEG. For consideration of DCEG Sub-Group. Changes approved 28/05/25. | N/A | N/A | N/A | N/A | Y | N | N | N | N | ? | N | N
18 | 167 | PT15 | Amend Comment entry for COCC - NCOR, SECC - NSEG and CCOC - NCCO sub-fields. | Draft changes made to DCEG. For consideration of DCEG Sub-Group. Change approved by S-100TSM. | N/A | N/A | N/A | N/A | Y | N | N | N | N | ? | N | N
19 | 218 | DCEG SG | Correct encoding guidance for seabed material extraction areas from categoryOfProductionArea = 13 (seabed material extraction area), which does not exist. | Draft change made to DCEG at clause 16.7.2 (corrected to categoryOfProductionArea = 5). For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
20 | 466 | Por SG | Consistency with S-52 Ed 4.0(.4). Refer to email correspondence 26-27/03/25. | Issue open to progress. | N/A | S-52 PL Ed 4.0(.4) | N/A | N/A | N | N | N | N | Y | N | ? | ?
21 | 85 | PT15 | Improved guidance for encoding the TidalStreamPanelData feature. | Draft change made to DCEG. For consideration of DCEG Sub-Group. Change approved 28/05/25. Any further changes to be identified as normal course of business. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
22 | Email from Christina Ulrich 17/04/25. | DCEG SG | Clarify that the value to be populated for “system” attribute defaultClearanceDepth on features that are within or partly within a DepthArea or DredgedArea feature having an unknown value for the attribute depthRangeMinimumValue follows the same rule as for features that are within or partly within an UnsurveyedArea feature. | Draft change made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
23 | Email from Gert Morlion 28/04/28. | DCEG SG | Amend the term "None" for identifying no geometry as an allowable geometric primitive for S-101 features to "No Geometry" to be consistent with S-100. | Draft change made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
24 | Secretariat observations | DCEG SG | Remove redundant duplicated last row of Table 30-2. | Draft change made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
25 | 166 and Email from Ben Hazelgrove 16/05/25 | DCEG SG 28/05/25 | Correct CRNM vertical component subfield for the CRSH field in the compound CRS encoding examples at tables 5-1 and 5-2 to remove the text “Depth – “. | Draft change made to Main Doc. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | Y | N | N | N | N | ? | ? | N
26 | 148 | DCEG SG 28/05/25 | Clarify that an aggregation or composition may include only a single component (containee) within the “container” due to the splitting of the aggregation or composition at the ENC dataset limits (NOTE: Applied for Fairway Aggregation for Edition 2.0.0 - needs to be applied for other associations.) | Agreed at DCEG SG meeting 28/05/25. Draft change made to DCEG. For consideration of S-101PT. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | ?
27 | 182 See Serial 63 below. | DCEG SG 28/05/25 | There are two ways to encode ferry cables in S-101 after the introduction of the new value 7 (ferry) to attribute categoryOfCable. Suggestion is to remove this new value and revert to encoding corresponding to S-57 (encode using FerryRoute feature). Further discussion between S-101PT Chair and Secretary regarding retention of removed modelling for backward compatibility and how this is to be indicated/described in the DCEG. | Agreed at DCEG SG meeting 28/05/25. Draft changes made to DCEG. For consideration of S-101PT. Papers in preparation for S-101PT16 and possibly S-100WG10. | N/A | N/A | N/A | N/A | N | N | Y | Y(?) | Y(?) | ? | ? | ?
28 | 189 | DCEG SG 28/05/25 | Clarify the encoding of the extent of the geometry of Bridge features covering their components so as to avoid possible conflict. | Agreed at DCEG SG meeting 28/05/25. Draft change made to DCEG. For consideration of S-101PT. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
29 | 207 and email from Richard Fowle 23/05/25. | DCEG SG | Add topmark as an allowable complex attribute for feature MooringBuoy. | Use case supplied by DK. Draft change made to DCEG. For consideration of DCEG Sub-Group. | N/A | N/A | N/A | N/A | N | Y | Y | Y | Y | N | N | Y
30 | Email from Christina Ulrich 29/07/25 | DCEG SG | Corrected binary logic for Boolean type attribute value False from (2) to (0). | Correction required and applied at DCEG clause 2.4.2. For approval of S-101PT. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
31 | 216 | PT16 | Correct erroneous listing of type for attributes soundingDistanceMaximum and soundingDistanceMinimum from Real (RE) to Integer (IN) at DCEG clause 3.11. | Correction required and applied at DCEG clause 3.11. For approval of S-101PT. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
32 | Email from Jonathan Pritchard 12/08/25. | PT16 | Amend reference to S-101 Dataset Loading and Display (Rendering) Algorithms to S-98 Appendix E. | Correction required to align with document structure in S-98 Edition 2.0.0 and applied at Main document clauses 4.7, 4.7.1 and 4.7.2. For approval of S-101PT. | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | N | N
33 | 210 | PT16 | Amend subfield comment for the SMAX subfield of the SPAS field to specify that a NULL value is {232-1} and not {0}. | Correction required to align with S-100 Edition 5.2.0 (clause 10a-7.3.2.3). Applied at Main document clauses B-5.1.31 and B-6.1.30. For approval of S-101PT. | N/A | N/A | N/A | N/A | Y | N | N | N | N | Y | ? | ?
34 | 213 | PT16 | Amend multiplicity of sub-attribute leastDepthOfDetectedFeaturesMeasured and associated guidance from mandatory to conditionally mandatory. | Correction required to align the data model with the corresponding guidance. Changes applied at DCEG clauses 3.8 and 3.11. | N/A | N/A | N/A | N/A | N | N | Y | Y | N | Y | N | N
35 | 217 | PT16 | Amend definition for value 63 (wave recorder) for attribute categoryOfSpecialPurposeMark to allow for wave recorders attached to daymarks to be taken into account. | Correction required to allow for wave recorders attached to daymarks to be taken into account. Changes applied at DCEG clause 27.67. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N
36 | 219 | PT16 | Add missing arrows from Bridge text box to feature. Amended text in Bridge text box to be consistent with changes made as a result of resolution of Issue #189. | Correction required for consistency. Changes applied at DCEG clause 6.6. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
37 | Email from Liz Hahessy 14/08/25 and IHO Sec response 16/08/25. | PT16 | Correct S-57 acronym reference HORCLR throughout to be italic for attribute horizontalClearanceValue and upright for horizontalClearanceWidth. | Correction required for consistency. Changes applied throughout DCEG. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
38 | 223 | PT16 | Amend lower bound multiplicity value for complex attribute tidalStreamValue from 1 to 13 - there must be a minimum of 13 values populated for the tidalStreamPanelValues complex attribute to be valid. | Clarification required for informing S-101 validation and for logical consistency. Change applied at clause DCEG 10.5. | N/A | N/A | N/A | N/A | N | N | Y | Y | N | N | N | Y?
39 | 222 | PT16 | Correct S-4 reference for physical and virtual AIS from B-480-484 to B-489. | Correction required to align with latest Edition of S-4. Change applied at DCEG clauses 21.2.1 and 21.3.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
40 | 54 | PT17 | Amended guidance for the encoding of QualityOfBathymetricData features covering land areas from “must not” to “should not”. | Correction required to align with proposed change to S-158:101. Change applied at DCEG clause 3.8.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | Y?
41 | 190 | PT17 | Removed guidance related to spatial accuracies related to curve features being prohibited. | Correction required to align with first sentence of paragraph. Change applied at DCEG clause 2.3.2. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | Y | Y?
42 | 244, Email from Christian Mouden 24/09/25 and IHO Sec response 25/09/25. | PT17 | Clarified that the fixed scale values defined for minimumDisplayScale and optimumDisplayScale only must be taken from the values in Table 3-1 of the S-101 Main document; and scale value for maximumDisplayScale can be any numeric value. | Correction required to align with guidance in S-101 DCEG clause 3.5 (maximumDisplayScale can be any numeric value). Change applied at Main document clause 4.6. | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | N | N
43 | Email from Christian Mouden 30/09/25 and IHO Sec response 02/10/25. | PT17 | Clarified that the display of the “gross overscale” pattern in ECDIS is applied in accordance with S-98 Main document, clause 12.3.3. | Change applied at Main document clause 4.6. | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | Y | Y
44 | Email from Christian Mouden 25/09/25 and IHO Sec response 30/09/25. | PT17 | Clarified that the optimumDisplayScale for the entire dataset is defined in S100_DatasetDiscoveryMetadata; and that where a dataset has multiple DataCoverage features, the value for maximumDisplayScale populated in the S100_DatasetDiscoveryMetadata must be an empty (null) value. | Clarification applied at Main document clause 4.5.3. | N/A | N/A | N/A | N/A | Y | N | N | N | N | Y | Y | Y
45 | Email from Heaxagon Geospatial (via Yong) 25/09/25. | PT17 | Various portrayal issues. | With Portrayal SG lead. | N/A | N/A | N/A | N/A | N | N | N | N | Y | N | N | Y?
46 | 208 | PT17 | Added new guidance related to the relationship between the multiplicities as described in the DCEG and as included in the Feature Catalogue, where a feature that is included in the “containee” end of the relationship may or may not appear in more than one association instance of a named association. | Revisions applied throughout Section 25. | N/A | N/A | N/A | N/A | N | N | Y | Y | N | Y | Y | Y | Feedback from DK supplied 25/09/25. Confirms consistency within the FC however multiplicities need to be corrected in the FC and clarifications required in the DCEG.
47 | Email from Ben Hazelgrove 03/10/25 and IHO Sec response 03/10/25. | PT17 | Issue with Validation Checks reporing an Error when soundings in a sounding group fall withinin different SoundingDatum features having the same vertical datum defined. | With Validation Checks SG Lead | N/A | N/A | N/A | N/A | N | N | Y? | N | N | Y? | N | Y
48 | GI Registry, Concept Register clarification proposal 09/10/25 | PT17 | Clarified definition for attribute categoryOfRestrictedArea code value 19 (waiting area) as proposed by the NIPWG on behalf of ITCPO/IHMA. | Clarification applied at DCEG clause 27.57. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N
49 | Email from Ruiran 20/10/25 and IHO Sec response 21/10/25. | PT17 | Clarified that the attribute verticalDatum applies only to the values populated for the populated vertical clearance(s). | Clarification applied at DCEG clauses 6.7.1, 6.8.1, 6.9.1, 6.10.1, 8.11.1 and 8.13.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
50 | Email from Ben Hazelgrove and IHO Sec response 22/10/25. | PT17 | Amended cardinality of attributes depthRangeMaximumValue and depthRangeMminimum value from optional (0,1) to conditional mandatory (0,1†) and added associated guidance. Amended associated S-57 attribute for depthRangeMaximumValue to include DRVAL1 where the Quality OfBathymetricData is also covered by a SweptArea; and amended the guidance for the population of depthRangeMaximumValue and depthRangeMinimumValue. | Clarification applied at DCEG clauses 3.8 and 3.8.1. | N/A | N/A | N/A | N/A | N | N | Y | Y | N | Y | N | N
51 | Email from Ben Hazelgrove 28/10/25 and IHO Sec response 30/10/25. | PT17 | Amended guidance for population of successive instances of sub-complex attribute fixedDateRange to specify that the dateStart an instance must be equal to the date immediately following the dateEnd of the previous instance. | Clarification applied at DCEG clause 3.8.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | Y
52 | Email from Ben Hazelgrove and IHO Sec response 27/11/25. | PT17 | Amended guidance for SpatialQuality associated to Obstruction, UnderwaterAwashRock or Wreck where attribute height or valueOfSounding is populated with an empty (null) value to state that sub-complex attribute verticalUncertainty must not be populated. | Overtaken by events. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | Y?
53 | 234 | PT17 | Amended model for features TidalStreamFloodEbb, CurrentNonGravitational and TidalStreamPanelData to deprecate complex attribute orientation and add simple attribute orientationValue. | Revision applied at clauses 10.2, 10.3 and 10.5. | N/A | N/A | N/A | N/A | N | Y | Y | Y | Y | Y | Y | Y
54 | 180 | PT17 | Expanded scope of definition to allow for the Structure/Equipment association to be used to associate features that are not intended as aids to navigation. | Clarification applied at DCEG clause 25.16. | N/A | N/A | N/A | N/A | N | N | Y | Y | N | Y | N | N
55 | 180 | PT17 | Added reference to clauses 18.1.and 18.2 for additional guidance on encoding the StructureEquipment association for aids to navigation. | Clarification applied at DCEG clause 25.16. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
56 | 192 | PT17 | Clarified the relationship between SoundingDatum and the Dataset Coordinate Reference System record for the dataset; and the requirement for multiple SoundingDatum features in a single dataset. | Clarification applied at DCEG clause 3.9.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
57 | 196 | PT17 | Indicated complex attribute multiplicityOfFeatures and its sub-attributes as an attribute that is no longer intended to be populated. Added new simple attribute number of features. | Revision applied at clauses 6.2, 27.131 and 29.12. | N/A | N/A | N/A | N/A | N | Y | Y | Y | Y | Y | Y | Y
58 | 196 | PT17 | Added new guidance for encoding of attribute numberOfFeatures, including intended ECDIS portrayal outcomes. | Clarification applied at DCEG clause 27.139. | N/A | N/A | N/A | N/A | N | N | Y | N | Y | N | Y | Y
59 | 199 | PT17 | Added new enumerate value 9 (painted) (from S-57) for attribute natureOfConstruction, for use for Daymark features only, with associated guidance. | Revision applied at clauses 20.14, 20.14.1 and 27.136. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N
60 | 208 | PT17 | Amended multiplicity of “container” end of association from 0,1 to 0,* to allow “containee” features to be included in more than one association instance. | Revisions applied at clauses 25, 25.1,25.2, 25.4, 25.13 and 25.21. | N/A | N/A | N/A | N/A | N | N | Y | Y | N | Y | Y? | Y
61 | 215 | PT17 | Added new allowable truncated date value for same day each month (no specific year or month - ------DD) for dateFixed and periodicDateRange attributes. | Revision applied at clause 2.4.7. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | Y? | Y
62 | 220 | PT17 | Added new guidance for provision of a visual indicator in ECDIS where the horizontal position and vertical accuracies encoded on a sounding, rock, obstruction or wreck indicates a lower accuracy than indicated by the underlying QualityOfBathymetricData Meta feature. | Clarifications applied at clauses 11.3.1, 13.3, 13.4.1, 13.5.1 and 13.6.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y? | N | N
63 | 182 | PT17 | Indicated value 7 (ferry cable) as a value for attribute categoryOfCable that is no longer intended to be populated. | Revision applied at clauses 14.2, 14.3 and 27.12. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | Y? | Y?
64 | 226 | PT17 | Indicated value 18 (bearing light) as a value for attribute categoryOfLight that is no longer intended to be populated. | Revision applied at clauses 19.2, 19.3 and 27.37. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | N
65 | 225 | PT17 | Amended/removed redundant INT1 references. | Clarifications applied at clauses 7.1, 20.5, 20.5.1 and 20.13.1. | N/A | N/A | N/A | N/A | N | Y | Y | N | N | N | N | N
66 | 228 | PT17 | Indicated value 21 (dredging area) as a value for attribute categoryOfRestrictedArea that is no longer intended to be populated. | Revision applied at clauses 17.8 and 27.57. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | N
67 | 228 | PT17 | Amended guidance for the encoding of “dredging areas” to be encoded using OffshoreProductionArea and not RestrictedArea. | Revision applied at clauses 14.6.1 and 16.7.2. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
68 | 231 | PT17 | Updated Table 2-8 for entry UpdateInformation to have attribute scaleMinimum set to the same value as the associated feature. | Revision applied at clause 2.5.9. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | N
69 | 233 | PT17 | Amended value for attribute categoryOfSignalStationTraffic code 9 from “dredging” to “dredging signal station”. | Revision applied at clauses 22.5 and 27.62. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N
70 | S-101PT16-07.1A | PT17 | Added guidance at Note 3 related to the depth accuracy component of the categories of Zone of Confidence that the formula used to determine depth accuracy is informative only. | Clarification applied at clause 27.74. | Y | Y | N/A | Y | N | N | Y | N | N | N | N | N
71 | S-101PT16-07.3 | PT17 | Mandated maximum string lengths for Text type simple attributes. | Revision applied at clauses 27.8, 27.79, 27.84, 27.89, 27.97, 27.104, 27.132, 27.133, 27.149, 27.153, 27.169, 27.170, 27.198, 28.21 and 28.22. | N/A | N/A | N/A | N/A | N | N | Y | Y | N | Y | N | Y?
72 | S-101PT16-07.3 | PT17 | Added text pattern (Regular Expression (RegEx) notation) for formatted text type attributes. | Revisions applied at clauses 27.77, 27.98, 27.117, 27.129, 27.142 and 27.145. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | Y | N | Y
73 | 89 (S-101 Validation Checks) | PT17 | Added new guidance for the encoding of areas of the Contiguous Zones, EEZs or Territorial Seas of adjoining Coastal States that are in dispute. | Clarification applied at clause 16.2.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | N
74 | Email from Peter Duguid 19/12/25. | PT17 | Added guidance on the requirement for an Exchange Set to contain a digital signature (CATALOG.SIGN) file. | Clarification applied at Main Doc clause 11.2. | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | N | N
75 | Email from Peter Duguid 19/12/25. | PT17 | Added guidance on the mandatory requirement to digitally sign datasets for inclusion in an Exchange Set. | Clarification applied at Main Doc clause 11.3.1. | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | N | N
76 | 94 (S-101 Validation Checks) | PT17 | Added new guidance for compilers to take potential ECDIS screen clutter into account when determining whether to encode complex attribute sectorLimit for directional lights. | Clarification applied at clause 19.3.1.2. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | N
77 | 236 (Paper S-101PT16-05.1 and Decisions and Actions from S-101PT16) | PT17 | Added new enumerate attribute categoryOfObstruction value 24 (decommissioned platform jacket) and associated encoding guidance. | Revisions applied at clauses 13.6, 13.6.1 and 27.42. | Y | N/A | Y | S-4 clause B-445.1(h) | N | Y | Y | Y | Y | N | N | N
78 | 237 (Paper S-101PT16-05.1 and Decisions and Actions from S-101PT16) | PT17 | Amended name of feature SweptArea to HighConfidenceDepthArea to reflect change in S-4. Amended definitions for HighConfidenceDepthArea, attribute sweptDate and enumerate value mechanicallySweptSurvey. Deprecated feature SweptArea. | Revisions applied throughout DCEG. Changed feature table entry for new feature name at clause 11.5. Deprecation at clause 11.12. | Y | N/A | Y | S-4 clause B-415 | N | Y | Y | Y | Y | Y | Y | Y
79 | 238 (Paper S-101PT16-05.1 and Decisions and Actions from S-101PT16) | PT17 | Indicated value 9 (anchorage for periods up to 24 hours) as a value for attribute categoryOfAnchorage that is no longer intended to be populated. | Revisions applied at clauses 16.3, 16.5 and 27.10. | Y | N/A | Y | S-4 clause B-431.3 | N | N | Y | Y | N | Y | Y | Y
80 | 238 (Paper S-101PT16-05.1 and Decisions and Actions from S-101PT16) | PT17 | Added new simple attribute maximumAnchorageTime. | Revisions applied at clauses 16.3, 16.5 and 27.127. | Y | N/A | Y | S-4 clause B-431.3 | N | Y | Y | Y | N | Y | Y | Y
81 | Paper S-101PT16-05.1 and Decisions and Actions from S-101PT16 | PT17 | Amended “DGPS” to “DGNSS positioning” (definition of zone of confidence A1; and A1 in Zone of Confidence Table). | Clarification applied at clause 27.74. | Y | N/A | Y | S-4 clause B-481.4 | N | Y | Y | Y | N | N | N | N
82 | 120 | PT17 | Added new Geo feature DepthDiscontinuity. Replaced guidance on encoding of discontinuities between surveys with reference to new clause 11.11. | Revisions applied at clauses 2.3.1, 2.5.9, 11.9.3 and new clause 11.11. | N/A | N/A | Y | N/A | N | Y | Y | Y | Y | N | Y? | Y?
83 | 117 | PT17 | Added System attribute inTheWater as an allowable attribute for feature SlopeTopline. | Revision applied at clause 15.5. | N/A | N/A | Y | Suggested for S-4 clause B-411.7 | N | Y | Y | Y | Y | Y | Y | Y
84 | 117 | PT17 | Added new guidance for encoding subsurface cliffs not indicatable by contour interval or sounding pattern. | Revisions applied at clauses 5.1, 15.5.1 and new clause 11.7.6. | N/A | N/A | Y | Suggested for S-4 clause B-411.7 | N | N | Y | N | N | N | N | N
85 | 85 | PT17 | Added more complex example for population of the complex attribute tidalStreamPanelValues. | Revision applied at clause 10.5.1. | N/A | N/A | Y | Y | N | N | Y | N | N | Y? | N | N
86 | DK Paper and discussions at DCEG SG meeting 20-12/01/26 | PT17 | Transposed terms “Empty (null)” and “Unknown” in Tables 30-1 to 30-3 for consistency. | Revision applied at clause 30.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
87 | 247 also S-101 Validation Checks Issue #149 | PT17 | Clarified that Dam features of type surface only are required to be covered by a LandArea feature. | Clarification applied at clause 8.12.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | N
88 | 130 | PT17 | Renamed clause 2.3 to general clause heading “Geometry”. Former clause 2.3 “Geometric primitives” relocated to clause 2.3.1 and former clause 2.3.1 “Capture density guide” relocated to clause 2.3.2. Former clause 2.4.7 "Spatial attribute types" moved to new clause 2.3.3 and former clauses 2.4.8 to 2.4.12 reduced by one sub-clause number. | Clause number revisions applied as listed in Description. | N/A | N/A | N/A | N/A | Y | N | Y | N | N | Y | N | N
89 | 130 | PT17 | Added new guidance for representing geodesic curve segments using a “densification” factor of short loxodromic curve segments. | Clarification applied at clause 2.3.2. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | N
90 | DCEG Editor observation 02/02/26. | PT17 | Clarified that VerticalDatum Meta features are not required if the dataset does not contain any height information or land area. | Clarification applied at clause 3. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y? | N | Y? | No longer to be considered. Change made erroneously.
91 | 235 | PT17 | Add missing source identifier for features Helipad, StructureOverNavigableWater, MooringArea; and add feature Chart1Feature. | Included in "Changes to S-101 Feature Catalogue Required for S-101 Edition 2.1.0" document. | N/A | N/A | N/A | N/A | N | N | N | Y | N | N | N | N
92 | 240 | PT17 | Added new guidance for encoding a Daymark feature for an object that is intended to be a daytime aid to navigation is located on top of a pile. | Clarification applied at clause 8.4.1. | Y | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
93 | 245 | PT17 | Amended indication and added new example for simple attribute signalGroup to account for the signal group for a signal transmitted from a radar transponder beacon. | Clarification applied at clause 27.163. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | N
94 | Email from Klas Östergren 03/02/26. | PT17 | Added new remarks bullet providing guidance on encoding attribute techniqueOfVerticalMeasurement on feature DepthNoBottomFound (consistency with guidance for Sounding features). | Clarification applied at clause 11.8.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | N
95 | 201 | PT17 | Amended format and guidance for population of attribute communicationChannel. | Revision applied at clause 27.77. Doscussion ongoing. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | Y | N | N
96 | DK Paper and discussions at DCEG SG meeting 20-12/01/26 | PT17 | Added new guidance providing a comparison between language used in S-158:101 and S-101 in regard to attribute population. | Clarification applied at clause 1.4. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
97 | Validation Checks GitHub Issue #146 | PT17 | Clarified that Obstruction features of type surface only that are always dry are required to be covered by a LandArea feature. | Clarification applied at clause 13.6.1 | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
98 | Email from Tom De Puyt 28/01/26 | PT17 | Clarified the encoding of wadis using the attribute categoryOfLandRegion = 21 (wadi). | Clarification applied at clause 5.7.1 | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
99 | Email from Christina Ulrich 06/05/25 | PT17 | Added value 3 (deeper than the range of depth of the surrounding depth area) for attribute expositionOfSounding as an allowable value for the UnderwaterAwashRock feature. | Clarification applied at clause 13.4 | N/A | N/A | N/A | N/A | N | N | Y | Y | N | N | N | N
100 | 190 | PT17 | Added new guidance that complex attribute verticalUncertainty on Information feature SpatialQuality can only be used when associated with features Sounding and DepthNoBottomFound. | Revisions applied at clauses 2.3.3, 3.3, 3.8.1, 3.11.1, 24.5.1 and 25.15. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | N
101 | 190 | PT17 | Clarified guidance that vertical uncertainties are to be populated at the feature (attribute verticalUncertainty) level where depth or clearance is populated at the feature (attribute) level. | Clarification applied at clause 3.2 | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | N
102 | 190 | PT17 | Added improved guidance for population of horizontal position and vertical uncertainties for rocks, wrecks and obstructions. | Clarifications applied at clauses 13.4.1, 13.5.1 and 13.6.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y? | N | N
103 | 190 | PT17 | Added complex attribute verticalUncertainty as an allowable attribute for features FloatingDock, Obstruction, PipelineSubmarineOnLand, UnderwaterAwashRock and Wreck. | Clarifications applied at clauses 8.18, 13.4, 13.5, 13.6 and 14.4. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N
104 | 190 | PT17 | Added new guidance that complex attribute verticalUncertainty only apply to attributes depthRangeMaximumValue and depthRangeMinimumValue for feature PipelineSubmarineOnLand. | Clarification applied at clause 14.4.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y? | N | N
105 | Editor observation | PT17 | Clarified the difference in meaning between the encoding of the complex attribute verticalUncertainty as a sub-complex attribute of the complex attribute verticalClearanceOpen and as bound as a complex attribute to the Gate feature itself. | Clarification applied at clause 8.11.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
106 | Paper S-101PT17-06.6 and Decisions and Actions from S-101PT17 | PT17 | Added new complex attribute datumDifferenceInformation (sub-attributes datumSeparationValue, stationName and verticalDatum) and bound to required features. Deprecated simple attribute verticalDatum from these features (except for SoundingDatum); and amended encoding guidance throughout. | Revisions applied at clauses 3.8, 6.7, 6.8, 6.9, 6.10, 6.11, 6.16, 8.7, 8.11, 8.13, 19.2, 19.3, 19.4, 19.5 and 29.1 | Y | N/A | N/A | N/A | N | Y | Y | Y | N | Y | Y | Y
107 | Paper S-101PT17-06.6 and Decisions and Actions from S-101PT17 | PT17 | Added new simple attribute datumSeparationValue. Included as sub-attribute for new complex datumDifferenceInformation; and amended guidance throughout as required. | Revisions applied at clauses 3.9, 6.7, 6.8, 6.9, 6.10, 6.11, 6.16, 8.7, 8.11, 8.13, 19.2, 19.3, 19.4, 19.5 and 27.85 | Y | N/A | N/A | N/A | N | Y | Y | Y | N | Y | Y | Y
108 | Paper S-101PT17-06.6 and Decisions and Actions from S-101PT17 | PT17 | Added new complex attribute datumDifferenceInformation as a new sub-complex attribute to the vertical clearance complex attributes. | Revisions applied at clauses 29.37, 29.38, 29.39 and 29.40 | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | Y | N | N
109 | Paper S-101PT17-06.6 and Decisions and Actions from S-101PT17 | PT17 | Clarified definition of simple attribute stationName. | Clarification applied at clause 27.171. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N
110 | Paper S-101PT17-06.3 and Decisions and Actions from S-101PT17 | PT17 | Added new guidance as to what is considered to be a “navigable” Gate feature. | Clarifications applied at clauses 8.11 and 8.11.1. | N/A | N/A | N/A | N/A | N | N | Y | N | N | Y | N | N
111 | 229 | PT17 | Added guidance that the files referenced by the attributes fileReference and pictorialRepresentation are included in the Exchange Set and Electronic Navigational Data Service. | Clarifications applied at DCEG clauses 27.99 and 27.144; and Main Document clause 11.4.1. | N/A | N/A | N/A | N/A | Y | N | Y | N | N | N | N | N
112 | 242 | PT17 | Amended feature name CollisionRegulationsLimit to CollisionRegulations to reflect national encoding requirements. Added surface as an allowable geometric primitive and amended encoding guidance throughout. Deprecated feature CollisionRegulationsLimit. | Revisions applied at clauses 2.3.1, 16.27 and 16.29. | N/A | N/A | N/A | N/A | N | Y | Y | Y | Y | Y | Y | Y
113 | 243 | PT17 | Amended guidance and recommended scale minimum step values for features PylonBridgeSupport, SpanFixed and SpanOpening to reduce potential ECDIS screen clutter. | Revisions applied at clause 2.5.9. | N/A | N/A | N/A | N/A | N | N | Y | N | N | N | N | N
114 | Paper S-101PT17-06.8 | PT17 | Corrected Remark for S100_SupportFileFormat value TIFF to state that this is the only format allowed for pictorial ENC support files. | Revision applied at clause 12.1.3.1. | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | N | N
115 | Paper S-101PT17-06.4 | PT17 | Increased maximum allowable file size for ENC Update datasets from 200 kb to 300 kb. | Revision applied at clause 4.5.4 (Main Document). | N/A | N/A | N/A | N/A | Y | N | N | N | N | Y | Y | Y
116 | 494 | Port SG | Whole metre depths < 10 metres are portraying with a "0" decimetre value (not required); and drying depths > 9.9 metres are displaying with the drying height "underline" indication appearing under one of the whole metre digits. | Reported to NIWC 17/03/26 and new GitHub Issue created. | N/A | N/A | N/A | N/A | N | N | N | N | Y | N | N | N
117 | 241 | Document review | Added new enumerate attribute verticalDatum value 50 (national low water datum). | Clarifications applied at clauses 3.9 and 27.198. | N/A | N/A | N/A | N/A | N | Y | Y | N | N | N | N | N
118 | GI Registry Clarification proposal (NIPWG) | Reg DCB | Clarified definition for attribute qualityOfVerticalMeasurement code value 10 (maintained depth). | Clarification applied at clause 28.16. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N
119 | 249 | Document review | Amended multiplicity of supportFileSpecification field for S100_SupportFileDiscoverymetadata from [1] to [0..1]. | Revisions applied at Main document clause 12.1.3. | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | N | N
120 | 253 | HSSC18 | Amended value for attributes categoryOfSignalStationWarning and categoryOfSignalStationTraffic as required to be specific to signal stations. | Revision applied at clauses 22.4, 22.5, 27.62 and 27.63. | N/A | N/A | N/A | N/A | N | Y | Y | Y | N | N | N | N
121 | S-100WG/S-101PT review comment (GB) | HSSC18 | Clarified the format of the values for the dataReplacement field of S100_DatasetDiscoverymetadata to be a single dataset name without file extension. | Clarification applied at Main document clause 12.1.2. | N/A | N/A | N/A | N/A | Y | N | N | N | N | N | N | N