## Sheet1
| S-101 PT 2.0.0 Delivery Plan | [5 empty] | S-101 PT Chair 20240305
Ref | Theme | Task | Lead | Start | End | Status | Comments
1 | Edition 1.2.0 | 1.2.0 PC Review | Port SG | 2024-02-21 | 2024-03-11 | IN PROGRESS | Email from Jeff
2 |  | Prepare FC 1.2.3 addressing issues identified | KHOA | 2024-02-22 | 2024-03-07 | IN PROGRESS | Confirmed by Minju 20240223
3 |  | Publish final 1.2.0 content and inform S-100WG | Chair | 2024-03-11 | 2024-03-11 | PLANNED | Awaiting completion of ref 1 and 2
4 | Edition 1.3.0 | Prepare DCEG and DPS 1.3.0. Submit association and association role names to GI Registry. | JW | 2024-03-08 | 2024-03-22 | PLANNED | Includes applying S-100 5.2.0 changes, any outstanding items moved to Backlog. Association issues to be addressed.
5 |  | Prepare a 1.3.0 Feature Catalogue | KHOA | 2024-03-25 | 2024-04-19 | PLANNED | FCB expected 11th March MJ 20240229
6 | 2.0.0 Prep | Conduct PT Review Cycle | JW | 2024-03-08 | 2024-05-03 | PLANNED
7 |  | Verify FC/DCEG | Chair | 2024-04-19 | 2024-05-03 | PLANNED
8 |  | Prepare a 1.3.0 Portrayal Catalogue | Port SG | 2024-03-22 | 2024-05-17 | PLANNED | Dependency on test data.
9 |  | Prepare a 1.3.0 Validation Checks | Val SG | 2024-03-22 | 2024-05-17 | PLANNED
10 |  | Prepare final documents for PT13 (1.4.0) | JW | 2024-05-03 | 2024-05-17 | PLANNED | DPS, DCEG & Review comments
11 | Finalise 2.0.0 | Hold S-101PT13 | Chair | 2024-06-16 | 2024-06-19 | PLANNED
12 |  | Prepare final documents draft 2.0.0 | JW | 2024-06-20 | 2024-07-05 | PLANNED | DPS, DCEG and FC
13 |  | Portrayal edit and make 2.0.0 | Port SG | 2024-06-20 | 2024-07-05 | PLANNED | Dependency on test data.
14 |  | Validation Checks edit and make 2.0.0 | Val SG | 2024-06-20 | 2024-07-05 | PLANNED
15 |  | Send to S-100WG for approval | Chair | 2024-07-05 | 2024-07-05 | PLANNED
B1 | Backlog | Resolve metadata inheritance | Port SG
B2 |  | Resolve uncertainty alerts/indications | Port SG
B3 |  | Put robust FC checks in place | Chair |  |  |  | Develop schematrons and formal checks, test with 2.0.0
B4 |  | Resolve DQWG Comments | JW | 2024-03-15 | 2024-03-22
B5 |  | Registry updates for symbols VGs etc | Port SG
B6 |  | Resolve association inconsistencies | JW | 2024-03-05 | 2024-03-22
B7 |  | Resolve ODS
B8 |  | Resolve rendering algorithm