## S-101PT Actions
S-101PT Actions @20210519
No. | Action | Detail | Lead | Status | Remarks | NIWC Remarks
S-101PT4-06 | NCWG activities affecting S-101 development | Draft amendments to the S-101 DCEG to make provision of encoding different colours of floodlighting. | JW | Ongoing. | Email to Antonio 07/04/21.
S-101PT4-07 | NCWG activities affecting S-101 development | Consider how to reduce the triggering of “false” alarms in ECDIS through consistent encoding practices. This should be documented in the S-101 DCEG. | Chair/IHO Sec | Ongoing | S-101 Catch-Up March 2021: Action to be transferred to the S-101 Roadmap (Chair). S-101PT7: Report back to S-101PT8.
S-101PT4-14 | Sector Extension Portrayal Attribute | Improve the wording describing sector light extension as described in paper 5.5. | NIWC/JW | Ongoing | Recommend transfer to DCEG SG, noting that this action is distinct from the associated discussion taking place within the Portrayal Sub-Group (GitHub issue #3). S-101PT7: JW and DG to discuss further offline. | DCEG 30.4 sector extension - see paper S-101PT4-5.4 1) Change definition (current is misleading, implies extension is from origin vice default): “The distance in screen millimeters (mm) by which a sector is extended beyond the default.” 2) Recommend remove second bullet item from remarks.
S-101PT4-15 | Sector Extension Portrayal Attribute | Conditional Symbology Procedure needs to be developed for item 2 in paper 5.5. | HA/HP/JW | Ongoing | S-101PT7: JW and HA to discuss further offline. Neesds to be taken in association with Action S-101PT4-14.
S-101PT5-03 | Visualization of Quality of Bathymetric Data | Consider the implementation of DQWG recommendations on improved portrayal of Quality of Bathymetric Data information in ECDIS (for S-101PT6). | S-101 Portrayal Sub-Group | Ongoing
S-101PT5-07 | Feature Catalogue | KHOA, Portolan Sciences (and any other interested parties) to review changes to the FC to ensure validitiy with S-100 FC schemas (As new versions of the FC are created). | KHOA/RM/HA/YB/NIWC | Ongoing | Email from Izzy 21/09/20. Note however that this action is intended to be ongoing. FC draft Ed 1.0.1 circulated to small group 21/04/21. | Comments provided
S-101PT5-09 | Portrayal | Engage with the S-100WG in regard to work required on S-101 portrayal, ECDIS performance, etc. (TSM8). | Vice-Chair | Ongoing | See Port SG Report XX
S-101PT5-13 | Datum Issues | A small group, led by NIWC, to discuss the issues raised in the Paper S-101PT5-10. Possible feedback required to TSM8. | NIWC (Lead) | Ongoing | Recommendation 1 & 2: We need a path to close these out. Recommend address via update to PS. 1) S-101 ISO-8211 ordering of VDAT records (S-101PT Chair: Propose new action to make proposal re VDAT needed.) 2) S-101 ISO-8211 encoding of AXTY (axis orientation) Recommendations 3 and 4 are withdrawn Recommendation 5 (modify model of sounding/verticalDatum): Recommend refer to DCEG SG S-101PT7: OEMs to please look at Portrayal Issues in the GitHub and provide input to these discussions. | Awaiting feedback / guidance
S-101PT5-21 | Compendium of AHO Proposals | Paper S-101PT5-18 to be considered by the DCEG Sub-group (November 2020). | S-101 DCEG Sub-Group/S-101 Portrayal Sub-Group | Ongoing | To be discussed at next DCEG SG meeting.
S-101PT5-23 | NIWC Testbed Update | DCEG Sub-Group to discuss the following issues raised in the NIWC Testbed Update report (S-101PT5-21 – listed by the associated Presentation slides): Slides 15, 21, 27. | S-101 DCEG Sub-Group | Ongoing | To be discussed at next DCEG SG meeting.
S-101PT5-27 | NIWC Testbed Update | National language support and ECDIS Pick Report issues (including those identified in slides 30 and 31 of the S-101PT5-21 agenda item presentation) to be addressed as a lower priority task (for S-101 Edition 1.x or 2.0). | S-101PT | Ongoing | Note low priority. S-101PT7: To be discussed intersessionally. | 1) S-52 10.8.4 - note aggregates use priority of highest priority member which intersects pick region, show single pick report entry for aggregates. 2) Is there a need to exclude attributes from the pick report (e.g. S-57 category "C" attributes, or tidal stream panel values)? If so, recommend add new attr to DCEG section 30 which catalogs attributes to exclude. Alternatively, propose extension to FC model and catalog these attributes in the FC - supports use by other product types.
S-101PT6-01 | NIWC Testbed Update (Action S-101PT5-25 - slide 27) | S-100 Validation Checks developers to pick up the invalid geometries issue to confirm checks cover this; and guidance on what systems should do when receiving such data exists. | JP | Ongoing
S-101PT6-05 | DCEG Update | Investigation to be conducted into possible amendments to the UOC resulting from the change in terminology from “Emergency Wreck Marking Buoy” to “New Danger Marking Buoy” (for ENCWG6). | JW | Ongoing | To be discussed at the IHO/IALA Technical Coordination Meeting April 2021. Discussion at this meeting indicate that a decision will be made by IALA later in 2021.
S-101PT6-06 | Portrayal Progress | Project Team Members to provide feedback on any of the Portrayal Sub-Group GitHub issues before 04 April 2021, noting that subject to no adverse comments this will be taken as S-101PT endorsement of the decisions/actions agreed by the Portrayal Sub-Group. | S-101PT | Ongoing | S-101PT7: JW to take up with Alvaro.
S-101PT6-08 | Portrayal Progress | Ensure that all S-101 portrayal considerations as included in the “S-57 Removed_Remodelled Items” spreadsheet have been amalgamated with the work that has been done by Germany and US (NOAA) before 04 April. | AS/JW | In Progress
S-101PT6-10 | Validation Update | Incorporate process to ensure alignment of all draft Validation Checks and test datasets to single versions of related publications (S-100/S-101/S-101DCEG) in the overall Validation Checks development process. | Chair | Ongoing
S-101PT6-11 | S-101PT Workplan Update | Pending completion of the Edition 1.0.1 DCEG (Action S-101PT6-04), version 1.0.1 of the S-101 Feature Catalogue to be prepared by end of March 2021. | IK/KHOA | In Progress | Expected 09 April.
S-101PT6-12 | S-101PT Workplan Update | Establish a repository for S-101 test datasets, with “development” test data to be made available by 01 September 2021. | Chair/IHO Sec | In Progress | Use Registry Testbed space? Discuss with Yong.
S-101PT6-18 | Quality of Horizontal Measurement | Raise the decisions made in relation to the restriction of the values of the attribute qualityOfHorizontalMeasurement to the NCWG for possible impacts on S-4 and INT1. | CM/MH | Ongoing | S-101PT7: Proposal to be submitted to next NCWG meeting.
S-101PT7-01 | HSSC13 Outcomes | Any S-101PT members interested in contributing to the development of the DF Concept “Governance” document to indicate to the IHO Secretariat (jeff.wootton@iho.int) at the earliest opportunity. | S-101PT | New Action
S-101PT7-02 | S-101PT Actions | References to S-101PT meeting Agenda item numbers to be removed from column 2 of the Consolidated Actions spreadsheet. | IHO Sec | Completed
S-101PT7-03 | S-101PT Actions | S-101PT Work Plan to be updated taking into account S-100WG and HSSC approval milestones. | Chair | New Action
S-101PT7-04 | DCEG Update | Include changes that directly impact on S-101 implementation in the DCEG Document Control page for the next Edition. | JW | New Action
S-101PT7-05 | Feature Catalogue | Add IF (Lloyd’s Register) to the small “expert group” for future S-101 Feature Catalogue reviews. | JW | New Action
S-101PT7-06 | Outreach | PT members interested in participating in the Outreach Sub-Group to notify the Chair by email (thomas.richardson@ic-enc.org) at the earliest opportunity. | S-101PT | New Action
S-101PT7-07 | Modify TextPlacement to Support Bearing/Distance | Include the Paper Modify TextPlacement to Support Bearing/Distance as a new Issue in the S-101 Documentation and FC GitHub repository (https://github.com/iho-ohi/S-101-Documentation-and-FC) for discussion within the DCEG Sub-Group; and the S-101 Portrayal GitHub repository (https://github.com/iho-ohi/S-101-Portrayal-SubWG) for portrayal implications. | JW/AS | New Action
S-101 Portrayal Sub-Group Actions
PortSG-01 | Quality of Bathymetric Data - Visualization of Vertical and Positional Uncertainties | Develop a portrayal proposal capable of managing both, positional and depth uncertainty values on charted Sounding, Underwater Rock, Wreck and Obstruction. | KHOA | Pending | GitHub #1.
PortSG-02 | Quality of Bathymetric Data - Visualization of Vertical and Positional Uncertainties | Develop changes to the A&I catalogue and on-shore ECDIS to implement the use of Horizontal Position Uncertainty, Vertical Uncertainty and displayUncertainties by ECDIS in-built route checking safety functions. Use the 'ECDIS expected performance' section of paper DQWG15_2020_05.1B as an starting point for this job. | NIWC | Pending | GitHub #1. | Awaiting test data
PortSG-03 | Quality of Bathymetric Data - Visualization of Vertical and Positional Uncertainties | (DCEG and FC): Add new boolean attribute displayUncertainties to the following feature types: Sounding, Underwater Rock, Wreck and Obstruction. | JW/KHOA | Completed | GitHub #1.
PortSG-04 | Fairway portrayal | Submit full proposal using the online ''S-101 Portrayal request from". | Norway | Pending | GitHub #2.
PortSG-05 | Light Sector Portrayal - Sector Light Length | Provide updated version of the PC to Norway. | NIWC | Pending | GitHub #3. | Awaiting feedback on GitHub post of 10/29/2020
PortSG-06 | Light Sector Portrayal - Sector Light Length | Report lessons learnt and/or submit full proposal to S-101PT7. | Norway | Pending | GitHub #3.
PortSG-07 | Quality of Bathymetric Data and ECDIS Performance (Management of Temporal variation) | DCEG subWG to discuss and present to the S101PT re-modelling proposals in support of the temporal downgrading of QoBD. | JW | Completed | GitHub #4.
PortSG-08 | Grouping of Soundings in ENC Updates | Add guidance in new version of the DCEG. | JW | Pending | GitHub #5.
PortSG-09 | Grouping of Soundings in ENC Updates | Inform the ENCWG chair so this guidance can be considered for inclusion in the UOC. | JW | Pending | GitHub #5.
PortSG-10 | Portrayal Catalogue 1.1.1_Endorsement and update to registry | Upload latest draft of the PC to the new Github repository. Any futher changes to be timely reflected and tacked in this location. | NIWC | Completed | GitHub #6. | Complete - recommend close issue
PortSG-11 | Portrayal Catalogue 1.1.1_Endorsement and update to registry | Publish 'official' PC version 1.0.1 (in line with FC and DCEG 1.0.1). | IHO Sec/KHOA | Pending | GitHub #6.
PortSG-12 | Quality of Bathymetric Data - Decide portrayal requirements | Update PC draft as required. | NIWC | In Progress | GitHub #7. | Close on confirmation that desired portrayal is to use new CATZOC attribute and implement S-52 portrayal.
PortSG-13 | Quality of Bathymetric Data - Decide portrayal requirements | DCEG subWG to update QoBD modelling as required. | JW | Completed | GitHub #7.
PortSG-14 | Portrayal of shared edges | Test proposed solution and report back to S-101PT7. | NIWC | In Progress | GitHub #8. | Ongoing
PortSG-15 | Id values in portrayal catalogues | Add xmlID values to the registry. | JW | Pending | GitHub #9.
PortSG-16 | Id values in portrayal catalogues | Update PC with xmlID values. | NIWC | Pending | GitHub #9. | Awaiting completion of PrtSG-15
PortSG-17 | Light descriptions with unknown lightCharacteristic | Update PC to support the interpretation endorsed by the S101PT. | NIWC | In Progress | GitHub #10. | Recommend close
PortSG-18 | S-101 PC and Mariners viewing groups | Remove mariner's viewing groups/ viewing group layers from S-101 PC. | NIWC | Completed | GitHub #12. | Recommend close: * Mariners groups have been removed from the PC * Recommend notify (Julia / Raphael?) to update S-98 with guidance for OEMs: * Application developers are responsible for implementing support for mariners / manufacturers features - Using viewing groups as specified in C-10.5.5 - Using viewing group layers as specified in C-10.5.6 - Using independent 'Mariners' display modes as specified in C-10.6
PortSG-19 | S-101 PC and Mariners viewing groups | Liaise with S-100WG Chair and IEC T80 representative to resolve this issue outside the S-101 PC. | NIWC | Completed | GitHub #12. | S-98? See above.
PortSG-20 | SY(CHDATD01) symbol has no portrayal parameters. | Portrayal Register - Add new Viewing Group Layer to manage the independent selection (on/off) of SY(CHDATD01). | JW | Pending | GitHub #13.
PortSG-21 | SY(CHDATD01) symbol has no portrayal parameters. | Implement changes to on-shore ECDIS. | NIWC | Pending | GitHub #13. | Awaiting final guidance
PortSG-22 | Guidance on Date dependent and Safety check | Report back to S-101PT7. [Note that S-64 3.0.0 expanded the test data for this purpose.] | NIWC | In Progress | GitHub #14. | Requested feedback from Furuno and 7cs: * 7cs: no response * Furuno: Always uses mariner selected date(s)
PortSG-23 | IEC 61174 (4.18) Default selector requirement | Inform the ENCWG chair. | TR | Pending | GitHub #15.
PortSG-24 | IEC 61174 (4.18) Default selector requirement | Propose S-98 amendment to S-100WG chair. | TR | Pending | GitHub #15.
PortSG-25 | IEC 61174 (4.18) Default selector requirement | Update PC and on-shore ECDIS as required. | NIWC | Completed | GitHub #15. | Recommend close - PC has been updated so that viewing group layers controlling text are not included in any catalogued display mode (e.g. text groups are not in base, std, or other)
PortSG-26 | OEM guidance on application of changes to viewing groups | Submit paper to S-100WG recommending update to S-98 Annex C. | NIWC | In Progress | GitHub #16. | Recommend close and address in S-98
PortSG-27 | S-101 Feature dependency issues | Submit change proposal to TSM8/S-100WG6 recommending update to S-100 Part 9a. | NIWC | In Progress |  | Will submit to next S-100WG. PC currently implements this proposed change: https://github.com/IHO-S100WG/TSM8/blob/main/6.X-1%20Multiple%20viewing%20groups%20per%20drawing%20instruction/Allow%20multiple%20viewing%20groups%20per%20drawing%20instruction.pdf
PortSG-28 | Independent Mariner Selections | Report back to S-101PT7. [Note that S-64 3.0.0 expanded the test data for this purpose.] | NIWC | Pending | GitHub #18. | Awaiting feedback
PortSG-29 | ENCWG 'ENC Display subWG' | Submit portrayal change proposals identified by the ENC Display Sub-Group to the S-101PT using the online 'S-101 Portrayal request form'. | CM | Pending | GitHub #19.
PortSG-30 | ECDIS Chart 1. | Seek volunteers (or HSSC funding) to develop the first 'S-101 ECDIS Chart 1' (or ECDIS Chart S-101) version as per the requirements listed in S-52 Ed 6.1.1 (3.1.4) and S-52 PL Part I (17.7 & 18.2). | TR | Pending | GitHub #20.
PortSG-31 | ECDIS Chart 1. | Inform decision and way forward to S-100WG Chair. | TR | Pending | GitHub #20.
PortSG-32 | S-101 ECDIS Performance requirements log. | Create, update and present S-101 ECDIS performance requirements' log prototype to S-101PT7. | AS | In Progress | GitHub #21.
PortSG-33 | Light Sector portrayal - Sector arc extension | Continue discussions in Github and report final recommendation at S-101PT7. | AS | In Progress | GitHub #26.
PortSG-34 | Review new portrayal requirements related to S-101 new/remodelled features and attributes | Finalise review by 04 April 2021; seek Portrayal Sub-Group approval and liaise with NIWC and KHOA as required to update PC as required. Report progress to S-101PT7. | AS | In Progress
PortSG-35 | Small Craft moorings - Update symbology | Report progress at S-101PT7. | AS | In Progress | GitHub #28.
PortSG-36 | flipBearing attribute for TextPlacement | Report progress at S-101PT7. | AS | In Progress | GitHub #29.

## Completed_Closed
Source | Action | Detail | Lead | Status | Remarks
S-101PT4-01 | Finish the S-57 to S-101 Conversion Report | Incorporate comments received. Compile a list of edge cases from the UOC/DCEG part of the study. Release the test dataset containing a set of the edge cases for testing converter technology. | Jonathan Pritchard | CLOSED | Overtaken by events - this work is now being done by the S-57 to S-101 Conversion Sub-Group (ENCWG).
S-101PT4-02 | S-101 ENC Portrayal | Determine all portrayal gaps, Design portrayal on gapped features/types Sub-WG to work on refining the current symbols, line styles, sounding structure/portrayal, colours/palettes etc… . User feedback is to be sought as part of the work. | US/NOAA NCWG Chair [Members: IHO Sec, IALA, Carnival, Germany, Teledyne-Caris, IIC, NZ, KHOA, US (NOAA), US (NGA), Netherlands (DGWG Chair) | Complete
S-101PT4-03 | Update S-101 to final IHO GI Registry | Update content of S-101 for any changes based on IHO GI Registry deconfliction work | Jeff Wootton | Complete - all draft S-101 Edition 1.1.0 items aligned to the Registry.
S-101PT4-04 | Validation Checks | Denmark and IHO Sec to investigate incorporating the S-100 product validation checks into a database and developing a GUI interface. | Bruno Cardoso (DK) Tony Pharaoh (IHO Sec.) | CLOSED | Task OBE checks now fall within Validation Check Sub Group. New action to be taken. Agenda item 4.4 refers.
S-101PT4-05 | S-57 to S-101 Convertor | IHO Sec to include entries in the S-57 to S-101 conversion spreadsheet for new items included in S-101 Edition 1.0.0. | Jeff Wootton | Completed
S-101PT4-08 | S-57 to S-101 Portrayal Gap Analysis | Provide the spreadsheet identifying the new S-101 data modelling (refer action for Agenda item 4.4) to the NCWG Chair for consideration of the NCWG of new symbology requirements at its next meeting. | Jeff Wootton | Completed (August 2019)
S-101PT4-09 | Offshore Solar Farms | Netherlands to draft a definition for “solar farm” and submit to the Registry Manager (for registration). Registry Manager to include the new item in the DCEG. | AM/Jeff Wootton | Completed
S-101PT4-10 | DCEG Changes for S-101 Edition 2.0.0 | Continue application of draft changes to the S-101 DCEG in line with the changes approved by the S-101PT4 meeting and changes to the FCD Register. For further review at S-101PT5. | Jeff Wootton | Completed
S-101PT4-11 | DCEG Changes for S-101 Edition 2.0.0 | Discuss additional encoding guidance for the population of the depthRangeMinimum attribute for isolated shoal depth areas. | JW/AS/MH/RF | Completed | Refer to outcomes of paper presented to ENCWG Catch-Up meeting (February 2021). Amendments applied to DCEG Ed. 1.0.1 iaw changes to UOC approved at this meeting.
S-101PT4-12 | Proposal of Alternate Options for Display Scale | Propose to the S-100WG Chair to include an item on loading strategy to be discussed at the next Test Strategy meeting. | Megan Bartlett (US) | Completed
S-101PT4-13 | Quality of Horizontal Measurement | Submit paper 5.4 identifying inconsistencies (with definitions) to the next DQWG. | Christian Mouden (FR) | Completed | See action S-101PT5-01.
S-100TSM7 | Visualization of Quality of Bathymetric Data | What extent does DQWG findings reflect in S-101? - Email Rogier and Yong | S-101PT | Completed | See action S-101PT5-02.
S-100TSM7 | Alerts and Indications | S-52 A&I needs to be captured in S-101 | US/NIWC | CLOSED | This is a Policy issue. There is no requirement for A&I in S-101, but there is a requirement in S-52.
S-100TSM7 | Alerts and Indications | Need to define what those mappings are (not all S-52 in S-101 and vice versa) | US/NIWC | CLOSED | Need to implement S-101 A&I in the PC using S-52 as guidance since there is nothing to guide in S-101. We are doing / have done the technical issue by adding A&I to S-101 PC.
S-100TSM7 | Alerts and Indications | Sumbit full proposal to S-100WG5 | US/NIWC | Completed
S-101PT5-01 | Quality of Horizontal Measurement | Develop proposal for quality of horizontal measurement based on S-101PT4-5.4 discussion. | CM | Completed | Refer to paper S-101PT6-14. Approved at S-101PT6 and decisions incorporated in DCEG Edition 1.0.1.
S-101PT5-02 | Visualization of Quality of Bathymetric Data | Develop proposal for S-101PT consideration on possible amendments to S-101 modelling of the Quality of Bathymetric Data feature based on the outcome of the DQWG investigation of improved portrayal of this information in ECDIS (for TSM8). | JW | Completed | Refer to paper S-101PT6-12. Approved at S-101PT6 and decisions incorporated in DCEG Edition 1.0.1. Note however that further work will be required in portrayal.
S-101PT5-04 | Changes Intoduced in S-101 Edition 1.1.0 DCEG | PT members interested in participating in the S-101 DCEG Sub-Group to notify JW by email (jeff.wootton@iho.int) at the earliest opportunity. | S-101PT | Completed
S-101PT5-05 | Changes Intoduced in S-101 Edition 1.1.0 DCEG | Redline version of the S-101 DCEG to be sent to S-101 DCEG Sub-Group members for review (before end of September 2020). | JW | Completed | Email to Sub-Group 28/10/20.
S-101PT5-06 | Changes Intoduced in S-101 Edition 1.1.0 DCEG | The definition as to what constitutes and “editorial” change to the S-101 DCEG is to be determined, in consultation with the S-101PT Executive (September 2020). | JW/Chair/Vice-Chair/YB | Completed | Email correspondence with S-101PT Executive 05-07/10/20.
S-101PT5-08 | Portrayal | PT members interested in participating in the S-101 Portrayal Sub-Group to notify the Vice Chair and JW by email (alvaro.sanchez@defence.gov.au and jeff.wootton@iho.int) at the earliest opportunity. | S-101PT | Completed
S-101PT5-10 | Validation Checks | PT members interested in participating in the S-100 Data Validation Sub-Group to notify the Chair and JW by email (thomas.richardson@ic-enc.org and jeff.wootton@iho.int) at the earliest opportunity. | S-101PT | Completed
S-101PT5-11 | S-101PT Work Plan | The draft S-101 Work Plan to be forwarded to the S-100WG Chair for S-100WG endorsement and inclusion in the S-100WG report to HSSC12; and to the IHO Secretariat for posting on the S-101PT page of the IHO web site (September 2020). | Chair | Completed | Included in S-100WG report (S-101PT Report) to HSSC12.
S-101PT5-12 | S-101PT Work Plan | Establish an Issues and Risk Log and design an S-101 Engagement Plan (S-101PT6). | Chair | Completed | Refer to paper S-101PT6-11. Completed - see new actions S-101PT6-13 and S-101PT6-14.
S-101PT5-14 | Navigational Purposes | A dedicated meeting of a small group to be convened to discuss the issues raised in Paper S-101PT5-11 (October 2020). Possible feedback required to TSM8. | NIWC (lead)/Chair/IHO Sec | CLOSED | Proposal withdrawn.
S-101PT5-12 | S-101PT Work Plan | Establish an Issues and Risk Log and design an S-101 Engagement Plan (S-101PT6). | Chair | Completed | Refer to paper S-101PT6-11. Completed - see new actions S-101PT6-13 and S-101PT6-14.
S-101PT5-15 | VALSOU Decimal Places | Paper S-101PT5-12 to be considered by the DCEG Sub-group (November 2020). | S-101 DCEG Sub-Group | CLOSED | Resolution amended to 0.01 metres for testing purposes. Closed pending testing recommendations. NOTE: ENCWG has agreed to 1.0m resolution.
S-101PT5-16 | VALSOU Decimal Places | Paper S-101PT5-12 to be submitted to the ENCWG for consideration. | IC-ENC | Completed
S-101PT5-17 | Fairway Portrayal | Paper S-101PT5-14 to be considered by the Portrayal Sub-Group (November 2020). | S-101 Portrayal Sub-Group | Completed | See Port SG Report S-101PT6-07 and Action S-101PT6-06.
S-101PT5-18 | Light Sector Portrayal | Paper S-101PT5-15 to be considered by the Portrayal Sub-Group (November 2020). | S-101 Portrayal Sub-Group | Completed | See Port SG Report S-101PT6-07 and Action S-101PT6-06.
S-101PT5-19 | Quality of Bathymetric data and ECDIS Performance | Paper S-101PT5-16 to be considered by the Portrayal Sub-Group (November 2020). | S-101 Portrayal Sub-Group | Completed | See Port SG Report S-101PT6-07 and Action S-101PT6-06.
S-101PT5-20 | Grouping of Soundings | Paper S-101PT5-17 to be considered by the Portrayal Sub-Group (November 2020). | S-101 Portrayal Sub-Group | Completed | See Port SG Report S-101PT6-07 and Action S-101PT6-06.
S-101PT5-22 | S-57 to S-101 Encoding | Liaise with the S-100WG lead on S-57 to S-101 conversion (Jonathan Pritchard) on strategies that may be adopted for S-57 datasets to facilitate S-57 to S-101 conversion | S-101 DCEG Sub-Group | Completed | Ongoing liaison with conversion sub group is required. Note drafting of S-57 to S-101 Conversion Guidance document for data producers (in development). S-101PT7: S-57 to S-101 Conversion to be included as a standing Agenda item for S-101PT meetings.
S-101PT5-24 | NIWC Testbed Update | Portrayal and ECDIS Performance Sub-Group to discuss the following issues raised in the NIWC Testbed Update report (S-101PT5-21 – listed by the associated Presentation slides): Slides 4, 12, 16, 17, 22, 25, 26, 28, 32, 33, 34, 35, 36, 37. | S-101 Portrayal Sub-Group | Completed | See Port SG Report S-101PT6-07 and Action S-101PT6-06.
S-101PT5-25 | NIWC Testbed Update | NIWC to report to the S-100WG (TSM8) the following issues raised in the NIWC Testbed Update report (S-101PT5-21 – listed by the associated Presentation slides): Slides 15, 21, 27. | NIWC | Completed | Slide 15: OBE per latest S-101 Part 10a redlines Slide 21: SevenC's indicated they would submit proposal to standardize encoding of boolean attributes Slide 27 (invalid geometries): Ensure validation check is present? Completed - See new Action S-101PT6-01.
S-101PT5-26 | NIWC Testbed Update | Paper to be developed to describe the implementation of units of measurement for weights and measures (in conformance to S-52 clause 10.8) (for S-101PT6). | Chair/RM | Completed | See agenda item S-101PT6-INF-01. See Paper TSM8-6.2.
S-101PT6-04 | S-101PT6-06 - DCEG Update | Prepare final redline and clean versions of S-101 DCEG Edition 1.0.1 and publish on the IHO web site and the IHO GI Registry by end of February 2021. Include any changes approved as a result of discussions on Paper S-101PT6-12 and any other Papers for S-101PT6. | JW | Completed | DCEG Edition 1.0.1 posted 01 March 2021.
S-101PT5-24 | NIWC Testbed Update | Portrayal and ECDIS Performance Sub-Group to discuss the following issues raised in the NIWC Testbed Update report (S-101PT5-21 – listed by the associated Presentation slides): Slides 4, 12, 16, 17, 22, 25, 26, 28, 32, 33, 34, 35, 36, 37. | S-101 Portrayal Sub-Group | Completed | See Port SG Report S-101PT6-07 and Action S-101PT6-06.
S-101PT5-25 | NIWC Testbed Update | NIWC to report to the S-100WG (TSM8) the following issues raised in the NIWC Testbed Update report (S-101PT5-21 – listed by the associated Presentation slides): Slides 15, 21, 27. | NIWC | Completed | Slide 15: OBE per latest S-101 Part 10a redlines Slide 21: SevenC's indicated they would submit proposal to standardize encoding of boolean attributes Slide 27 (invalid geometries): Ensure validation check is present? Completed - See new Action S-101PT6-01.
S-101PT5-26 | NIWC Testbed Update | Paper to be developed to describe the implementation of units of measurement for weights and measures (in conformance to S-52 clause 10.8) (for S-101PT6). | Chair/RM | Completed | See agenda item S-101PT6-INF-01. See Paper TSM8-6.2.
S-101PT6-02 | DCEG Update | PT members interested in participating in the Associations Sub-Group to notify JW by email (jeff.wootton@iho.int) at the earliest opportunity. | S-101PT | CLOSED | IHO Sec (lead), TR, RM, JP, DG, KD, HB, RF, VB, MB, HA, RB Note paper TSM8-6.8.
S-101PT6-03 | DCEG Update | PT members interested in participating in the S-101 Dataset Load/Unload Sub-Group to notify JW by email (jeff.wootton@iho.int) at the earliest opportunity. | S-101PT | CLOSED | CM (lead), JW, RG, PlB, MB, VB, KD, HA, RM, HB, IK, AS, DG
S-101PT6-04 | DCEG Update | Prepare final redline and clean versions of S-101 DCEG Edition 1.0.1 and publish on the IHO web site and the IHO GI Registry by end of February 2021. Include any changes approved as a result of discussions on Paper S-101PT6-12 and any other Papers for S-101PT6. | JW | Completed | DCEG Edition 1.0.1 posted 01 March 2021.
S-101PT6-07 | Portrayal Progress | Add a dedicated area for S-101 Portrayal Catalogue development under the IHO GitHub. | IHO Sec | Completed | Completed 23/04/21: https://github.com/iho-ohi/S-101_Portrayal-Catalogue
S-101PT6-09 | Validation Update | Investigate the possibility of submitting a request to fund the development of S-101 test datasets utilising the IHO Special Projects Fund (for HSSC13). | Chair | Completed | Request passed to S-100WG as part of HSSC13 Report.
S-101PT6-13 | S-101 Roadmap | PT members interested in participating in the S-101 Roadmap Drafting Group to notify the Chair by email (thomas.richardson@ic-enc.org) at the earliest opportunity. | S-101PT | CLOSED | Chair (lead), JW, VP, HP, AS, RG, LH
S-101PT6-14 | S-101 Issues Log | PT members to review the draft S-101 Issues Log and supply any amendments or additions by email (thomas.richardson@ic-enc.org and jeff.wootton@iho.int) at the earliest opportunity. | S-101PT | CLOSED
S-101PT6-15 | Bathymetric Data Quality | Changes to be applied to the draft S-101 DCEG Edition 1.0.1 as approved by the S-101PT in regard to the recommendations on remodelling of S-101 features based on the DQWG recommendations related to improving the indication of bathymetric data quality in ECDIS (for inclusion in finalised Edition 1.0.1 DCEG). | JW | Completed | JW email 01/03/21.
S-101PT6-16 | Portrayal of Small Craft Mooring Areas | Submit a proposal to the Portrayal Sub-Group requesting the development of new symbology for the portrayal of small craft mooring areas in S-101. | AS | Completed | Portrayal GitHub repository Issue #28.
S-101PT6-17 | Quality of Horizontal Measurement | Amend the allowable values of the attribute qualityOfHorizontalMeasurement in S-101 to the values 4 (approximate) and 5 (position doubtful), for S-101 DCEG Edition 1.0.1. | JW | Completed | JW email 01/03/21.
S-101PT6-19 | Placement of Texts in S-101 | PT members interested in participating in the S-101 Text Placement Sub-Group to notify CM by email (christian.mouden@shom.fr) at the earliest opportunity. | S-101PT | Closed | CM (lead), IK, KO, HA Note paper TSM8-6.15